# BEGINNINGS FUND ETHIOPIA INVESTMENT PLAN

Ethiopia Investment Plan Overview

| Grantees: | Investments Presented: - Federal Ministry of Health (FMOH) – Reproductive, Maternal, Newborn, and Child Health (RMNCH) Compact Investments Planned for 20 May 2026 Investment Committee: - Government of Ethiopia - Federal Ministry of Health (FMOH) - International Institute for Primary Health Care – Ethiopia (IPHCE) - Addis Ababa University (AAU) – Saving Little Lives (SLL) 360 - CHAI Ethiopia - Infrastructure Development |
| --- | --- |
| Implementer(s) (if different to Grantee): | - Ethiopian Pharmaceuticals Supply Service (EPSS) - Ethiopian Society of Obstetricians and Gynecologists (ESOG) - Ethiopian Pediatrics Society (EPS) - Regional Health Bureaus (Afar, Amhara, Central Ethiopia, Oromia, Sidama, Somali, South Ethiopia, and Tigray) |
| Geographic Focus: | Eight regions (Afar, Amhara, Central Ethiopia, Oromia, Sidama, Somali, South Ethiopia, and Tigray); 46 districts (Woredas); and 210 target facilities and national support |
| Amount: | USD90million |
| Co-Investment/Complementary Funding: | USD506million in Government commitments and USD220million in complementary funding from other donors and partners. |
| Term: | 60 months (1 July 2026 – 30 June 2031) |
| Investment Description and Impact Goals: | Alongside the Government of Ethiopia, led by the Federal Ministry of Health (MOH), this investment will increase availability of quality MNH commodities, increase the number, competency, and skills-mix of the MNH workforce, support maternal and neonatal unit infrastructure development, improve the quality and use of MNH data and the efficiency of referral systems, and enhance advocacy and community engagement initiatives to improve uptake of facility-based MNH services. Through this investment, the Beginnings Fund will help catalyse Ethiopia’s goal to accelerate progress towards ending preventable maternal and newborn deaths and save ~86,124 lives by 2031: - reducing maternal mortality by 15% from 195 to 166 per 100,000 live births - reducing stillbirths by 15.7% from 19 to 16 per 1,000 live births - reducing neonatal mortality by 26% from 25 to 20 per 1,000 live births |
| Pathway to Impact: | See Annex A |
| Governance and Management: | The MOH will lead overall implementation of the Ethiopia Investment Plan. The governance structure is closely aligned with that of existing programmes, including joint annual and quarterly reviews of the national maternal and newborn health (MNH) programme, to ensure efficiency and alignment with the government’s One Plan, One Budget, One Report framework. Beginnings Fund will finalize a Memorandum of Understanding with the Government of Ethiopia outlining key commitments and measures of success once the Ethiopia Investment Plan is approved. A Steering Committee, co-chaired by the Minister of Health, and the Beginnings Fund CEO (with the Programme Director as an alternate); and comprising representatives from EPSS, the Maternal, Child, and Adolescent Health Lead Executive Office (LEO), and the Regional Health Bureaus, will meet biannually to provide strategic oversight, address major bottlenecks, and approve annual budgets and work plans. A Programme Management Team, comprising technical leads from MOH (including Human Resources for Health, Pharmaceutical and Medical Devices, Infrastructure, and Data and Digital Health LEOs) and the main implementing partners (IPHCE, SLL360, and CHAI), and the Beginnings Fund Investment Team (Program Director, Senior Country Program Officer, Director of Statistics and Impact Evaluation, and Director of Finance and Operations) will manage implementation, monitor progress, and implement any course corrections. The team will meet weekly during the initial months of implementation and shift to monthly meetings once the program is underway. Audits: This programme will utilise annual audits conducted by the Office of the Federal Auditor General of Ethiopia, and from an independent party as commissioned by Beginnings Fund. The audit reports will be reviewed by the Audit and Risk Oversight Committee (AROC) . |
| Reporting: | A consolidated annual narrative and financial report will be prepared by the MOH, with support from IPHCE, and submitted by 1 September each year. |

Acronyms and Definitions

| BEmONC | Basic Emergency Obstetric and Newborn Care |
| --- | --- |
| CE-MPMM | Confidential Enquiry into Maternal and Perinatal Morbidity and Mortality |
| CEmONC | Comprehensive Emergency Obstetric and Newborn Care |
| CHAI | Clinton Health Access Initiative |
| CPAP | Continuous Positive Airway Pressure |
| CS | Caesarean Section |
| DHIS2 | District Health Information System 2 |
| EPHI | Ethiopian Public Health Institute |
| GFF | Global Financing Facility |
| HEP | Health Extension Programme |
| HEWs | Health Extension Workers |
| HPV | Human Papillomavirus |
| HSTP | Health Sector Transformation Plan |
| ICMNCI | Integrated Community Case Management of Newborn and Childhood Illness |
| IPCG | Intrapartum Care Guideline |
| IST | In-Service Training |
| KMC | Kangaroo Mother Care |
| LEO | Lead Executive Office |
| MCH | Maternal and Child Health |
| MEOWS | Modified Early Obstetric Warning Score |
| MMEIG | Maternal Mortality Estimation Inter-Agency Group |
| MMR | Maternal Mortality Ratio |
| MOH | Ministry of Health |
| OB/GYN | Obstetrician/Gynaecologist |
| PHC | Primary Health Care |
| SBA | Skilled Birth Attendance |
| SCM | Supply Chain Management |
| SDG | Sustainable Development Goals |
| SLL360 | Saving Little Lives 360 |
| TOT | Training of Trainers |
| UHC | Universal Health Coverage |
| WHO | World Health Organization |

Situational Analysis

Ethiopia, Africa’s second most populous country, has an estimated population of 110 million, including ~30 million women of reproductive age (15–49 years). With an annual birth rate of 3.36%, demand for quality maternal and newborn health (MNH) services is high. Over the past two decades, Ethiopia has made substantial progress, reducing maternal mortality by 78% (from 871 in 2000 to 195 per 100,000 live births) , neonatal mortality by 45% (from 49 to 25 per 1,000 live births), and stillbirth rates from 15 to 10 per 1,000 births, between 2020 and 2024. The recently released Ethiopian Demographic and Health Survey (EDHS) 2024-2025 indicates an increase in facility births from 48% to 61%, and a significant rise in the percentage of deliveries assisted by skilled providers, from 12% in 2011 to 64% in 2024-2025. These gains are attributed to sustained investments in primary health care, health workforce expansion, essential commodities, and improved antenatal care coverage.

Despite this progress, facility-based delivery remains very low, and the rate of postnatal care coverage within 48 hours of birth is only at 35%. Persistent system-level constraints, including human resource shortages, commodity stock-outs, weak referral systems, inadequate infrastructure, limited health financing, and poor data quality, continue to impede equitable access to quality care, particularly in rural and pastoralist regions. Ethiopia is administratively divided into 12 regions, two city administrations, 115 zones, and 1,054 woredas (districts), with 77% of the population living in rural areas. This decentralised structure with resource-limited infrastructure, underpins significant service coverage disparities between regions and woredas within the same region. Antenatal coverage ranges from 12.7% in Somali and 57% in Tigray to over 90% in Addis Ababa, while facility delivery rates vary from 33% in Afar to over 98% in urban regions. Marked inconsistencies between survey data and routine DHIS2 reports highlight ongoing challenges in data quality and its use for decision-making.

Maternal mortality is driven primarily by obstetric haemorrhage (57%), hypertensive disorders (19%), and infections (18%), with all three “delays” contributing significantly: delays in seeking care (36%), delays in reaching health facilities due to poor transport and referral systems (29%), and delays in receiving adequate care due to insufficient facility readiness, particularly in rural regions (35%). Only 10% of delivery facilities have access to blood transfusion services. This drops to 3% in the more rural areas. Although all hospitals and CEmONC health centres are mandated to provide caesarean delivery services, only 11% of facilities do so nationally, with extreme regional inequities. Neonatal mortality rate (NMR) constitutes 57% of all under-five mortality and accounts for 88% of infant deaths. The leading causes of neonatal deaths include prematurity (45%), infections (30%), and birth asphyxia (13%), primarily stemming from inadequate facility-based newborn care, particularly concerning neonatal resuscitation, infection prevention and management, and specialized care for small and sick newborns. Investment in neonatal intensive care units (NICUs), skilled healthcare personnel, and essential supplies such as oxygen, antibiotics, and thermal care equipment is vital for these statistics to improve.

The Government of Ethiopia has prioritized MNH through progressive policy frameworks, including the revised National Health Policy (2024), Health Sector Transformation Plans, the Reproductive Health Strategic Plan (2021–2025), and the 2022 Newborn and Child Survival Roadmap. These strategies emphasize equity, quality, advanced maternal and neonatal care, and alignment with SDG 2030 targets. However, foundational system constraints persist. Essential MNH commodity availability stands at only 39%, disrupting continuity of care; equipment functionality at 74%, and cold-chain systems critical for MNH commodities such as vaccines and oxytocin remain weak. The health workforce density (10.3 per 10,000) is far below the WHO recommended ratio of 44.5 per 10,000 needed to achieve Universal Health Coverage, with acute urban rural disparities, high attrition, and insufficient skills mix. There is a persistent mismatch between supply and demand due to poor workforce planning, inequitable distribution, weak governance, low motivation, and limited absorption capacity. High turnover, especially in rural and conflict-affected areas, has led to facility closures and compromised service delivery, particularly in maternal and child health. Weak regulatory enforcement, low licensing rates, inconsistent Continuing Professional Development (CPD), and poor-quality training undermine competency.

Referral systems are fragmented, under-resourced, and poorly equipped, characterized by weak communication, poor documentation, fragmented referral protocols, and limited use of digital tools. Budgetary constraints hinder the coverage of fuel costs for existing ambulances, all of which negatively impact timely and effective referrals.  Infrastructure gaps, particularly in electricity, water, and connectivity, severely compromise service readiness. The shortfall in these necessities threatens the availability of essential services such as 24-hr clean and safe delivery, emergency obstetric care, neonatal intensive care, safe surgery, basic laboratory and imaging diagnostics services, and infection prevention and control (IPC).  Only 54% of facilities have reliable electricity, and 32% have communication tools.

Resource constraints, including limited infrastructure and insufficient technical capacity among healthcare workers, have hindered scale up of critical data initiatives such as expansion of the DHIS2 (version 2.36), the electronic Community Health Information System (eCHIS), and additional systems, including the Electronic Medical Records (EMR), Smart-care ART, HRIS, and supply chain platforms. As a result, health facilities and communities rely on a hybrid system of electronic and manual data recording, requiring manual entry into DHIS2, compromising the timeliness and reliability of data for evidence-based decision-making.

MNH financing remains constrained, with government health expenditure at 25.6% and out-of-pocket spending at 40.5%. The SDG Performance Fund has played a critical role in improving coverage, equity, and resilience, demonstrating measurable reductions in maternal and child mortality and strengthening primary care delivery. However, declining donor contributions underscore the need for increased domestic financing and sustainable co-financing mechanisms.

Recurrent external shocks, including conflict and COVID-19, have reversed gains in several regions, damaging infrastructure, disrupting services, and exacerbating workforce shortages and gender-based violence. Strengthening health system resilience is essential to protect past investments and accelerate progress.

In collaboration with its partners and stakeholders, the Ministry of Health is planning to address these foundational barriers and accelerate progress toward Ethiopia’s maternal and newborn health goals.

Strategic Approach and Operational Plan

The Beginnings Fund will partner with the Government of Ethiopia through the Federal Ministry of Health (FMOH) to accelerate reductions in maternal and neonatal mortality and prevent stillbirths to reach Ethiopia’s 2030 goals and save ~86,124 lives. Beginnings Fund investments will support the scale-up of priority interventions targeted at the drivers of maternal and neonatal morbidity and mortality and stillbirths; improve the availability and use of quality maternal and newborn health (MNH) commodities and services; increase the number, improve competency, and optimise skills-mix of the MNH workforce; and reinforce MNH systems, including infrastructure development, referral systems, data and quality improvement, and advocacy. Investments will further advance Ethiopia’s Health Sector Development and Investment Plan (HSDIP 2023/24–2025/26) through direct support to government entities, including the MOH, the International Institute of Primary Health Care-Ethiopia (IPHCE), and Ethiopia Pharmaceutical Supplies Services (EPSS), and eight regional health bureaus.

To ensure targeted and impactful investments, a multidisciplinary technical team, led by the Federal  Ministry of Health, Maternal and Child Health Executive Office, with representatives from EPSS, IPHCE, Regional Health Bureau program teams, key partner organizations, and the Beginnings Fund Investment Team, conducted a comprehensive analysis of Ethiopia’s maternal and newborn health data, reviewed current MNH investments and those in the pipeline supported by other partners including the US Department of State, Gates Foundation, World Bank and GFF,  to identify priority areas for this investment plan.

Based on maternal and neonatal morbidity and mortality data, the team first identified 96 districts that significantly contribute to the national burden. From this, 46 high-burden districts were further prioritized based on rankings across three major mortality indicators and gaps in partner support. These districts represent the highest potential for impact, accounting for approximately 33% of maternal deaths and 40% of neonatal mortality nationwide. The core team then assessed MNH service delivery performance and health system readiness within these districts, focusing on the availability of essential services such as Emergency Obstetric and Newborn Care (EmONC), Neonatal Intensive Care Units (NICU), and Skilled Birth Attendant training. This analysis highlighted significant gaps in service coverage and workforce distribution. Health facilities along the referral pathway, including hospitals and selected health centres, were identified for intervention in consultation with regional and Woreda health offices. All primary and secondary hospitals in these districts were included in the final selection, with a maximum of three health centres in each hospital’s catchment area selected based on live birth numbers.

The Beginnings Fund investment will target 210 facilities across 46 districts from eight regions with the highest rates of maternal and neonatal deaths and stillbirths. The target facilities consist of 55 hospitals (28 primary and 27 secondary hospitals) and 155 health centres (17 to be upgraded to provide Comprehensive Emergency Obstetric and Neonatal Care [CEmONC] and 138 providing Basic Emergency Obstetric and Neonatal Care [BEmONC]), and regional hospitals along the referral pathway will benefit from the Beginnings Fund package of interventions. Through this investment, the Fund will reinforce ongoing government efforts to improve MNH outcomes by enhancing the timeliness and quality of antenatal care at primary level facilities and increasing access to emergency and essential services closer to communities.

To ensure women receive early and high-quality antenatal care (ANC) services, point-of-care ultrasound (POCUS) will be introduced in all target facilities to meet the national goal of providing an ultrasound scan before 24 weeks, ensuring early identification and management of high-risk pregnancies. This will be integrated with targeted education and community mobilization efforts that are already in place to encourage pregnant mothers to seek care through ANC services. Access to Antenatal corticosteroid (ACS) therapy will be improved through training on the appropriate use of this treatment for pregnancies at risk of preterm birth in all target facilities, particularly in health centres where ACS is not consistently provided due to a lack of health worker skill and confidence in its administration, despite approval to use at the health centre level in national guidelines. This investment will also support the scale up of routine blood pressure monitoring and improved coverage of magnesium sulphate for all pregnant women during ANC, intrapartum, and postnatal periods to improve prevention, early detection, and management of hypertensive disorders of pregnancy.

To improve intrapartum care and reduce complications during labour and delivery, including stillbirths and birth asphyxia from prolonged labour, Beginnings Fund will support the dissemination and uptake of the new National Intrapartum Care Guidelines and WHO’s Labor Care Guide (LCG) to replace the traditional partograph for management of labour progression in all target facilities. Clinical trials have shown that the LCG can reduce rates of caesarean section and unnecessary labour augmentation. Digital intrapartum monitoring will be introduced to adequately detect maternal and foetal distress and to ensure timely access to caesarean sections in all CEmONC facilities. Beginnings Fund will also support the rollout of the national post-partum haemorrhage (PPH) treatment guidelines and the rollout of the PPH bundle in all target facilities.

To improve the quality of newborn care, this investment will support, across all target facilities, the implementation of Level 1 Essential Newborn Care (ENC); Level 2 Small and Sick Newborn Care (SSNC) with KMC Plus which includes immediate Kangaroo Mother Care (iKMC) and specialised lactation support; and the introduction of Newborn Evaluation, Stabilization, and Transition (NEST) teams (comprised of neonatologists, paediatricians, neonatal nurses, midwives, and other trained professionals) to provide immediate post-birth stabilisation and resuscitation. It will also support Level 3 neonatal intensive care units (NICU) across all target hospitals. Blended Integrated Management of Newborn and Child Illness (IMNCI) training will be provided to outpatient health providers in all target facilities to manage newborn illnesses, including Possible Serious Bacterial Infection (PSBI) at the community level. Two randomised trials conducted by Addis Ababa University (AAU) in collaboration with WHO showed that outpatient treatment and early discharge (after 48 hours) of low mortality risk PSBI with oral antibiotics were as effective as standard inpatient treatment. These findings suggest that outpatient care and early discharge can reduce healthcare costs, optimize resources, and lower risks of hospital acquired infections. Catchment based mentorship on all interventions will be strengthened across target facilities, where experienced mentors from regional or tertiary hospitals will provide onsite training and coaching in hospitals and health centres in their catchment area.

This investment will support infrastructure development, data quality improvements, and referral system strengthening. Beginnings Fund, in collaboration with CHAI Ethiopia, the FMOH Infrastructure Division, and Mass Design, will support the renovation and expansion of operating room blocks and neonatal care units in eight selected hospitals and 17 health centres. In addition, the expanded facilities will be equipped with both medical and non-medical equipment necessary for delivering quality maternal and newborn health services. Beginnings Fund will support the expansion of the Electronic Medical Records (EMR) system, currently implemented in 172 health facilities across the country, into all 210 target facilities. While the EMR covers a wide range of data, this investment will focus on Maternal and Newborn Health patient level data. Additionally, this investment will facilitate the integration of the EMR system with the existing District Health Information Software 2 (DHIS 2), enabling efficient reporting of maternal and newborn health data from all target facilities.

To strengthen the referral system, MOH will finalize the development of the ongoing Referral APP V2 application. This application aims to enhance patient referrals and improve communication between health centers and hospitals. Once finalized, the application will be installed at all 210 facilities, ensuring an effective and efficient communication system for referrals. The Ministry of Health, through its Regional Health Bureaus (RHBs), will also conduct advocacy and orientation sessions for community leaders, local administrators, and heads of health facilities. This initiative aims to promote the effective use of ambulances within the referral system. Furthermore, the RHBs will work to engage community leaders and local administrators in encouraging early identification and referral of pregnant mothers for timely antenatal follow-ups. They will also facilitate the referral of mothers in labour and those with complications from the community to health facilities through existing referral mechanisms.

Programme Consortium:

- The Government of Ethiopia via the Federal Ministry of Health (FMOH) will provide overall strategic and technical leadership on the implementation of this investment plan, ensuring its alignment with national health priorities and policies, and close collaboration with regional health bureaus. FMOH will also lead procurement and maintenance of MNH commodities, recruitment and deployment of specialists, and strengthening data and referral systems.

- Ethiopian Pharmaceuticals and Supplies Agency (EPSS), the government procurement agency, will manage procurement, warehousing, and distribution of essential MNH commodities (both pharmaceuticals and equipment), supported by Beginnings Fund.

- Regional Health Bureaus will provide technical assistance and programmatic guidance to woredas and health facilities throughout implementation. A designated focal person – a Maternal and Child Health Coordinator – will be recruited for each region under this investment, to manage regional technical assistants and coordinate project activities.

- Ethiopian Society of Obstetricians and Gynecologists (ESOG) and Ethiopian Paediatrics Society (EPS) will be sub-granted through IPHCE to provide training, mentorship, and quality improvement teams to improve the delivery of maternal and newborn service packages.

- Addis Ababa University, which manages Saving Little Lives (SLL) 360, a programme in partnership with NEST360, will work closely with EPS to lead the scale up of key interventions to improve newborn care in target facilities.

- Clinton Health Access Initiative will coordinate and manage infrastructure development activities.

Objective 1: Invest in the scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality

Policy Alignment: Health Sector Development Investment Plan (HSDIP) 2023/24-2025/26, National Reproductive Health Strategic Plan 2021-2025

Beginnings Fund Investment: USD13.6million

Government Commitment: USD 81.3million

Key Implementing Partner(s): MOH (Maternal, Child and Adolescent Health; and Pharmaceutical and Medical Equipment LEOs), IPHCE, ESOG, EPS, and SLL360

Co-/Complementary Investments: Engender Health, Jhpiego (RISE Project), GFF

Beginnings Fund will provide support for 210 target facilities in focus woredas to:

- Strengthen ANC to include early visits and point‑of‑care ultrasound (POCUS) through inclusion into national ANC protocols, and comprehensive training and community mobilization efforts to ensure routine access in all 210 target facilities.

- Improve prevention, early detection, and management of Hypertensive Disorders of Pregnancy (HDP) through training to ensure routine blood pressure monitoring and increase uptake of magnesium sulphate and hypertension drugs per new guidelines.

- Expand Antenatal Corticosteroid (ACS) therapy to all target facilities, particularly health centres, where this service is not consistently provided, through training and digitalized job aids.

- Enhance digital maternal and foetal monitoring to ensure timely identification and management of complications during labour and delivery, through adoption of the new Intrapartum Care Guidelines and the WHO Labour Care Guide.

- Improve prevention, early detection, and treatment of postpartum hemorrhage (PPH) through scale up of the PPH bundle.

- Scale up newborn care through comprehensive training packages for:

- Level 1 Essential Newborn Care (ENC) and Level 2 Small and Sick Newborn Care (SSNC) with KMC Plus (includes immediate Kangaroo Mother Care (iKMC) and specialised lactation support) across all target facilities

- Level 3 neonatal intensive care unit (NICU) across all target hospitals;

- Introduction of Newborn Evaluation, Stabilization, and Transition (NEST) teams to provide immediate post-birth stabilisation and resuscitation, and triage.

- Integrated Management of Newborn and Child Illness (IMNCI) to manage newborn illnesses, including Possible Serious Bacterial Infection (PSBI) for outpatients.

- Conduct quarterly integrated supportive supervision from 55 hospitals to all 155 health centers under the catchment of each hospital

- Conduct joint supportive supervisions in collaboration with professional associations,  at the preservice training colleges in eight regions to help reinforce the MNH service integration into the pre-service curriculum and its implementations

At the national level, Beginnings Fund will provide support for the following activities:

- Support the rollout of the national consolidated comprehensive PPH guidelines, which are already validated and are currently in the process of formal endorsement.

Objective 2: Increase the availability and use of quality priority MNH commodities

Policy Alignment: Health Sector Development Investment Plan (HSDIP) 2023/24-2025/26, National Reproductive Health Strategic Plan 2021-2025

Beginnings Fund Investment: USD23million

Government Commitment: USD170million in matching funds to the RMNCH Compact Key Implementing Partner(s): MOH (Pharmaceuticals and Medical Equipment LEO), EPSS, SLL360, CHAI

Co-/Complementary Investments: USD160million in partner investments into the RMNCH Compact

Beginnings Fund will support the following activities in target facilities across the 46 focus districts

- Procure and distribute lifesaving MNH medicines, including oxytocin, misoprostol, heat stable carbetocin, magnesium sulphate (MgSO₄), tranexamic acid, antibiotics, antihypertensives; and Infection Prevention Control (IPC) supplies for all target facilities.

- Equip all facilities with POCUS, all 55 hospitals with standardized Level 2 NICU equipment, including CPAP systems, and all 17 CEmONC health centers with Level 1 NICU equipment.

- Train 126 biomedical engineers (at least two from each of the 55 hospitals and one from each region) to support the maintenance of medical equipment in focus districts and equip the training workshops with basic tools required for maintenance.

- Scale up MEMIS (Medical Equipment Management Information System) in all 210 facilities to record all equipment and supplies and monitor and manage their functionality.

- Train pharmacists in all target facilities on management and dispensing maternal and newborn health products.

Objective 3: Strengthen and expand the quality, number, and distribution of the MNH workforce

Policy Alignment: Health Sector Development Investment Plan (HSDIP) 2023/24-2025/26, Human Resources for Health Strategic Investment Plan (HRHSIP) 2024 –2030, National Reproductive Health Strategic Plan 2021-2025,

Beginnings Fund Investment: USD7million

Government Commitment: USD42million Key Implementing Partner(s): MOH, IPHCE, and local universities

Co-/Complementary Investments: Health Workforce Fund, ELMA Foundation

Beginnings Fund will provide support for the following activities at facility level:

- Provide scholarships for 120 health care workers to obtain specialisation through Master’s programmes, including in neonatal nursing and midwifery. The scholarship beneficiaries will sign agreements with a commitment to return to their health facilities from which they are selected.

- Support recruitment and deployment of 110 specialists (55 OB/GYN and 55 pediatricians) across the 55 hospitals to provide service delivery and catchment-based training and mentorship.

At the national level, Beginnings Fund will provide support for the following activities:

- Strengthen pre-service training of midwives and specialized nurses by integrating MNH programming into pre-service training curriculum, ensuring it is aligned with national and global standards of care, and introducing low-cost skills-based simulation training (e.g.: MamaNatalie and NeoNatalie from Laerdal).

- Include critical non-clinical training in midwifery and medical colleges, including topics such as Ethics and Human Rights and Respectful Maternity Care.

- Establish MNH simulation skills labs at  1 national and 8 regional levels to provide practical training for pre-service and in-service health workers

- In collaboration with the professional associations, conduct joint supportive supervision in universities and colleges in eight regions to reinforce MNH into the pre-service curriculum.

- Develop and digitize a maternal and neonatal health curricula aligned with national and global guidelines to support the blended training approach for in-service training and continued professional development.

Objective 4: Strengthen critical health system enablers, including MNH infrastructure, data quality improvement, referral systems, and advocacy for greater impact.

Policy Alignment: Health Sector Development Investment Plan (HSDIP) 2023/24-2025/26, National Reproductive Health Strategic Plan 2021-2025 Beginnings Fund Investment: USD23.6million

Government Commitment: USD159million for infrastructure development and USD54million for improving data systems.

Key Implementing Partners: MOH (Infrastructure and Digital LEOs), CHAI

Co-/Complementary Investments: USD60million from World Bank INSPIRER Project to improve women’s and girls’ health through digital health platforms for emergency transport and health extension workers, and HPV vaccinations

Beginnings Fund will support the following activities to enhance MNH service delivery in targeted facilities:

- Renovate operating room (OR) blocks for up to 17 CEmONC health centres and 8 hospitals to improve the quality of emergency obstetric services and surgical capacity for safe MNH operations.

- Renovation and expansion of Basic Newborn Unit (Level 1 NICU) & KMC Unit in   CEMONC HCs

- Renovation & Expansion of NICU Level 2 in selected hospitals to strengthen capacity for specialized newborn care with upgraded infrastructure and equipment

- Scale up the existing electronic medical records system to all 210 facilities:

  - Equip and install target facilities with computers to digitize maternal and newborn health records

  - Train health workers on uptake of the EMR system and recording of patient level data

  - Conduct quarterly supportive supervision to ensure data quality

- Recruit one data analytics expert to support integration of the EMR into DHIS2 for data reporting and provide training and technical support to target facilities.

- Install the Referral APP V2 application in all 210 facilities to ensure efficient communication for referrals.

- Conduct advocacy and orientation activities with health facility managers, community leaders, and local administrators to effectively utilize ambulances for referrals.

At the national level, Beginnings Fund will provide support for the following activities:

- Finalize the development of the Referral APP V2 application to improve patient referral and communication between health centres and hospitals

- Establish and launch a digitized and networked global Hub and Spoke Skills Lab Network (HSSLN) hub for MNH and establish “model” facilities to exchange best practices, support enhanced capacity, incubate innovations, and accelerate scale-up of high-impact interventions.

- Digitize the Maternal and Newborn Programme at all levels of government through the shared EMR platform to monitor MNH programs, including referral network performance.

- Support the design and integration of digital learning systems for MNH health workforce, including blended training modules and digitized job aids.

- Strengthen the Maternal and Perinatal Death Surveillance and Response (MPDSR) system through digitalization and standardized tools and checklists.

Country Budget and Sources

Of the total budget of USD90million, the key cost drivers are:

- Procurement of MNH commodities at USD23million (25%), of which USD10million will be through the RMNCH Compact.

- Systems improvements at USD23.6million, of which USD8.6million is for the improvement of data and referral systems and USD15million for infrastructure development.

- Scale up of interventions at USD13.6million, mainly driven by training, mentorship, and quality improvement costs.

- Technical Assistance, Coordination, and MEL at USD10.5million (12%) which includes program coordination and travel, secondments of technical and coordination staff to various MOH Lead Executive Offices (LEOs) and program evaluation.

The Workforce budget, which currently includes recruitment, scholarships, and the setup of MNH skills labs, at USD6.7million (7%), will likely increase as the scope of the investment is finalised. A contingency of 12.7million remains, and additional activities with the highest impact will be identified upon completion of the baseline assessment. The Government of Ethiopia will commit up to USD506million in co-funding and complementary investments towards the Beginnings Fund and related MNH initiatives, of which the majority is the Government’s projected spend on MNH over the next five years. This will be further complemented by more than USD220million complementary funding from additional partners, including the Gates Foundation, CIFF, MBZ Foundation, Global Financing Facility, and the World Bank.

Monitoring, Evaluation and Learning (MEL)

Robust monitoring, evaluation, and learning (MEL) will be integral to the success of this investment. This investment will enhance existing government data platforms to improve data quality, track progress, and generate evidence for adaptive management, ensuring alignment with government priorities and long-term integration into Ethiopia’s digital health architecture. These platforms include DHIS2, which aggregates facility-level data on MNH indicators and has been rolled out to public institutions nationally; EMR, which enables point-of-care data entry and patient-level tracking at health facilities; the MPDSR system, which captures and reviews maternal and perinatal deaths to inform quality improvement; and the IMNID, which tracks individual maternal and newborn case data at the facility level. Quantitative data generated from these systems will be supplemented by qualitative insights from supportive supervision and mentorship reports, clinical audits, training evaluations, and stakeholder consultations. Together, a continuous improvement approach to data review will be taken, utilising regular reviews and analyses at all levels of government to identify trends, track coverage and quality of care, and assess the effectiveness and sustainability of the planned interventions.

Beginnings Fund investments in national data systems are complemented by Ethiopia’s broader digital health transformation agenda. The National Data Management Center for Health (NDMC), which has led comprehensive assessments of health facility distribution and readiness, provides a strategic data infrastructure for evidence-based planning. In addition, the Sand Technologies initiative, funded by the Susan Thompson Buffett Foundation (STBF), is investing in digital health intelligence, a Health Intelligence Operating System (HIOS), and a National Intelligence Centre that will enable real-time data visibility, advanced analytics, and enhanced MoH capacity in data and artificial intelligence. Together, these investments will enable the programme to quickly identify high-risk areas and service bottlenecks, support evidence-based resource allocation, and enhance frontline capacity with robust national analytics.

IPHCE will lead the coordination of all MEL activities for the Ethiopia Country Plan. Leveraging its institutional capacity, IPHCE will work closely with the Digital Health LEO in MOH, the Regional Health Bureaus (RHBs), and the broader partner consortium to systematically track programme progress, ensure data quality, and facilitate the translation of evidence into practical recommendations for government and donors. This will be achieved through continuous monitoring, regular data reviews, data quality audits, and learning and dissemination workshops. IPHCE will also second one MEL Coordinator to support these MEL activities within the MOH. IPHCE will also coordinate baseline, mid-term, and endline evaluations to assess programme performance at key intervals, working closely with the Beginnings Fund MEL team to deploy a standardised health facility assessment tool utilized across all Beginnings Fund countries. IPHCE will also support the MOH to compile a consolidated annual narrative and financial progress report, tracking against measures of success within the Pathway to Impact (see Annex A). Progress will be monitored and reviewed by the Steering Committee and Programme Management Team to inform decision making and course correction. For the infrastructure component of this investment, CHAI will conduct joint monitoring with the FMOH Infrastructure Division through monthly site visits, milestone-based progress tracking, and reporting against the construction timeline.

Risk and Reward

| Risks (Significance/Likelihood) | Mitigating Strategies |
| --- | --- |
| External Procurement delays (MNH commodities and infrastructure) due to global supply chain disruptions, shipping, and customs, etc. (High/Moderate) | Work with Gates Foundation and partners from other anchor donors, and leverage the CHAI market-shaping grant, to ensure availability of essential MNH commodities, understanding and planning for market challenges ahead of time. MOH and EPSS will also establish fast-track procurement mechanisms. |
| Programmatic MNH workforce attrition, particularly in remote areas, for the staff to be recruited and deployed with the BF investment (High/Moderate) | Beginnings Fund will support compensation for newly recruited health workers in the first 2-3 years. The Investment Team will engage closely with MOH and RHBs to develop an HR transition plan outlining sustained allocation of government resources to absorb, retain, and motivate these health workers, and support the MOH to accelerate implementation of the workforce compensation reforms currently under development following recent strikes. |
| Political Change in government leadership during general elections to be held 1 June 2026. (Moderate/Moderate) | The plan developed aligns with the HSTP and the country's MNH priorities. Beginnings Fund has and will work closely with the technical teams (which don’t typically change) to ensure continuity of the plan in the event of a change in leadership. The implementation start date will be phased for each investment, beginning with the RMNCH compact prior to elections and all other investments to begin post-elections. |
| Geopolitical risks stemming from regional instability/conflict-affected regions of mainly Amhara, Oromia, and Tigray, and population displacement in some regions (Afar and Somali) (High) | Adopt a flexible and adaptive implementation model that includes prioritizing more stable districts for initial rollout, while maintaining readiness to operate in fragile settings and leveraging the existing RHB capacity in these fragile and conflict settings to directly manage implementation of some of the proposed interventions. |

Transition and Sustainability Plan

The Government of Ethiopia is committed to long-term sustainability and ownership of the Beginnings Fund maternal and newborn health (MNH) investments and has outlined a phased Sustainability and Transition Plan for the programme between 2026–2031. This plan aims to gradually transition leadership, continued implementation, and financing responsibilities from Beginnings Fund to national and sub-national government entities, ensuring that the high-impact interventions are institutionalized. This phased transition reinforces the government's commitment to achieving sustainable improvements in maternal and newborn health outcomes and towards building resilient health systems.

Phase 1: Consolidation (Year 1) – This phase will focus on developing all relevant tools, standard operating procedures (SOPs), and training packages to meet the objectives of implementation. These resources will be embedded into national systems, including health education curricula, digital platforms, and service delivery protocols. This is a foundational phase that ensures all components of the programme are standardised, accessible, and aligned with national guidelines.

Phase 2: Transition (Years 2-4) – This phase will involve a gradual shift of implementation responsibilities to regional and district health teams. Training, mentorship, and supportive supervision will be intensified at sub-national levels to ensure readiness for handover. While external partners will continue to provide technical support, their operational footprint will be progressively reduced.

Phase 3: Sustainment (Year 5) – This phase marks the complete transition of leadership and financing to the Federal Ministry of Health (FMOH) and Regional Health Bureaus (RHBs). External partners will exit implementation roles, and the government will assume full responsibility for sustaining and expanding MNH acceleration efforts. This final phase ensures that the gains made under the Beginnings Fund are preserved and scaled through domestic systems and resources.

Annex A: Pathway to Impact:

By 2031:

•  Reduction in maternal mortality by 15% from 195 to 166 per 100,000 live births

•  Reduction in stillbirths by 15.7% from 19 to 16 per 1,000 live births

•  Reduction in neonatal mortality by 26% from 25 to 20 per 1,000 live births

| Obj. 1: Invest in the scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 210 facilities across 46 focus districts in eight regions (Afar, Amhara, Central Ethiopia, Oromia, Sidama, Somali, South Ethiopia, and Tigray), which account for approximately 33% of maternal deaths and 40% of neonatal mortality nationally: |  |
| • 100% of 210 target facilities provide package of ANC diagnostics (anaemia, infection, pre-eclampsia detection, POCUS) by end Year 1 • 100% of target facilities equipped with MNH products and newborn corners established in 155 health centres by end Year 1 • Digital maternal and foetal monitoring tools deployed to all target facilities by end Year 2 • PPH bundle (including detection drapes and heat-stable carbetocin) scaled up to all 210 facilities by end Year 2 • Level 1 ENC and Level 2 SSNC with KMC Plus scaled across all target facilities; Level 3 NICU across all target hospitals by end Year 3 • NEST teams established for immediate post-birth stabilisation and resuscitation in all target hospitals by end Year 2 • IMNCI for outpatient management of newborn illness including PSBI rolled out to all target facilities • Quarterly integrated supportive supervision from 55 hospitals to all 155 health centres under their catchment | • Early ANC coverage (within 12 weeks) increased from 7.7% to 50% by end Year 5 • % of pregnant women attending ANC tested for syphilis: from 80% to 100% by end Year 5 • % of women attending ANC receiving MMS: from 24.7% to 100% by end Year 5 • % of women who received uterotonics within the first minute after delivery: maintained at ≥97% • % of asphyxiated neonates resuscitated and survived: from 88% to 95% by end Year 5 • % of babies with suspected sepsis who receive parenteral antibiotics: from 30% to 100% by end Year 5 • % of preterm and low-birth-weight babies who receive KMC: from 80% to 100% by end Year 5 • NICU recovery rate: from 81.6% to 94% by end Year 5 |
| At the national level: |  |
| • National consolidated comprehensive PPH guidelines formally endorsed and rolled out • Intrapartum Care Guidelines and WHO Labour Care Guide adopted nationally | • CS rate in targeted districts increased from 1.7% to 10% by end Year 5 |

| Obj. 2: Increase the availability and use of quality priority MNH commodities |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 210 facilities across 46 focus districts: |  |
| • 100% of 210 target facilities equipped with lifesaving MNH medicines (oxytocin, misoprostol, heat-stable carbetocin, MgSO₄, tranexamic acid, antibiotics, antihypertensives, IPC supplies) by end Year 1 • All 55 hospitals equipped with standardised Level 2 NICU equipment including CPAP; all 17 CEmONC health centres equipped with Level 1 NICU equipment by end Year 1 • All 210 facilities equipped with POCUS by end Year 1 • MEMIS scaled up in all 210 facilities to record, monitor, and manage equipment functionality by end Year 2 • 126 biomedical engineers trained (at least two per hospital, one per region) by end Year 2 • Pharmacists in all target facilities trained on management and dispensing of MNH products by end Year 1 • Supportive supervision on MNH commodities SCM conducted across target facilities | • Availability of tracer essential MNH medicines in targeted facilities: 80% by Year 3, 100% by Year 4 • % of functional MNH medical devices in targeted facilities: [TBD after baseline] • Procurement lead time for MNH commodities reduced to ≤120 days by end Year 5 |
| At the national level: |  |
| • Clinical guidelines updated and regulatory approval received for key MNH commodities (POCUS, heat-stable carbetocin, detection drapes) | • % increase of essential MNH commodities available in EPSS national store |

| Obj. 3: Strengthen and expand the quality, number, and distribution of the MNH workforce |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 210 facilities across 46 focus districts: |  |
| • 110 specialists (55 OB/GYN and 55 paediatricians) recruited and deployed across 55 hospitals by end Year 1 • 120 health care workers enrolled in Master’s programmes for specialisation in neonatal nursing and midwifery, with return-to-facility agreements signed • Catchment-based training and mentorship from hospital physicians to health centres operational by end Year 2 • Quarterly integrated supportive supervision from hospitals to health centres | • % of targeted hospitals with requisite skill mix of MNH specialists (midwives, neonatal nurses, anaesthetists, paediatricians, neonatologists, biomedical technicians): [TBD after baseline] • % of targeted hospitals achieving targeted staff:patient ratio in maternity units: [TBD after baseline] • % of targeted hospitals achieving targeted staff:patient ratio in newborn units: [TBD after baseline] • CS rate in targeted districts increased from 1.7% to 10% by end Year 5 |
| At the national level: |  |
| • Pre-service training of midwives and specialised nurses strengthened by integrating MNH into curriculum with simulation-based training (MamaNatalie, NeoNatalie) • MNH simulation skills labs established at national and regional levels • Critical non-clinical training (Ethics, Human Rights, Respectful Maternity Care) integrated into midwifery and medical colleges • Digitised maternal and neonatal health curricula developed for blended in-service training and CPD • Joint supportive supervision with professional associations in universities and colleges across eight regions | • 120 MNH specialists complete post-basic/postgraduate training: 90% complete within 12 months of programme timeline; 90% deployed to high-burden maternity and newborn units; 90% retained at 12 months post-deployment |

| Obj. 4: Strengthen critical health system enablers, including MNH infrastructure, data, quality improvement, referral systems, and advocacy for greater impact |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| Infrastructure (in up to 25 facilities across eight regions): |  |
| • Infrastructure condition assessment completed for all targeted facilities by end Year 1 • Conceptual and technical designs approved by FMOH and Beginnings Fund by end Year 1 • Contractors procured and contracted for all targeted sites by end Year 2 • Renovation/expansion of OR blocks for up to 17 CEmONC health centres and 8 hospitals completed by end Year 4 • Renovation and expansion of Level 1 NICU and KMC units in CEmONC health centres completed by end Year 4 • Renovation and expansion of Level 2 NICU in selected hospitals completed by end Year 4 • Handover certificates and one-year defects liability period completed for all sites by end Year 5 | • MNH infrastructure, furniture, and equipment improved at up to 25 facilities (8 hospitals and up to 17 health centres) • 100% of districts in target areas with at least one CEmONC facility: [TBD after baseline] • 100% of health centres with OR blocks providing CEmONC services by end Year 4 • 100% of target hospitals providing CEmONC services: 80% by Year 3, 90% by Year 4, 100% by Year 5 • % of targeted districts with at least one Level 2 inpatient unit plus CPAP: [TBD after baseline] |
| MNH Data Systems and Quality Improvement (in 210 facilities): |  |
| • EMR system scaled up to all 210 facilities with computers installed, health workers trained, and quarterly supportive supervision by end Year 2 • One data scientist and one data analyst recruited to support EMR-DHIS2 integration • Quarterly supportive supervision to ensure data quality across all target facilities | • Digitised MNH data reporting integrated through EMR-DHIS2 platform across target facilities |
| Emergency Transport, Referral, and Innovation: |  |
| • Referral APP V2 application finalised and installed in all 210 facilities by end Year 2 • Advocacy and orientation activities with facility managers, community leaders, and local administrators on ambulance use for referrals • Hub and Spoke Skills Lab Network (HSSLN) established and launched for MNH | • Referral network performance monitored through shared EMR platform at all levels of government |
| At the national level: |  |
| • Digitised and networked MNH programme established through shared EMR platform at all levels of government • Digital learning systems for MNH workforce developed, including blended training modules and digitised job aids • MPDSR system strengthened through digitalisation and standardised tools and checklists | • MPDSR data used for continuous quality improvement and policy feedback at national and regional levels |

Notes:

• Baselines and targets marked [TBD] will be established following the baseline health facility assessment in Year 1.

The AROC is established by the Ministry of Health to ensure transparency, accountability, and effective governance within the ministry's financial operations. In accordance with the Federal Government of Ethiopia Financial Administration Proclamation No. 648/2009, Article 6, the Ministry is obligated to review audit reports and formulate responses to enhance internal control and financial management.

2024 –2025 EDHS

Ethiopia Mini Demographic Health Survey, 2019

Maternal mortality, newborn mortality, and still births

Does not include Beginnings Fund notional commitment of USD10million.

In addition to the 46 districts, additional woredas may be targeted via the RMNCH compact contribution.

Does not include contributions from Regional Health Bureaus still under finalization.

Details and scope of support from the Health Workforce Fund and ELMA Foundation is under development