# BEGINNINGS FUND RWANDA INVESTMENT PLAN

Rwanda Investment Plan Overview

| Grantees: | Investments Presented: Rwanda Ministry of Health (RMOH) Rwanda Biomedical Centre (RBC) Rwanda Medical Supply (RMS) CHAI Rwanda (CHAI) |
| --- | --- |
| Implementer(s) (if different to Grantee): | University of Rwanda |
| Geographic Focus: | 12 districts (Bugesera, Gasabo, Gicumbi, Muhanga, Musanze, Ngororero, Nyagatare, Nyamasheke, Nyanza, Nyarugenge, Rubavu, and Rwamagana districts) and national support |
| Amount: | USD35million |
| Co-Investment: | USD205million (USD195.2million in Government commitments and USD9.7million in direct co-investments/complementary investments from partners during the grant term). |
| Term: | 60 months (1 October 2025-30 September 2030) |
| Investment Description and Impact Goals: | Rwanda is committed to achieving significant reductions in maternal and neonatal mortality through a comprehensive and integrated approach to health system strengthening. Progress has been made through the launch of the health workforce reform (4x4 Reform) aimed at quadrupling the number of trained health workers within four years; establishing eight Level II Teaching Hospitals and successfully launching an obstetrics residency program to expand the nation’s training capacity and decentralized provision of tertiary care to improve equitable access to quality care; significant reduction in prices of commodities procured through strategic purchasing; committing to financing of maternal and newborn (MNH) commodities through national insurance schemes in the long run, and digitizing its electronic medical records system (roll out of e-Buzima). There is a significant opportunity to build on these investments and committed government leadership to enhance maternal and newborn care. Beginnings Fund will target the scale-up of priority interventions that address the leading causes of maternal and neonatal deaths, and stillbirths during antenatal care, labour and delivery, and newborn care. Alongside the Government of Rwanda, this investment will increase availability of quality MNH commodities, increase the number, competency, and skills-mix of the MNH workforce and move to expand training capacity at L2THs, improve the quality and use of MNH data and supporting maternal and neonatal unit infrastructure development. Through these investments, the Beginnings Fund will help catalyze Rwanda’s goal to accelerate progress towards ending preventable maternal and newborn deaths and save ~14,585 lives by 2030: - reducing maternal mortality by 10.5% from 229 to 205 per 100,000 live births - reducing stillbirths by 11% from 17 to 15 per 1,000 live births - reducing neonatal mortality by 39% from 18 to 11 per 1,000 live births |
| Pathway to Impact: | See Annex A |
| Governance and Management: | The Ministry of Health (MOH) will oversee governance and management of the Rwanda Investment Plan. The governance mechanism is designed to align closely with existing national systems and structures, ensuring coherence, efficiency, and country ownership. A Steering Committee, co-chaired by the Minister of Health, Dr. Sabin Nsanzimana; and the Beginnings Fund CEO, Alice Kang’ethe, comprising of representatives of Rwanda Biomedical Centre (RBC), Rwanda Medical Services (RMS), and CHAI will provide strategic oversight throughout the implementation of the plan. The steering committee will meet bi-annually. A Management Team, consisting of the technical leads from the implementing agencies (RBC, RMS, the MOH Department of Health Workforce Development and Department of Digitization), CHAI, and the Beginnings Fund investment team (Patricia Wamala (Program), David Gathara (MEL) and Fred Lwegaba (Finance)), will manage implementation, monitor progress, and support course correction on an ongoing basis. Audits: This program will utilize annual audits conducted by Rwanda’s Office of the Auditor General. |
| Reporting | A consolidated annual narrative and financial report will be prepared by RBC with support from CHAI, and submitted by August 30 each year, two months after the MOH fiscal year end, to align with national reporting timelines. |

Acronyms and Definitions

ANC 			Ante Natal Care

BEmONC		Basic Emergency Obstetric and Newborn Care

CEmONC 		Comprehensive Emergency Obstetric and Newborn Care.

CBHI 			Community-Based Health Insurance

CHAI 			Clinton Health Access Initiative

CPAP 			Continuous Positive Airway Pressure

CTG 			Cardiotocography

DHIS2 			District Health Information Systems 2

DHS 			Demographic Health Survey

DQAs 			Data Quality Assessments

ELMIS			electronic Logistics Management Information System

EMR 			Electronic Medical Records

HC			Health Centre

HSC 			Heat Stable Carbetocin

HMIS			Health Management Information System

HSSP 			Health Sector Strategic Plan

IKMC			Immediate Kangaroo Mother Care

IPC 			Infection Prevention and Control

LAN			Local Area Network

L2TH 			Level 2 Teaching Hospital

MCCH 			Maternal, Child and Community Health

MMS 			Multiple Micronutrient Supplements

MNH			Maternal, Newborn Health

MOH			Ministry of Health

NICU 			Neonatal Intensive Care Unit

NHIC 			National Health Intelligence Centre

ODA			Official  Development Assistance

POCUS			Point of Care Ultrasound

PPH			Post Partum Hemorrhage

RBC			Rwanda Biomedical Centre

RDB			Rwanda Development Board

RMNCAH		Reproductive, Maternal, Newborn, Child and Adolescent Health

RMS			Rwanda Medical Supply

RSSB			Rwanda Social Security Board

SGHP			Second Generation Health Post

SSNC			Small and Sick Newborn Care

TXA 			Tranexamic Acid

UBT 			Uterine Balloon Tamponade

UR			University of Rwanda

WHO 			World Health Organization

Situational Analysis

Rwanda made significant improvements in maternal and neonatal health outcomes in the past two decades, reflecting a rise in facility births to 94% and improvements in antenatal care (ANC) coverage now at 47%.   In 2015, Rwanda became one of the few countries that met the Millennium Development Goals for maternal mortality and has since reduced maternal mortality by 22% from 292 deaths in 2015 to 229 deaths per 100,000 live births in 2023. Neonatal mortality decreased from 19.7 in 2015 to 17 deaths per 1,000 live births in 2022, and stillbirth rates are estimated at 17 per 1,000 births for the period 2017 to 2020. Despite this progress and high access to facility-based services, the mortality rates have remained high and stagnant in the last decade, pointing to gaps in the quality of care due to a shortage of qualified health workers, inadequate infrastructure and essential equipment, and insufficient access to key pharmaceuticals and medical supplies.

In Rwanda, the leading causes of maternal mortality are obstetric hemorrhage (45.5%), hypertensive disorders (14%), and infections (13%). With approximately 83% of maternal deaths occurring in hospitals, most maternal deaths (54%) are linked to delays in accessing care or not receiving quality care. Although ANC coverage has improved, it is still low, with only 52% of women accessing care during the first trimester and 47% completing at least four visits in 2024. These challenges are further complicated by high rates of teenage pregnancy (5%) and lack of access to family planning (14% in married women and 37% in unmarried women). The leading causes of neonatal mortality are birth asphyxia (28%), prematurity (25%), and sepsis (9%).  Like maternal deaths, most neonatal deaths occur in district hospitals (65%) and referral hospitals (14%), highlighting gaps in the quality of small and sick newborn care (SSNC) at both secondary and tertiary levels of care.  Most maternal and newborn deaths also occur within the first 48 hours after delivery, emphasizing the need for high-quality intrapartum and SSNC within hospitals.

The Government of Rwanda (GOR) recognizes this need and is committed to achieving significant reductions in maternal and neonatal mortality and stillbirths through a comprehensive and integrated approach to health system strengthening, establishing several large-scale health initiatives to realize this vision.

Rwanda’s biggest health workforce challenge is a shortage in the number of health workers. There are currently only 1.2 health workers per 1,000 people, well below the WHO recommended ratio of 4.45 per 1,000. As of May 2025, the average staffing rate is 68.5% for all public hospitals and health centers (excluding Rwanda Military Hospital and King Faisal Hospital), with attrition rates of up to 45% in rural regions due to poor working conditions, low salaries and limited career growth opportunities. There is a significant shortage of specialized health workers to provide EmONC and specialized newborn care, including obstetricians, pediatricians, anesthesiologists, nurses, midwives, and non-physician anesthetists. In addition, there is insufficient training and mentorship to equip existing staff, including general practitioners, to provide emergency obstetric care and caesarean sections. This staffing deficit and high attrition, along with the resulting heavy workloads, results in poor quality of care, underscoring the urgent need for a significant increase in specialized health workers.

To address this, Rwanda embarked on an ambitious plan to increase the number and quality of its health workforce through the launch of the 4 x 4 Reform in July 2023. This initiative, approved by the Cabinet of the Government of Rwanda, aims at quadrupling the current health workforce within four years, to meet WHO’s health worker to population ratio while enabling quality service provision through improved pre-service and in-service medical training. The initiative prioritizes health cadres across several disciplines, including pediatricians, midwives, nurses, obstetrics and gynecology residents and fellows to serve MNH, which currently has low enrollment compared to demand. Between 2020 and 2022, the average annual enrollment of undergraduate nursing and midwifery programs was 648 and 72, respectively. The GOR aims to increase this number to 5,500 undergraduate nurses and 2,100 undergraduate midwives annually, leading to a respective eight-fold and 29-fold increase in enrollment. Over the past two years, the government has invested USD103million in scholarships and USD28 million in residency programs under the reform, and partners, including ELMA, Expertise France, UNFPA, and STBF, have contributed an additional ~USD38million to its progress. This initial work has resulted in a 3.7-fold increase in health training enrollment.

To support the high demands of in-service training required under the 4x4 Reform, the Ministry of Health (MOH) established eight Level II Teaching Hospitals (L2THs) in early 2024 to simultaneously expand nationwide training capacity and decentralize tertiary-level care to enhance equitable access to specialized care. Although Rwanda has a well-established referral pathway between primary health care facilities to tertiary hospitals, having only four tertiary referral hospitals (three of which are in Kigali) leads to significant delays in accessing CeMONC, particularly for peripheral and rural health facilities. This decentralization of tertiary-level care has allowed the University of Rwanda to expand its Obstetrics and Gynaecology residency program from the tertiary referral hospitals to L2THs, increasing the residency intake from 25 to 60 residents annually. The African Health Sciences University (AHSU), a newly accredited health sciences institution launched in September 2024, is currently conducting six residency programs (Anaesthesiology, Internal Medicine, Paediatrics, Emergency & Critical Care, General Surgery, and OBGYN) at two L2THs (Kibuye and Kibungo Hospitals). However, gaps still remain in the training of specialist pediatric workforce, including pediatricians and neonatal nurses, across the L2THs.

Only 28% of health facilities meet the minimum EmONC standards. In addition to the health workforce and training gaps, insufficient access to essential MNH commodities contributes to this challenge. While GOR currently procures urine dips sticks (with 10 tests), hemoglobinometers, oxytocin, misoprostol, tranexamic acid, azithromycin caffeine citrate, glucometers, BiliDx strips, and suction pumps, gaps in other commodities, including heat-stable carbetocin, cold chain equipment for oxytocin storage, surfactants, calibrated drapes, uterine balloon tamponades, CPAP machines, incubators, radiant warmers, phototherapy and CTG machines, persist across health facilities. Where equipment is available, improper utilization and maintenance results in frequent breakdowns. While GOR has integrated routine diagnostics screening for anemia, hypertension, and urinalysis, covered under the Community-Based Health Insurance (CBHI) scheme, key maternal nutrition supplements, including MMS, calcium, and IV iron, remain partially introduced, undermining the achievement of a comprehensive ANC package.

Recognizing the importance of access to quality infrastructure, equipment, and pharmaceuticals to achieve its MNH goals, GOR has invested significant amounts of domestic funding in MNH infrastructure and commodities, including ~USD7.5million in infrastructure development for the renovation of maternity and neonatology units at two L2THs (Kabgayi and Nyamata), and up to USD 1.2million on procurement of MNH pharmaceuticals and supplies not reimbursed under the current Community-Based Health Insurance (CBHI) scheme, in the last four years. In addition, GOR has channeled ~USD10million in donor funding towards MNH equipment, including procurement of ultrasounds, incubators, cardiotocographs, CPAP machines, and delivery beds; and received support from UNICEF to introduce and scale up Multiple Micronutrient Supplementation (MMS). Through strategic purchasing initiatives, GOR has been able to improve access to high-quality health products, at more competitive prices.

Gaps in MNH data systems, including poor accessibility and interoperability, limit the use of key data to inform decision making, such as early detection and management of high-risk pregnancies, monitoring quality improvement, and reporting. GOR is planning to fully digitize its national medical records system through the launch of an electronic medical records (EMR) system called e-Buzima, to centrally store patient data across 533 public health facilities, enabling medical personnel and patients to access health records in real time. To date, GOR has invested close to USD17million in infrastructure upgrades and equipment to support this expansion. LAN connectivity has been established in 20 health centers and computers have been procured and deployed in 333 health centers. Despite this substantial investment, further investment is needed in the procurement of digital equipment and training of frontline users (health workers, data managers, and information officers) to close the gaps in MNH data systems.

Rwanda funds its healthcare system through government allocations, donor support, and innovative insurance schemes. In 2014/15, government funds (primarily taxes) contributed 29% of total health financing, with external funds (53%) and out-of-pocket payments & insurance (19%) covering the rest (HFSP 2018/24). A key success is universal health insurance through CBHI and RSSB, covering more than 90% of the population, particularly vulnerable groups. Within this, CBHI covers 85.3%, and its coverage scheme includes ANC, deliveries (including c-sections), neonatal care, and postnatal services at public and contracted private facilities. However, financial sustainability remains a concern. Additionally, although Rwanda has improved fund pooling, fragmentation remains an issue—the funds allocated to each pool do not always match the population served. Despite efforts to distribute financial risk, inequalities persist, with lower spending per CBHI member compared to RSSB formal sector members, leading to differences in benefits (HFSP 2018/24; HFSP 2025/29).

The health budget for the year 2024/2025 was RWF 427.6 billion (~USD 295million) representing 15.8% of total government and partner expenditures (MoH, 2023). Donor funding accounts for approximately 40% of the health budget. Despite this contribution, MNH services remain underfunded relative to need. This high level of reliance on external funding poses sustainability risks, especially with the current funding constraints. While the CBHI program alleviates some financial barriers, gaps in funding for lifesaving commodities and equipment persist.

Rwanda has developed a comprehensive policy framework aimed at improving MNH, most notably through the Fifth Health Sector Strategic Plan 2024-2029 (HSSP V) and the National Strategy for Transformation, both of which emphasize the improvement of the quality of primary health care, workforce development, and strategies to accelerate the reduction of maternal, neonatal and child deaths through adoption of MNH bundles and optimization of existing interventions and guidelines. The HSSP V budget projection over five years for Maternal and Newborn health is ~USD 91 million (10.8%) of which GoR contribution is estimated at 47% (~USD 43 million). Despite this, several key gaps still exist, including a shortfall in addressing key health workforce challenges, such as retaining skilled professionals and improving career development opportunities, especially in rural areas.

Beginnings Fund Strategic Approach

Significant investments made by the Government of Rwanda on improving maternal and newborn health present a unique opportunity for the Beginnings Fund to partner alongside GOR to accelerate reductions in maternal and neonatal mortality and prevent stillbirths to reach Rwanda’s 2030 goals and save ~14,585 lives.

Beginnings Fund investments will support the scale up of priority interventions targeted at the drivers of maternal and neonatal morbidity and mortality and stillbirths, improve the availability and use of quality MNH commodities, increase the number, competency and skills-mix of the MNH workforce, and improve MNH systems, including infrastructure development, scale up of digital health systems, optimising MNH quality of care data in the national health information systems, and use of data for quality improvement. Investments will further Rwanda’s Fifth Health Sector Strategic Plan 2024-2029 (HSSP V) and "4x4 Reform” strategy through direct support to government via the Ministry of Health (MOH), Rwanda Biomedical Centre (RBC), and Rwanda Medical Supply (RMS). An MOH Technical Team, led by Dr Francois Regis Cyane (Acting Head, Maternal, Child, and Community Health Division in RBC), working with lead clinicians, midwives, district managers, professional associations and the investment team, analysed MNH data to identify key areas for strategic investment, outlined below.

The Beginnings Fund investment will target 12 districts: Bugesera, Gasabo, Gicumbi, Muhanga, Musanze, Ngororero, Nyagatare, Nyamasheke, Nyanza, Nyarugenge, Rubavu, and Rwamagana. These districts host 12 strategically important hospitals that account for 43% of the national maternal and neonatal mortality burden and 40% of annual deliveries. As part of GOR’s strategy to decentralize provision of high-quality care and decrease referral times, eight of these district hospitals have been upgraded to Level 2 Teaching Hospitals (L2THs) to provide specialist MNH services, including being staffed with obstetric gynaecologists and equipped with improved diagnostics capacity.  One of these L2TH (Kibogora) addresses a critical gap in the southwest region, where long distances to the nearest tertiary referral facility (Butare) leads to delays in emergency care, and the four remaining district hospitals (DHs) are all high-burden hospitals. Downstream, the networks of care tied to these 12 hospitals include 162 BeMONC health centers (HCs), three medicalised (CeMONC) HCs, and 14 second generation posts (SGHPs) (See Annex B). Upstream, these facilities will be supported by four tertiary hospitals through linked referral systems for specialist services not offered at the district level. While initiatives to improve service delivery in the tertiary hospitals are already funded by GOR, Beginnings fund will support the set-up of a virtual hospital network between the four DHs and two tertiary facilities given they will not form part of the L2TH network.

There is a significant opportunity to shift MNH outcomes across these high-burden districts by improving the quality of antenatal care, primarily delivered in HCs, and increasing access to quality EmONC and small and sick newborn care (SSNC) at district level, with the goal to improve accountability for preventing maternal and newborn morbidity and mortality districtwide. In addition, there are opportunities to align funding for greater impact in two districts (Bugesera and Rubavu) with GFF investments supporting three HCs to provide CEMONC. Priority interventions outlined below will be implemented in these districts using a hub-and-spoke model to establish or improve existing CEmONC and introduce Level II newborn care in the L2THs and DHs (hubs). The interventions will also support HCs and SGHPs (spokes) providing BEmONC to improve antenatal care to diagnose and treat preventable conditions affecting morbidity and mortality at the time of birth and more confidently manage deliveries.

Point-of-care diagnostics to support early identification of anemia, hypertension, and infection already form part of the routine antenatal care (ANC) package delivered in health facilities, covered by CBHI. Roll out of point-of-care ultrasound (POCUS) has begun in 390 facilities (100 of these are in the Beginnings Fund targets districts), through support from Gates Foundation and introduction of micronutrient supplementation (MMS) is underway through a UNICEF investment. Beginnings Fund support will enhance the existing ANC package through procurement and scale up of POCUS and calcium supplementation in all target facilities, leading to efforts to achieve national coverage by 2030. Every pregnancy in targeted facilities will be scanned to date gestational age and help identify and refer high-risk pregnancies and mentorship on delivering the full ANC bundle will be provided to nurses and midwives in HCs and SGHPs.

To improve intrapartum care and reduce prolonged labor, which drives maternal morbidity, stillbirths, and birth asphyxia, digital intrapartum monitoring will be introduced in all target facilities to adequately detect maternal and fetal distress and ensure timely access to caesarian sections. National roll out of the PPH bundle for early detection and management (calibrated drapes, uterine balloon tamponade, fridges to store oxytocin, and heat-stable carbetocin), will be strengthened through catalytic procurement, training and mentorship.  Onsite training, mentorship, and quality improvement will be provided through a cascaded training model where doctors, nurses, and midwives in hospitals will be trained as trainers and support nurses and midwives in HCs and SGHPs in its referral network. Improved uptake of antenatal corticosteroids during pre-term labor will be improved by integrating gestational age data from POCUS to quality improvement data analytics for high-risk screening to reduce respiratory distress in premature babies.

To improve the quality of newborn care, newborn corners will be established in all BEmONC facilities to improve essential newborn resuscitation, warmth, and stabilization and neonatal units in all target hospitals will be equipped with the full SSNC bundle (Level 2 newborn care, CPAP, and iKMC) to ensure comprehensive newborn care coverage. Additional workforce and commodity support will be provided in L2THs to support the expansion of nursing and pediatric residency programs and enhance its teaching and referral capacity.  Level 3 newborn care equipment, including portable x-rays, mechanical ventilator machines, surfactant, and laryngoscopes for its delivery, and additional laboratory equipment for increased diagnostics capacity, will be procured. Pediatric sub-specialists will be recruited to both deliver more specialized care and train pediatricians and neonatal nurses. Oxygen delivery systems at HCs will be enhanced through procurement of oxygen concentrators for facilities and cylinders for ambulances.

At the national level Beginnings Fund will complement efforts by WHO, UNICEF, UNFPA, CHAI, and relevant professional associations working in close collaboration with MOH/RBC   to review and update national MNH guidelines and clinical protocols to incorporate novel interventions and products such as EMOTIVE, caffeine citrate, and heat-stable carbetocin for PPH prevention, and  build capacity to establish a pool of district-based mentors to support ongoing monitoring and quality improvement in the implementation of the MNH bundles and IPC practices. Beginnings Fund will also support integration of optimized EmONC, including safe cesarean section techniques, care of, and use of technologies for small and sick newborns, into the national medical education curriculum, ensuring ongoing capacity building for intern doctors and early-career general practitioners.

Beginnings Fund will make investments in infrastructure development through RBC to support upgrades of two hospitals as per MoH policies and standards. This will include renovation of the maternity and neonatology units of Kabaya district hospital whose maternal newborn infrastructure is old and limited for its workload (4,217 deliveries  1,418 neonatal admission annually), renovation of the neonatology unit of Gisenyi district hospital (which has the second highest newborn workload (3,206 neonatal admissions annually) and mortality among  district hospitals nationally, and equipping the renovated MNH units of both hospitals with medical and the requisite non-medical equipment  e.g. theatre lights and oxygen piping. Renovation and upgrading MNH units will ensure integration of iKMC in the design and equipping of these units. Complementary investment for Level 2 teaching hospitals with specialized MNH equipment and commodities including some limited support for laboratory equipment is critical for improving diagnostics requisite for maternal and newborn care service in four priority teaching hospitals while ensuring specialist skills are optimized for both teaching and service delivery with timely and quality care along the maternal-newborn continuum. For instance, while availability of blood is not a challenge in Rwanda, capacity of grouping and crossmatch to enable transfusion is limited. Similarly, sepsis is a key driver for both maternal and newborn mortality; however, hospitals do not have a capacity for culture and sensitivity. Further, this approach strengthens the existing referral care system, which was overloading the four main tertiary hospitals.

Program Consortium:

- The Government of Rwanda via Ministry of Health Department of Health Workforce for MNH workforce and Department of Digital Health for the data improvement investments.

- Rwanda Biomedical Centre for the scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality and infrastructure improvements in Kabaya (maternal and neonatal unit) and Gisenyi (neonatal unit).

- Rwanda Medical Supply for the procurement of essential MNH commodities and equipment and strengthening the supply chain of the same commodities.

- CHAI Rwanda to manage the recruitment of additional human resources who will support health workforce initiatives and scale up of high impact interventions, and the scholarships for the undergraduate program.

Operational Plan

Based on engagement with the MOH Technical Team, key networks of care at district and sub-district level are targeted based on referral patterns and population density, for implementation of priority interventions. This includes a total 191 targeted facilities across the 12 districts, consisting of 15 CEmONC sites (eight level II teaching hospitals (L2TH), four district hospitals (DH), and three medicalized health centres (HC)) and 162 HCs and 14 SGHPs providing BEmONC. All sites will be equipped for priority interventions, and two hospitals will be supported with infrastructure development to expand access to EMONC and SSNC. The implementation capacity will be strengthened through technical support provided by CHAI who will directly assist the Technical Team at the Ministry of Health (MOH) in coordinating and executing the investments outlined in this plan at both the national and district levels.

The following objectives and activities will be supported directly through Beginnings Fund investments in the Government of Rwanda and key implementing agencies (see investment memos for detailed plans). Outlined below against each objective, are a) government policy alignment, b) the amount of Beginnings Fund investment, c) government co-investment and commitments, and e) complementary investments that will advance planned support.

Objective 1: Invest in the scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality

Policy Alignment: HSSP V

Beginnings Fund Investment: USD1,038,817

Government Commitment and Support: - USD6,166,667 minimum annual support for national scale up of MNCH interventions, or USD30.8million over the grant term - In-kind support from four staff in the Maternal, Child, and Community Health division to support program implementation, estimated at USD73,500 over the grant term, and operational and indirect costs (not quantified) - Update key policy and guidance documents with MNH interventions and ensure alignment of external financing from partners

Key Implementing Partner(s): RBC, CHAI

Co-/Complementary Investments: TBD

  - Beginnings Fund will provide support for 191 target facilities in focus districts to:

  - Scale up point-of-care ultrasound (POCUS) to improve gestational age-dating and risk-differentiated referrals through equipping, training, and mentorship

  - Roll out the PPH bundle to prevent and manage post-partum hemorrhage through training and onsite mentorship.

  - Roll out digital intrapartum monitoring to manage labor and increase timely access to c-sections through equipping, training, and onsite mentorship

  - Support improvements in safe anesthesia and c-sections through equipping operating theatres and onsite mentorship

  - Support the uptake of antenatal corticosteroids for premature labor through mentorship and quality improvement, in conjunction with roll out of POCUS

  - Establish Level 2 newborn care (or improve coverage where it already exists) in 12 target hospitals through equipping, training and mentorship, quality improvement cycles, and improved data use.

  - Through a training of trainers model, provide orientation on the delivery of ANC, intrapartum, and SSNC bundles to hospitals which will cascade training and provide supportive supervision to HCs and SGHPs in its catchment area.

  - Provide practical skills training on optimized EmONC (including delivery of the PPH bundle, safe cesarean section techniques, and care and use of technologies for small and sick newborns) and establish peer-to-peer hospital-based mentorship of new nurses, midwives and general practitioners by experienced staff.

  - Deploy district-based mentors to monitor progress on implementation of interventions to improve healthy pregnancy, intrapartum care, and SSNC.

At national level, Beginnings Fund will provide support for the following activities:

- Working closely with CHAI through the Beginnings Fund market shaping grant, support scale up of PPH bundle at the national level through catalytic procurement of products, training of trainers, development of service delivery guidelines, and ongoing quality improvement.

- Complement efforts by WHO, UNICEF, UNFPA, CHAI, and relevant professional associations to develop an optimized EmONC curriculum that integrates safe cesarean section techniques, PPH bundle, and use and care of technologies for SSNC, to be incorporated into national pre-service and in-service curriculums.

Objective 2: Increase the availability and use of quality priority MNH commodities

Policy Alignment: HSSP V, RMS Strategic Priorities 2024-26, Rwanda Sustainable Public Procurement Policy

Beginnings Fund Investment: USD11,068,172

Government Commitment and Support: - USD2,099,293 minimum annual spend or USD10.5million over the grant term for routine MNH medicines. - In-kind support from two staff to support procurement activities, estimated at USD29,000 over the grant term, and operational and indirect costs (not quantified) - USD50,000 for procurement of heat-stable carbetocin - RMS will integrate the procurement and distribution of BF into existing processes to reduce costs while ensuring that the majority of funds are directed towards purchasing commodities and equipment. RMS will share purchase orders and delivery confirmations with BF to verify that the funds were used to acquire BF-supported maternal and neonatal (MN) commodities and equipment. Additionally, RMS will provide three technical staff members to assist with the procurement of commodities and equipment. Each staff member will spend up to 25% of their time on BF-supported activities, and RMS will cover the costs for these positions, totaling approximately USD 30,000 over three years. Furthermore, RMS will collaborate with partners such as RBC and CHAI to scale up new maternal and neonatal health (MNH) products, update the essential commodity and equipment list, assist with quantification, and support the transition to Community-Based Health Insurance (CBHI) financing for currently excluded commodities by 2029.

Co-/Complementary Investments: USD1.5million (POCUS and CPAPs from Gates Foundation); USD864,000 (in-kind support of heat stable carbetocin from UNFPA) USDxx (in-kind equipment and commodities from MBZ); and USDxx (in-kind MMS support from CIFF)

Beginnings Fund will support the following activities in high-burden facilities in the 12 focus districts:

- Equip all 191 facilities with POCUS and digital intrapartum monitoring and infant warmers in labor wards

- Equip 12 hospitals with EmONC and SSNC equipment, pharmaceuticals and supplies

- Equip 8 L2THs with lab equipment for blood grouping, cultures and sensitivity, and sterilization of equipment as part of infection prevention and control for sepsis

- Equip all 165 HCs with oxygen concentrators and oxygen cylinders to be placed in ambulances

See Annex C for full list of commodities to be procured through Beginnings Fund investment

At national level, Beginnings Fund will provide support for the following activities:

- Develop annual procurement plans and conduct catalytic procurement and distribution of priority MNH commodities, including the PPH bundle, (see Annex C) for the prioritized MNH commodities to prevent stockouts and strengthen service delivery

- Strengthen quantification and forecasting systems by improving data accuracy

- Support the introduction of novel or underutilized MNH commodities and devices, so commodities like POCUS hardware and software including AI use cases, are institutionalized

- Work closely with MOH and Field Technologies to improve digital tracking systems to monitor MNH product shipment, distribution, and inventory management.

- Strengthen existing digital platforms to track maintenance and repairs for MNH equipment (real-time monitoring, quick response, and sustainable functionality of costly MNH technologies).

Objective 3: Strengthen and expand the quality, number, and distribution of the MNH workforce

Policy Alignment: Update: HSSP V and 4x4 Reform

Beginnings Fund Investment: USD9,749,707

Government Commitment and Support: - In-kind support from three MOH technical staff to support program implementation, estimated at USD66,000 over the grant term, and operational and indirect costs (not quantified) - Appropriately deploy MNH undergraduates to maternity and neonatal units in 12 target districts, with a focus on achieving a targeted 1:12 nursing ratio in district hospitals - Finance external faculty for residency programmes from Year 4 of Beginnings Fund programme and transition to local staff by Year 5 - USD210,084 in scholarship support for pediatric residency programme - USD69 million in scholarships for MNH cadres part of the health workforce 4x4 reforms - 104 health workers (64 nurses and 40 doctors) completing post-basic/post-graduate training as MNH cadres - 90% optimally deployed to high-burden maternity and newborn units - 90% retained in the public sector at 12 months - Bonded to work within the GoR public service for at least 5 years

Key Implementing Partners: MOH Department of Health Workforce and University of Rwanda

Co-/Complementary Investments: TBD

Beginnings Fund will provide support for the following activities in focus districts:

- Improve specialized staffing capacity and support the expansion of pediatric and nursing residency programs in L2THs through recruitment of pediatricians and neonatologists to provide on-site service delivery and training.

  - Produce 40 pediatricians, 44 neonatal nurse residents and 20 peri-operative nurse residents through the residency programs.

  - Provide scholarship support for the 64 specialized nurses to complete residency program. Scholarship support for the 40 pediatricians will be supported by GOR.

At national level, Beginnings Fund will provide support for the following activities:

- Provide scholarship support to train 580 MNH workers (300 midwives, 150 nurses, and 130 non-physician anesthetists). Selection is based on aim to increase the pool of priority cadres for MNH service delivery and postgraduate programs more generally. While there is no guarantee, graduates will predominantly be deployed to high-burden facilities which overlap with Beginnings Fund target facilities. (see Annex D)

Objective 4: Strengthen other critical health system enablers, including MNH infrastructure, data and quality improvement, and advocacy for greater impact.

Policy Alignment: Beginnings Fund Investment: USD9,310,302

Government Commitment: - USD5.5million to support ongoing renovation in Kibagabaga L2TH, and beginning renovation in Muhororo district hospital - Support full renovation of Ruhengeri Level 2 Teaching hospital (all services) worth USD78 million - USD1million for set up of LAN to facilitate e-Buzima roll-out in 12 target hospitals - Underwrite the maintenance, internet and ICT staff cost required to support e-Buzima functionality within target hospitals

Key Implementing Partners: MOH Department of Digital Health, RBC, and CHAI

Co-/Complementary Investments: USD3.35million from GFF to support renovation of three medicalized (CeMONC) health centers from 2025-2027; USD4million to support renovation of Nyamata hospital from Imbuto Foundation

Improve MNH infrastructure at targeted facilities: To enhance MNH service delivery, the Beginnings Fund investment will support infrastructure improvements at Kabaya District Hospital for Maternity and Neonatology Units as well as for Gisenyi DH for Neonatology Unit. The renovation aims to address critical gaps in service availability, improve patient outcomes, and optimize the delivery of emergency obstetric and neonatal care.

- Maternity Ward Renovation (Kabaya DH): The current ward is undersized and lacks standardized infrastructure and equipment, limiting service delivery. Renovation will expand capacity, improve patient flow, and enhance emergency obstetric care for high-risk pregnancies.

- Operating Theater Upgrade (Kabaya DH): The small, non-standardized theater hinders timely emergency C-sections and surgeries. Upgrades will expand space and enhance infection control, ensuring efficient maternal and neonatal emergency care.

- Neonatal Unit Expansion (Kabaya and Gisenyi DH): The wards for both DHs are too small to accommodate newborns needing specialized care. Expansion will include thermal support, CPAP machines, incubators, and phototherapy units, improving preterm and critical newborn survival.

- Equipping the renovated MNH units of Kabaya Hospital and Gisenyi hospitals with medical and requisite non-medical equipment e.g. theatre lights and oxygen piping.

Improve data availability and use for the development of evidence-based MNH policy frameworks: To support strengthening data systems, facilitating data reviews, and enhancing innovation for routine monitoring of patients:

- Support the integration of maternal and neonatal inpatient data into e-Buzima

- Procure and distribute computers to support the roll out and deployment of the e-Buzima in 45 health facilities (12 hospitals and 33 health centres) focusing on the maternal and newborn modules and service areas.

- Enhance data analytics capacity for MNH data at NHIC through recruitment of two data scientists and two statisticians and procure and set up workstations and equipment needed for these additional personnel

- In collaboration with Field Technologies (Gates Foundation funds) and RMS support the deployment of a digital Supply Chain Intelligence platform that integrates EMR and ERP systems for real-time visibility and improved delivery of PPH and broader MNCH products and promoting better forecasting and quantification.

- Procurement and integration of centralized patient monitoring dashing pulling data across medical devices (Internet of Things (IOT) in 11 priority health facilities for real-time cases monitoring in maternity and neonatal wards through procurement, installation & implementation of IMPALA patient monitors with IoT for neonatal wards in 11 priority health facilities.

- Support national, subnational and facility-level teams to track and improve the quality of maternity and SSNC care following implementation using routine QI, dashboards, and mentorship.

- Monthly data review on MNH Indicators and support hospitals staff to analyze gaps, design Quality Improvement projects and implementation for better obstetric and sick and small newborns care outcomes

- Integrate MNH QI across labor and delivery wards and neonatal units.  Identify knowledge and skill gaps and guide low-dose-high-frequency simulation trainings.

- In partnership with NHIC, support facility champions lead regular QI sessions to identify challenges to quality and coverage and test improvement ideas. Use data to guide mentorship

- Support the MOH Quality Management Directorate to ensure Intrapartum/SSNC QI practice is embedded into MOH systems. Strengthen QIST and WIT teams to drive individual facility QI activities.

Country Budget and Sources

Of the total budget of USD35million, the key cost drivers are procurement of MNH commodities at USD11million (32%), increasing the quality and number of the MNH Workforce at USD9,749,707 (28%), and improvement of Infrastructure and Data Systems at USD9,310,302 (27%). Government of Rwanda (GOR) will commit USD195million in co-funding towards Beginnings Fund Interventions which will be further complemented by USD9.7million in funding from partners, including Gates Foundation, CIFF, MBZ Foundation, Global Financing Facility, and Imbuto Foundation. RMOH, RBC, RMS, and CHAI will provide an estimated USD806,653 in co-investments (USD168,500 of which is in-kind support from RMOH, RBC, and RMS for personnel and operational costs).

Monitoring, Evaluation and Learning (MEL)

The existing government-owned platforms and health data systems such as e-Buzima Electronic Medical Record (EMR), the National Health Intelligence Centre (NHIC), and HMIS will play a crucial role in supporting learning and research within the program by providing evidence-based insights into health outcomes, service delivery, and program effectiveness. Through regular review and analysis of MNH data will allow program teams, MEL team and program managers to identify trends, such as improvements in quality of care or declines in maternal and newborn health outcomes. By analyzing these trends, program teams will assess the relevance, effectiveness, and sustainability of interventions and adapt strategies to address emerging challenges. It will also enable tracking of critical process indicators, pinpoint systemic gaps, empower decision-makers to develop and implement policies and interventions that are based on actual program performance and outcomes, ensuring that changes are grounded in evidence.

Through targeted technical and operational support, Beginnings Fund will help enhance the real-time collection, integration, and analysis of MNH data within these systems. e-Buzima, Rwanda’s electronic medical records platform, enables direct point-of-care data entry by healthcare providers, reducing reliance on paper-based registers and minimizing manual errors. Developed as part of Rwanda’s broader digital transformation agenda, e-Buzima is designed to synchronize patient data across all health facilities that are using it, allowing medical personnel and patients to access health records in real time enhancing data sharing during referrals. The system also aims to reduce patient waiting time, ease hospital congestion, and improve prescription accuracy. When linked with the HMIS and visualized through NHIC dashboards, this data enables central- and district-level teams to track key MNH indicators in real time, supporting more precise, data-informed decision-making. It is hosted on national servers, ensuring data security and system uptime, while eliminating full dependency on monthly data entries by health facility-based data managers.

As part of the data transformative agenda for Rwanda, the Government launched the National Health Intelligence Center (NHIC), a strategic national platform designed to collect, process, and analyze real-time data from across the health system to strengthen evidence-based decision-making and policy development. The National Health Intelligence Center consolidates data from the across the healthcare system — from community health workers at the village level to national referral hospitals and across different health institutions —providing a comprehensive, real-time picture of Rwanda’s health landscape. It integrates data across critical domains including primary healthcare services, disease prevention and outbreak control, emergency and referral response, health financing and workforce, supply chain and logistics, and civil registration and vital statistics. The NHIC will generate real-time interactive dashboards from e-Buzima and HMIS, accessible at national, district, and facility levels. These dashboards will visualize key MNH indicators, including process metrics such as timely use of uterotonics, management of maternal complications, and neonatal resuscitation practices, enabling health workers and managers to act on emerging trends.

The dashboards will also be used during monthly performance review meetings at district level and during national joint monitoring and evaluation reviews. Program teams will use these insights to track coverage and quality of care, identify underperforming health facilities, and inform targeted support. NHIC will further support data use by issuing biannual data bulletins summarizing trends, key achievements, and recommendations. In addition, a digital feedback loop will be integrated into e-Buzima, where data validation prompts and quality alerts will flag common entry errors in real time, helping improve accuracy at the source.

Beginnings Fund will provide support for specialized technical staff, and equipment to support MNH service delivery system optimization and data use. Two data scientists and a statistician (with expertise in MEL) will be embedded within NHIC to improve data quality, oversee real-time analytics, and develop dashboards that allow stakeholders to identify gaps and monitor progress across targeted health facilities as part of the quality improvement and supportive supervision and mentorship activities. Both positions will be gradually absorbed into the government structure, ensuring long-term sustainability of capacity gains.

CHAI will support MEL, that will be embedded from Year 1, Q2 onwards, focusing on continuous performance tracking, adaptive management, and generating practical learning to drive impact, scalability, and sustainability. The MEL team—working in close collaboration with the MOH/NHIC, and facility-level MEL teams—will leverage routine data sources from HMIS, eLMIS, e-Buzima, and field-level data collected by clinical mentors, alongside insights from supervision, mentorship, training reports, clinical audits, and stakeholder consultations.

Both quantitative and qualitative data will be systematically analyzed to ensure that health information reflects the real operational context, helping identify challenges, track progress, and guide realistic and actionable solutions. MEL activities—including bimonthly data verification, clinical audits, and routine progress reviews—will guide adaptive implementation, quality improvement, and workforce development. This approach is more programmatic, embedded within government systems, and focused on driving continuous improvement rather than formal research. Findings will directly feed into monthly check-ins, quarterly reports, and serve during the RMNCAH Steering Committee, supporting real-time decision-making and informing the scaling of data-driven MNH quality improvement nationally and sustainably beyond the project period. This MEL approach seeks to ensure the BF investment not only drives improvements within the targeted high-burden facilities but also contributes to the institutionalization of data-driven quality improvement across Rwanda’s MNH system, adaptation and scale-up.

Progress against key program milestones (Annex A) will be monitored and reviewed by the MOH and implementing partners through regular meetings with the program management committee, supporting the identification of early signs of success and ensuring that strategies are adapted to evolving needs.  Annually, with support from CHAI, RBC will lead a compilation of a progress report, tracked against the program’s Pathway to Impact.

The Beginnings Fund consortium will leverage MOH structures to share results, exchange insights, and channel findings to scale MNH improvements nationally through HSSP V and Technical Working Groups. Annual learning exchanges between focus districts will be conducted to promote the hands-on sharing of program innovations and the fostering of communities of practice. To ensure that improved MNH data translates into joint accountability across the health sector, the MOH Technical team will ensure that key indicators for MNH are incorporated into the MOH unified M&E framework. This will ensure that MNH indicators are tracked, and lessons are shared during health sector reviews at the facility, district, and national levels, creating a strong foundation for continuous improvement and scale up.

Risk and Reward

| Risks (Significance/Likelihood) | Mitigating Strategies |
| --- | --- |
| Geopolitical factors (High/Moderate) Hospitals near borders, such as Gisenyi DH, Ruhengeri L2TH, and Kibogora L2TH, may receive an increased number of maternal and newborn cases due to regional instability, overwhelming already fragile facilities, and increasing the risk of stillbirths due to trauma. | Encourage MOH to work with partners such as WHO and UNFPA to develop emergency preparedness plans to ensure continuity of MNH services in such settings. Include a contingency in the overall budget to cater for such emergencies. The steering committee will decide on the nature of support to be provided during such emergencies. Advocate to have Beginnings Fund, be a part of the country health sector coordination group to influence resource allocation for such emergencies. |
| Disrupted supply chains (High/High) Essential maternal and newborn health commodities (e.g., oxytocin, CPAP machines) may face delays or shortages due to global supply chain disruptions. | Leverage the CHAI market shaping grant to ensure availability of essential MNH commodities. CHAI will continue collaborating with the MoH, RBC, and RMS to proactively identify potential supply chain bottlenecks using real-time data and jointly strengthen forecasting, inventory tracking, and procurement coordination |
| Health workforce shortages and turnover (High/High) Brain drain of trained healthcare providers, particularly in maternal and neonatal care, may limit the impact of interventions. | Implement targeted training programs to upskill existing health workers. Require that all supported trainees sign the “Training & Public Service Agreement” with the Ministry of Health to ensure their retention in public facilities for five years after completing their studies. |
| Delays in the implementing agencies (RMS, RBC, MOH) disbursement of funds for activity implementation due to bureaucratic bottlenecks in the (Moderate/Moderate) – Administrative challenges may slow down the procurement of essential supplies and the rollout of interventions. | Engage stakeholders early to ensure alignment of timelines and priorities. Leverage CHAI to support the implementing agencies, to accelerate implementation |

Transition and Sustainability Plan

Rwanda's vision for sustainable and equitable access to MNH commodities and life-saving interventions centers on building strong local capacity and fostering data-driven decision-making.  The nation recognizes that long-term success depends on moving beyond reliance on external donor funding and maximizing the use of constrained resources.  This strategic investment from the Beginnings Fund will be pivotal in achieving this vision, specifically by bolstering the MNCH workforce and fortifying the systems that support it.  This investment will be the cornerstone of Rwanda's transition to a resilient and locally driven MNH system.

To ensure continued availability of essential MNH commodities, RMS has adopted a strategic purchasing approach focused on value-for-money, standardization, and long-term sustainability in the procurement of health commodities and medical equipment. By leveraging centralized planning, market intelligence, and performance management, RMS ensures that investments translate into improved health outcomes. For equipment, RMS has ensured that supplier contracts include training of hospital Biomedical engineers in preventive and curative maintenance, and provision of technical support where the engineers may be challenged, in addition to availing spare parts whenever needed.  Through BF, which aims to enhance maternal and newborn health in Rwanda, this approach will be instrumental in guiding the procurement of high-quality, priority medical equipment. The strategy ensures that every investment is aligned with national health priorities, supports equitable access to essential services, and contributes to strengthening the continuum of care for mothers and newborns across the country. Additionally, The Government of Rwanda is actively working to ensure long-term sustainability by progressively integrating essential MNH commodities into service packages covered by the CBHI scheme. This transition aims to reduce reliance on external funding and embed MNH commodities into the routine financing structure. The integration process is already underway, and many of the prioritized commodities are expected to be fully covered by CBHI well before the end of the three-year period. Beyond year three, the Beginnings Fund is not expected to support any procurement of MNH commodities.

Under the health workforce, the government launched the 4x4 program in July 2023, with the first supported student cohorts beginning in December 2023 and March 2024. The first wave of graduates is expected late 2027 or early 2028.  All supported students have signed a Public Service Agreement with the Ministry of Health, committing to serve in the public sector for five years. The 12 districts included in the Beginnings Fund proposal are not only prioritized under this initiative but also reflect national priorities due to their large catchment populations and significant service delivery needs. Therefore, a substantial share of 4x4 graduates—particularly nurses and midwives—will be deployed to hospitals, health centres, and health posts in these districts.

Data and digital systems: All data systems (e-Buzima, HMIS, and NHIC) are fully hosted and managed by the Government of Rwanda through the Ministry of Health including routine maintenance costs for internet, local area network and hardware at health facilities. By supporting upgrades within these existing national platforms rather than introducing parallel tools, the BF ensures full alignment with government priorities and long-term integration into Rwanda’s digital health architecture. System enhancements, such as improved user interfaces, alert mechanisms, and real-time dashboards, will directly benefit a broader range of health programs beyond MNH, thereby strengthening Rwanda’s overall MEL system. In the long run, the BF’s support will help institutionalize a culture of data use, self-monitoring, and accountability at all levels of the health system. By improving real-time visibility and supporting data-driven resource allocation, this investment will ensure that limited health sector resources are directed to the most impactful and cost-effective interventions ultimately contributing to improved outcomes for women, newborns, and the broader population.

Annex A: Pathway to Impact (Still under development)

Annex A: Pathway to Impact

By 2030:

- Reduction in maternal mortality by 10.5% from 229 to 205 per 100,000 live births live births, 895 maternal lives saved

- Reduction in stillbirths by 11% from 17 to 15 per 1,000 live births, 4.663 stillbirths prevented

- Reduction in neonatal mortality by 39% from 18 to 11 per 1,000 live births, 9,027 newborn lives saved

| Obj. 1: Priority interventions scaled to address drivers of maternal and neonatal mortality and stillbirths |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 191 facilities in 12 focus districts (Bugesera, Gasabo, Gicumbi, Muhanga, Musanze, Ngororero, Nyagatare, Nyamasheke, Nyanza, Nyarugemge, Rubavu, and Rwamagana) which represent 43% of maternal and newborn deaths in Rwanda, and 39% of live births (154,687) annually: |  |
| - >80% of 191 facilities (designated for BEmONC and CEmONC) with all tracer commodities to perform EmONC by end Year 1 - >80% of 15 facilities meet EMoNC signal functions by end Year 2 - 169 providers including 144 Nurses/Midwives from HCs trained on POCUS and 24 Doctors trained as Trainers on POCUS - 72 Providers including nurses and doctors from hospitals neonatology unit will be trained on both sick and small newborn care - A pool of 40 mentors with competencies in antenatal, intrapartum, safe surgery and anesthesia, essential and small and sick newborn care established by end Year 1 (mentors will have different individual competencies) - Data-informed quality improvement cycles happening independently at each focus facility at a minimum frequency of one cycle per quarter per facility by end Year 3 | - >80% of health workers (~402) in targeted maternity and newborn units (12 district hospitals and 3 medicalized health centres) achieve EmONC and SSNC competency by end Year 3 (target to be determined post-baseline assessment) Coverage of interventions increased to 80%, by end Year 2: - >90% of pregnant women attending ANC screened for 1) anemia, 2) infection, and 3) high-blood pressure - % of women attending ANC who receive POCUS or U/S, with gestational age recorded on the first visit - % of women receiving quality intrapartum care and management of complications as per guidelines for - Post-partum Hemorrhage (PPH) - Sepsis - Pre-Eclampsia/Eclampsia - Obstructed labor - % of women who received digital intrapartum monitoring in labor - % of eligible women with pre-term labor who received antenatal corticosteroids - % of women with PPH detected early (300ml-500ml blood loss) and WHO-recommended treatment bundle received - % of eligible babies who received neonatal resuscitation - % of eligible preterm and low birth-weight babies who receive iKMC - % of babies between 1000-1499g who receive prophylactic CPAP - % of eligible babies between 1500 and 1999g with respiratory distress who receive CPAP - % of babies with clinical jaundice who receive phototherapy - % of babies with suspected sepsis who receive parenteral antibiotics - % of babies not hypothermic on admission to the neonatal unit - % of babies not hypothermic at any time in the neonatal unit At 12 CEmONC facilities (baseline and targets for below indicators to be established by end Year 1 following baseline health facility assessment) - At least 10% of expected live births delivered via cesarean section - Increased % of women with direct obstetric complications who are definitively treated without outward referral - 90% of facilities meet standard safety and infection prevention practices according to the Safe Surgical Checklist by end Year 3 - Less than 10% of post c-section surgical site infections while in-patient in the facility by end Year 3 - Reduced decision-to-incision time to 30 minutes or less by end Year 4 (measured by quality improvement cycles) - % and # of c-sections at 12 district hospitals - % and # of referrals between 12 district hospitals - % of babies admitted in the NICU with a neonatal admission diagnosis of birth asphyxia - % and # of fresh stillbirths in 191 targeted facilities |

| Obj. 2 Availability of quality MNH commodities improved in focus districts and at national level |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 191 facilities in 12 focus districts (Bugesera, Gasabo, Gicumbi, Muhanga, Musanze, Ngororero, Nyagatare, Nyamasheke, Nyanza, Nyarugemge, Rubavu, and Rwamagana) |  |
| - 100% of 191 facilities provide package of ANC diagnostics (anemia, infection, pre-eclampsia detection, blood glucose, BMI, digital foetal heart monitoring) by end Year 1 - 100% of 191 healh facilities equipped with POCUS - 100% of 191 BEmONC and CEmONC health facilities equipped with appropriate bundles of MNH products and newborn corners by end Year 1 - Planned preventive maintenance for MNH devices conducted according to MOH guidelines through the MEMMS by end Year 2 | - <10% stockouts of critical MNH commodities in targeted facilities by end Year 3 - >90% uptime of antenatal, intrapartum, and small and sick newborn care devices by end Year 3 |
| At national level |  |
| - Guidelines – Integration into Essential Medicine List , Standard Treatment Guidelines (STG), Essential Equipment List updated and regulatory approval received for key MNH commodities (point-of-care ultrasound, heat-stable carbetocin, detection drapes) by Year 3 | - Variance between the forecasted and actual demand for MNH products reduced to <15% by end Year 5 - Decreased gap between quantified need for MNH commodities and budget to <10% by end Year 5 - 90% of targeted facilities budgeting for essential MNH commodities costs based on actual need by end Year 5 - Sustainable financing plan for focus products (POCUS and PPH bundle) developed and implemented by end Year 5 |

| Obj. 3 Improved quality, number, distribution of MNH workforce in focus districts and at national level |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 12 health facilities in 12 focus districts (Bugesera, Gasabo, Gicumbi, Muhanga, Musanze, Ngororero, Nyagatare, Nyamasheke, Nyanza, Nyarugemge, Rubavu, and Rwamagana) |  |
| - In 5 level 2 teaching hospitals 10 pediatricians/neonatologists recruited as faculty by end Year 1 - In 8 level 2 teaching hospitals 16 nurse specialists recruited as faculty by end Year 1 - In 5 level 2 teaching hospitals 20 additional doctors (4 per hospital) enrolled into pediatric residency programme by end Year 1 - In 8 level 2 teaching hospitals 32 additional nurses (cohort 1) into neonatal nursing or peri-operative nursing residency program - In 4 district hospitals two additional nurses per hospital (one midwife and one neonatal nurse) | - % of targeted maternity and neonatal units achieve staff: patient ratios of 1:12 by end Year 2 (target to be determined post-baseline assessment) - % of targeted CEmONC facilities that have requisite skills-mix of MNH specialists (midwives, anesthetists, theatre nurses, pediatricians, OBS/GYN) by end Year 5 (target to be determined post-baseline assessment) - At least once a month QI sessions and training led by nurse and pediatric specialists in each of the hospitals - 104 health workers (64 nurses and 40 doctors) complete post-basic/post-graduate training as MNH cadres - 90% optimally deployed to high-burden maternity and newborn units - 90% retained in the public sector for 12 months |
| At national level |  |
| - Integrate optimized EmONC, including safe cesarean section techniques, care of, and use of technologies for small and sick newborns, into the national medical education curriculum | - Undergraduate scholarships to 300 midwives, 150 nurses and 130 non-physician anesthetists. - 95% are strategically selected according to Beginnings Fund-MOH criteria27 - 90% complete training and graduate within 12 months of program timeline - Increase in number of MNH cadres in the public sector (baseline to be determined) - 90% appropriately deployed to high-burden maternity and newborn units - 90% retained in the public sector at 12 months post deployment |

| Obj. 4: Critical health system enablers, including MNH infrastructure, data and quality, emergency transport and referral systems, leadership and management, and advocacy strengthened for greater impact and sustainability |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| Infrastructure: - Infrastructure assessment completed by end month 6 in Kabaya and Gisenyi district hospitals - Renovation of Gisenyi neonatal care unit completed by end Year 2 - Construction of the maternal and newborn unit of Kabaya hospital completed by end Year 3 MNH Data Systems: - E-Buzima rolled out to all 12 hospitals and 33 health centers where it is not operational (equipping with computers, internet, and training) by end month 6 - M-NID data systems fully operational in 177 BEmONC and CEmONC sites by end Year 1 - M-NID data baseline established by end Year 1.5 (month 18) - M-NID dashboard developed and at facility level by end Year 1 - Program monitoring dashboards for quality of care, workforce, and referrals operationalized within the NHIC and regularly used by RBC in focus facilities, districts and at national level by end Year 1 | Infrastructure: - One maternal newborn unit newly constructed, equipped and furnished at Kabaya hospital - One neonatal care units renovated - 100% increase in functional Level 2 neonatal units in 12 focus districts MNH Data Systems and QI: - 90% of patient-level M-NID data meet program defined data quality and completeness criteria by end Year 3 - >95% of facilities utilize MNH dashboard for quality improvement and decision making by end Year 2 Emergency Transport and Referral: - Newborn corners in 174 health centers and second-generation health posts equipped with warmers and oxygen concentrators to facilitate referral of sick newborns |

Annex B: Target Facilities

Total number of target facilities as represented by the 12 high-burden hospitals and its network of health facilities:

Annex C: MNH Commodities Funding Sources and Beginnings Fund Budget

Annex D: Targeted enrollment for aggregated healthcare cadres per the 4x4 reform

This number will increase as the Government of Rwanda confirms more partner commitments for the next five years.

RBC/MCCH Annual Report, 2023/2024

Trends in maternal mortality 2000 to 2023: estimates by WHO, UNICEF, UNFPA, World Bank Group and UNDESA/Population Division. https://www.who.int/publications/i/item/9789240108462

MoH Situation Analysis, 2024

Maternal, Child, and Community Health Division Annual Report 2022-2023

HMIS, 2024

Health Sector Situation Analysis Report, 2024

Republic of Rwanda, Ministry of Health, Health Sector Strategic Plan V July 2024-June 2029

Average annual government expenditure to scale up MNCH Interventions nationally, including training of health workers and procurement of essential medicines across all health facilities,

MBZ and CIFF numbers TBD.

Funds obtained through a loan facility to Government of Rwanda from Agence Française de Développement (AFD)

GOR and partners have so far invested ~$6.4M to scale up e-Buzima, install LAN and purchase computers. Beginnings Fund  will leverage on this investment in the 12 priority districts.