# BEGINNINGS FUND KENYA INVESTMENT PLAN

Kenya Investment Plan Overview

| Grantees: | Investments Presented: - Council of Governors - Digital Health Agency - International Centre for Reproductive Health Kenya - Jacaranda Health - Kenya Red Cross Investments Planned: - Aga Khan University Kenya (NEST360) - Lwala Community Health Alliance - HATCH Technologies - InSupply Health - Clinton Health Access Initiative (CHAI) - Emergency transport and referral system partner (TBD) - Infrastructure improvements partner (TBD) |
| --- | --- |
| Implementer(s) (if different to Grantee): | - Implementing partners under Clinton Health Access Initiative (CHAI) - Nairobi University - Moi University - Aga Khan University Kenya - Kenyatta National Hospital Nursing School - Kenya Medical Training College - Strathmore Business School - Professional Associations |
| Geographic Focus: | 21 counties (15 intensive counties - Bungoma, Kakamega, Kiambu, Kilifi, Kisumu, Mombasa, Nairobi, Nakuru, Garissa, Kisii, Migori, Machakos, Kwale, Kericho, and Kajiado; 6 equity counties - Samburu, Tana River, West Pokot, Turkana, Mandera, and Wajir); Council of Governors and national support |
| Amount: | USD76.0million budget, of which USD35.0million (44%) in investments are being currently presented to the Investment Committee, and the remainder will be presented by Q2 2026. This plan covers both presented and planned investments. |
| Co-Investment: | Total: USD108million: - Government of Kenya: USD325.7million - Technical Support Partners: USD34.1million |
| Term: | 60 months (1 May 2026 - 31 March 2031) |
| Investment Description and Impact Goals: | The Beginnings Fund investment will scale proven, high-impact interventions targeting the leading causes of maternal mortality— that is, postpartum haemorrhage, hypertensive disorders, and infections—and the primary drivers of neonatal deaths, which include prematurity, birth asphyxia, and sepsis. The approach focuses on enhancing the workforce numbers and skills, commodity security, data systems, and referral networks. Beginnings Fund will: - Scale up of priority evidence-based interventions. - Improve access to and quality of essential MNH commodities and equipment. - Increase the availability, competency, and equitable distribution of MNH health workers. - Strengthen MNH emergency referral systems. - Enhance MNH data quality and use through integration into Taifa Care (the national EMR). - Renovate and equip Level 2 and 3 newborn units and improve labour and delivery wards and operating theatres. Through these investments, Kenya aims to save approximately 46,494 lives ((Newborn lives 25,432, Still births 16,162, Maternal lives 4,900) by 2030. |
| Pathway to Impact: | See Annex A |
| Governance and Management: | Beginnings Fund will sign a Memorandum of Understanding with the Government of Kenya outlining key commitments and measures of success once this Investment Plan is approved. The Ministry of Health (MOH) and the Council of Governors (CoG) health secretariat will oversee governance and management of the Kenya Investment Plan. The governance mechanism is designed to align closely with existing national and sub-national health systems and structures, ensuring coherence, efficiency, and country ownership. A Steering Committee—comprising of the Principal Secretary of the State Department of Medical Services; Chief Executive Officer of the Council of Governors; the Beginnings Fund CEO, Alice Kang’ethe; Director of Family Health, Dr. Isaak Bashir; Chair Chief Officers for Health Caucus and Chair County Executive Committee members (CECs) for Health Caucus—will provide strategic oversight throughout the implementation of the plan. The steering committee will meet quarterly in the first two years and bi-annually thereafter. A Management Team, consisting of the technical leads from the implementing agencies Kenya Medical Supplies Agency, Digital Health Agency, Kenya National Blood Transfusion Services, Directorate of Family Health, Kenya Health Human Resources Advisory Council, the Council of Governors health directorate, County Executive Committee members (CECs) for Health nominated by the CEC Caucus, representatives from the implementing partners and the Beginnings Fund investment team, will manage implementation, monitor progress, and support course correction on an ongoing basis. Audits: This program will utilize annual audits conducted by Kenya’s Office of the Auditor General and independent audits through appointed auditors by Beginnings Fund for the implementing partners. |
| Reporting | Each grantee will submit annual Narrative and Financial Reports to the Beginnings Fund within two months of the close of the reporting period. |

Acronyms and Definitions

ANC 			Antenatal Care

BEmONC		Basic Emergency Obstetric and Newborn Care

CEmONC 		Comprehensive Emergency Obstetric and Newborn Care.

COG			Council of Governors

CPAP 			Continuous Positive Airway Pressure

CTG 			Cardiotocography

DHA			Digital Health Agency

DHS 			Demographic Health Survey

ELMIS			electronic Logistics Management Information System

EMR 			Electronic Medical Records

HMIS			Health Management Information System

HSSP 			Health Sector Strategic Plan

IKMC			Immediate Kangaroo Mother Care

KEMSA			Kenya Medical Supplies Agency

KHIS 			Kenya Health Information System

MNH			Maternal, Newborn Health

MOH			Ministry of Health

NICU 			Neonatal Intensive Care Unit

POCUS			Point-of-Care Ultrasound

PPH			Postpartum Hemorrhage

RMNCAH		Reproductive, Maternal, Newborn, Child and Adolescent Health

SHA			Social Health Authority

SHIF			Social Health Insurance Fund

SSNC			Small and Sick Newborn Care

TXA 			Tranexamic Acid

UBT 			Uterine Balloon Tamponade

WHO 			World Health Organization

Situational Analysis

The Government of Kenya, under the leadership of the President and Cabinet Secretary for Health, has renewed its commitment to reducing maternal and newborn mortality. This includes launching a Rapid Response Initiative (RRI), a short, intensive six-month cycle (March to August 2026) of targeted, high-impact interventions to accelerate progress and build momentum toward national MNH goals. To ensure policy decisions are anchored in accurate and credible evidence, in the first quarter of 2026 Kenya is also conducting a Mini-Demographic Health Survey to generate an updated population-based maternal mortality ratio, alongside a Reproductive Age Mortality Survey (RAMOS) review of facility-level maternal deaths with early results expected in the third quarter of 2026; together, these will provide clearer, more reliable MNH data to guide program direction and assess national progress.

Kenya's Health System and Recent Reforms

Kenya's healthcare system is structured into a two-tiered government framework as defined by the 2010 Constitution: the national government and 47 county governments.  The national government handles policy, regulation, and oversight of national programs and national referral hospitals (level 6), while county governments are responsible for the direct delivery of health services, resource management, and public health initiatives. Counties are coordinated through the Council of Governors (COG), a non-partisan organization that brings together all the forty-seven (47) Governors. It provides a forum of consultation and sharing of information and best practices among County governments. This decentralized approach, guided by the Kenya Essential Package for Health (KEPH), aims to improve equity and access by tailoring services to local needs across six distinct levels of care, from community health services (Level 1) to highly specialized national hospitals (Level 6).

To achieve its Universal Health Coverage (UHC) goal by 2030, Kenya has enacted several key legislative reforms. The Social Health Insurance Fund (SHIF) Act seeks to provide sustainable and equitable financing for healthcare by pooling resources from contributors to cover essential health services. The SHIF Act is central to reducing the financial burden on households by lowering out-of-pocket health expenditure, which has historically been a significant barrier to accessing healthcare. The Facility Improvement Financing (FIF) Act grants greater financial autonomy and incentivizes efficient resource use. It ensures that health facilities can generate and utilize funds transparently for their development and operational needs with the aim of enhancing service delivery and improving the overall quality of care. The Primary Healthcare (PHC) Act strengthens community-based care to focus on prevention and promotion, thereby reducing the strain on higher-level facilities. The Digital Health Act seeks to integrate digital technologies into healthcare to enhance efficiency, transparency, and equity. It provides a framework for the use of tools such as electronic health records (EHRs), telemedicine, and mobile health applications, ensuring that digital solutions are accessible and interoperable across the healthcare system. While all the above are strong initiatives, they are primarily geared towards improving access and financial risk protection, and there are not yet mechanisms in place to evaluate the achievement of effective coverage with high-quality care.

Maternal and Newborn Health: Progress and Persistent Challenges

While Kenya has made significant strides in maternal and newborn health (MNH) indicators, such as increasing facility deliveries to 89%, progress in reducing maternal and newborn deaths has stagnated. The Kenya Demographic and Health Survey (KDHS) 2022 report that ANC coverage for at least one visit from a skilled provider was 98%, however, only two-thirds of women had at least four ANC visits during their most recent pregnancy and only 29% of women had their first ANC visit during the first trimester (12 weeks). Despite more women accessing care, the Maternal Mortality Ratio (MMR) remains high at 355 per 100,000 live births, resulting in approximately 5,000 maternal deaths annually due to pregnancy-related causes. Similarly, the Neonatal Mortality Rate (NMR) is stubbornly high at 21 per 1,000 live births. Neonatal deaths account for 66% of infant deaths and 51% of total under-five deaths, pointing to a need for targeted interventions during the neonatal period to meaningfully reduce the overall under-five mortality rate. The 2021 estimates by World Bank placed the stillbirth rate in Kenya at approximately 19 per 1,000 births. This rate, while slightly improved from previous years, remains high compared to the global target of 12 per 1,000 births. Most stillbirths are caused by intrauterine hypoxia, often preceded by clinical indications of preeclampsia, placental abruption, obstructed labor, and small-for-gestational-age growth restriction. Maternal deaths still account for 16% of all deaths among women of reproductive age and remain a leading cause of death for adolescent girls in Kenya. These high maternal and neonatal mortality rates and stillbirth rates are suggestive of underlying issues in healthcare delivery and quality of care. This slow progress places the country off track to meet the Kenya Vision 2030 goals and the Sustainable Development Goal (SDG) targets by 2030. To achieve the national maternal and newborn goals and the SDGs, the annual reduction in maternal mortality would need to accelerate by approximately tenfold, and neonatal mortality by fifteenfold, relative to the current pace of decline.

The leading direct causes of maternal mortality are postpartum haemorrhage (37%), hypertensive disorders in pregnancy (21%), pregnancy-related infections (12%), and ruptured uterus (8%). The leading indirect cause of maternal mortality is anaemia. Newborn mortality is largely contributed to by prematurity (34%), birth trauma/birth asphyxia (32%), and infections/sepsis (9%). Inadequate coverage and service readiness with quality newborn services contributes to sub-optimal care. For instance, the Kenya Health Facility Census report 2023, highlights that out of all the health facilities assessed that had maternity services, only 12% provided newborn care services. Overall, only about 40% of the facilities had all the requisite equipment and personnel to provide the newborn care services with readiness to provide newborn health services being quite low (22%). Earlier work from 2018 on quality of newborn care in Nairobi County, showed that while 56% of newborns had access to a health facility providing 24/7 newborn care, only 25% received high quality clinical care with zero percent having quality clinical and nursing care.

Availability of Labour and Delivery Services:  Kenya conducted the Quality-of-Care Health Facility assessment of Emergency Obstetric and Newborn Care (EmONC) services which showed significant gaps in both basic and comprehensive care. Although nearly half of facilities offering delivery services reported providing Basic EmONC, only 37% could perform all seven required signal functions, with particularly low readiness for oxytocic administration (69%) and assisted vaginal delivery (48%). Newborn resuscitation capacity was similarly constrained: while 65% of facilities reported offering the service, essential equipment such as suction devices, neonatal bag and mask, resuscitation tables, and radiant warmers were available in only 45–69% of sites. Workforce capacity remains limited, with just 36% of staff trained in essential newborn care and 28% trained in EmONC within the last two years. This is evident as only 40% of health workers could correctly diagnose and treat PPH correctly. Comprehensive EmONC readiness is even more constrained, with only 19% of higher-level facilities able to deliver the full package, largely due to low availability of caesarean sections (29%) and blood transfusion services (31%). Oxygen availability was also inadequate, present in only 44% of delivery facilities. These service delivery gaps align with findings from the 2024 MPDSR report, which attributes delays in receiving appropriate care at facilities due to shortages of skilled staff, inadequate staffing levels, and lack of blood for transfusion, underscoring systemic constraints that directly contribute to preventable maternal and neonatal deaths.

Human Resource for Health Constraints: Kenya’s health workforce is dynamic and complex. The health workforce is managed directly by the county governments through the County Public Service Boards. A marginal number of frontline healthcare workers are directly managed under the national Government through the Public Service Commission. In Kenya, there is a paradoxical shortage of health workers in facilities with a surplus of trained unemployed health workforce. Reports show that many counties and health facilities experience significant shortages and maldistribution of frontline healthcare workers amidst growing unemployment of qualified personnel. Further, even when counties recruit, recent findings highlight mismatch in the mix of staff employed in the health sector with 15 out of 47 counties having more than 40% of the total workforce being non-health care providers (norm should be 30%). As such, the health workforce crisis is attributable to financing and planning problems to get health workers in the right spaces.  Further, in a study characterizing Kenyan hospitals’ suitability for medical officer internship training, pediatricians and obstetrician/gynecologists were not available in nine and five internship training centers respectively out of 61 training centres. Kenya’s medical specialist production remains limited due to constrained training capacity, high costs, and long training durations. Most specialists are concentrated in urban centers and private facilities, leaving rural and public hospitals critically underserved, especially those in arid and semi-arid regions. Further, many specialists seek opportunities abroad due to better remuneration and working conditions. Expanding training capacity, incentivizing rural deployment, and leveraging telemedicine are essential to ensure equitable access to specialist care nationwide. Recent data on nurse staffing ratios across 15 county referral hospitals over two years showed a median of one nurse to 20 babies in newborn units with up to 1:40 during night shifts (unpublished data) compared to the WHO global recommendation of one nurse to four babies.  In recognizing that human resources for health remain foundational to universal health coverage, the government established a HRH taskforce that identified fragmentation across 43 cadres, weak regulatory coherence, and poor workforce data, recommending streamlined planning, stronger coordination, and more equitable deployment to improve system performance.

Limited availability of commodities, equipment and diagnostics. Many maternal and newborn health (MNH) products have limited availability due to supply chain weaknesses, including inconsistent procurement, demand and supply forecasting, distribution planning and inventory management. The Quality-of-Care Health Facility Assessment (2024) reported availability of essential tracer commodities for labour and delivery at 65% in health facilities. Shortages of essential commodities contribute to high out-of-pocket health spending, with medicines accounting for an estimated 50% of these costs. Further, some MNH medicines have been found to be of poor quality due to lack of quality control in diverse unregulated supply, distribution, and storage channels. The Ministry of Health has rolled out KEMSA reforms that span governance restructuring, supply chain digitization, and operational overhauls aimed at improving transparency, restoring public trust, and achieving over 90% order-fill rate by end 2025 to strengthen commodity availability for service delivery. The reforms aim at strengthening facility ordering capacity, order rates, order turn-around and last mile distribution. By late 2025, the Government recapitalised KEMSA with a KSh 1.5 billion grant and advanced plans to secure a KSh 10 billion revolving credit facility to strengthen continuous supply of health commodities. As part of ongoing reforms, KEMSA has been undertaking operational transformations aimed at significantly raising its order fill rate — with its leadership reporting progress above 70% by the end of 2025 and plans to exceed 90% by the end of 2026.

Kenya continues to face a persistent shortage of blood and blood products, with only 449,689 units collected in the 2023/24 financial year, falling short by 15.7% against the WHO-recommended benchmark of at least 1% of the population donating annually, which translates to 533,310 units for Kenya’s 53.3 million citizens. This deficit is driven by weak donor mobilization, cultural barriers, inadequate financing, and uneven distribution of collection centers, compounded by inefficiencies in screening and supply chain systems. Maternal health bears the greatest burden, as 34% of all transfused blood is used to manage obstetric emergencies such as postpartum haemorrhage, the leading cause of maternal mortality. To address these challenges, Kenya has restructured its blood services through the establishment of the Kenya Blood Transfusion and Transplant Services (KBTTS) directorate to facilitate direct budget line from treasury, launched donor campaigns in schools and workplaces, and invested in equipment upgrades and emergency mobilization drives. However, gaps remain in sustainable financing, equitable access across rural and marginalized counties, modernization of digital tracking and supply chain systems. Notably, the 2025/26 budget allocated Ksh 300 million (approx. USD 2.4 million) for national blood transfusion services, down from consistently higher funding in prior years, reflecting broader reprioritisation within a constrained health budget and reductions in planned development allocations. This reduction highlights persistent financing gaps relative to the estimated resources required to fully support blood safety and supply targets.

Limited availability of referral and transport systems during maternity and newborn emergencies: In Kenya, 89% of facilities report to have some form of referral services, however, many were basic, under-resourced, under-developed and under-documented. Obstetric emergencies are plagued with poor referrals stemming from inconsistent adherence to protocols and SOPs, inadequately structured communication systems, inadequate tracking of available resources, delayed recognition of emergency situations by healthcare workers and lack of clear budget lines for referral transport systems. Neonatal referrals are particularly neglected, lacking thermal regulation, respiratory support, and continuous monitoring. Kenya’s referral strategy does not address neonatal transport explicitly, leading to avoidable maternal and neonatal morbidity and mortality.

Insufficient use of data for programmatic decision making. The first confidential enquiry into maternal deaths demonstrated poor documentation in maternal files with missing and incomplete data. Only 18% of health facilities have evidence of conducting data quality audits, of which only 21% had established concrete action points based on the data quality findings.  Most of the data in use is aggregate monthly data which is not effective in identifying gaps in pathways of care. Standardized individual-level in-patient datasets provide more detailed data for quality improvement (QI) initiatives to improve maternal and newborn care. These granular data are also key for supporting clinical audits, such as MPDSR processes, and other QI initiatives through audit and feedback. Lack of patient level data, longitudinal follow up, weak maternal & neonatal pairing, and delayed reporting constrain program planning and evidence use. Digitization of MNH individual level data and integration into Taifa Care EMR are essential for clinical governance, quality improvement, and accountability.  By February 2026, TaifaCare EMR had been deployed in 31 of Kenya’s 47 counties, and the Digital Health Agency (DHA) is continuing efforts to expand coverage to the remaining counties in the coming months.

Beginnings Fund Strategic Approach

In partnership with the Government of Kenya, Beginnings Fund investments aim to accelerate the reduction in maternal and neonatal mortality and prevent stillbirths to reach Kenya’s 2030 goals and save ~ 46,494 lives (Newborn lives 25,432, Still births 16,162, Maternal lives 4,900).  Beginnings Fund investments will support the rollout of priority interventions informed by evidence targeted at the drivers of maternal and neonatal morbidity and mortality; improve the availability and use of quality MNH commodities; advocate and support increase in the number and distribution of MNH health workers, and improve MNH systems; renovate/construct level 2 newborn care units at county and sub-county hospitals and at four high-burden county referral hospitals, expand newborn care to include level 3 newborn care units (5 NICU beds), enhance the competency and skills of health workers, advocate for iKMC and zero separation, and improve emergency stabilization, referral and transport of neonates, strengthen availability of blood and blood products, and integrate the maternal-newborn inpatient dataset in Taifa care (national EMR).

Beginnings Fund will make targeted investments in products, people, and health systems, focusing on strengthening the workforce, equipping facilities, and scaling low-cost, evidence-based interventions. Beginnings Fund investments will catalyse improvements and complement ongoing maternal and newborn investments in the target counties, including – but not limited to - the Building Resilient Health Systems (World Bank) and Increasing Access and Quality in Sexual, Reproductive, Maternal, Newborn and Adolescent Health Services in Kenya by STBF.

Beginnings Fund investments will ensure key technical partners are engaged to support implementation under the leadership and direction of both national and county government to ensure all interventions are embedded in national and county structures from inception. Investments will be made through relevant Government of Kenya departments and agencies (the Kenya Medical Supplies Authority, Kenya Blood Transfusion and Transplant Services Directorate, Digital Health Agency), the target counties through the Council of Governors, professional associations, training institutions, and technical support through non-government organizations.

Based on engagement with the MOH and CoG technical teams and stakeholders from lead government agencies and professional associations, key networks of care at county and sub-county level are targeted based on burden, referral patterns, equity, and need for implementation of priority interventions

The Beginnings Fund aims to target counties where 50% of preventable deaths occur, focusing interventions to achieve national impact. Pooled data from the Kenya Health Information System (KHIS) for 2022- 2024 were analysed to identify counties with the highest maternal and newborn deaths and stillbirths. Beginnings Fund investments will target 21 proposed counties. In the 15 highest-burden counties (maternal and newborn deaths and stillbirths high across all three indicators plus high number of deliveries), intensive support will reach 172 facilities with a package of interventions using a hub-and-spoke approach with the county referral hospital serving as the hub. Six marginalized and under-resourced counties have also been prioritised for equity and will receive targeted support for 28 highest-volume facilities (>600 annual deliveries). The 21 counties accounted for 62% of all facility deliveries, 62% of stillbirths, 68% neonatal deaths, and 69% of maternal deaths in Kenya in 2024.  Additionally, mapping planned or existing support against the 21 counties and health facilities will be undertaken to further refine the final set of hospitals and interventions to be supported.

The maternal and newborn intervention package described below will be the same in each focus facility, adjusted for existing support. National-level support for commodities, workforce development, data systems, policy, advocacy, blood transfusion services will benefit the entire country.

Description of Maternal and Newborn Health Intervention Packages for Beginnings Fund Support

To improve antenatal care, all focus facilities will be supported with the catalytic procurement of point-of-care diagnostics, including reagents, to facilitate early identification and management of infections, blood grouping, anaemia, hypertension, and diabetes. Point-of-care ultrasound (POCUS) will be introduced at all focus health facilities (starting at health centres (level 3) providing BEmONC to improve risk-differentiated care. Training and onsite mentoring of nurse-midwives, clinical officers and doctors, will be undertaken while also engaging with the MOH, professional associations and the Nursing Council of Kenya and other regulatory bodies to expand scopes of practice for these cadres to include POCUS use aligning with the recently launched National Obstetrics Point-of-Care Ultrasound (O-POCUS) Guidelines. The Beginnings Fund investment will leverage existing implementation and rollout of POCUS by the Gates Foundation to further increase coverage. Through the hub and spoke model high risk clinics will be established at high volume level 4 CEmONC facilities and county referral hospitals for follow up management of women requiring close monitoring and specialised care e.g. pre-eclampsia and diabetes in pregnancy mothers.

To improve care during labour and delivery and better identify foetal distress for early intervention, digital intrapartum and foetal monitoring technologies that span CTGs and foetal dopplers will be introduced at CEmONC and BEmONC facilities respectively. Strengthening of labour monitoring by dissemination and use of the labour care guide and partograph will be supported. The rollout and uptake of the WHO-recommended PPH bundle will be supported nationally through catalytic procurement and supply chain support linked to the CHAI regional investment. Uptake in focus facilities will be supported through training and onsite mentorship. To improve obstetric surgery and anaesthesia skills, a quality improvement approach will be implemented utilising the safe surgery checklist with a focus on county referral hospitals serving as a hub for dissemination.  Clinical attachments for refresher training in obstetric surgical teams at internship training hospitals will also be supported.

To improve essential newborn care and enhance neonatal resuscitation and stabilisation, newborn stabilisation sections will be equipped in all labour and delivery rooms, as well as in operating theatres in focus facilities. To improve Level 2 newborn care in 76 CEmONC health facilities, neonatal care units will be renovated and constructed in high-volume county and sub-county hospitals and health centres (CEmONC) in line with the draft MOH floor plans for newborn units.  Sites will be equipped, and clinical and biomedical staff will be trained to expand or establish Level 2 care. Data management and use, as well as QI cycles, and onsite mentoring will be supported at the facility level to improve coverage of CPAP, Kangaroo Mother Care, non-hypothermia, and phototherapy.

A Nairobi based study (Health Services that Deliver for Newborns) demonstrated that 18.3% of newborns require inpatient care, however, Kenya has only three WHO level 3 newborn units with a total of 27 functional NICU beds that cannot meet the demand for newborn specialised services. Investments made by ELMA through the Kenya Paediatric Fellowship Program have enhanced specialised workforce of critical care nurses, neonatologists and neonatal nurses to run level 3 newborn care units. To address the gap in level 3 newborn care, newborn units in three county referral hospitals will be expanded to include a 5-bed NICU capacity for level 3 newborn care. Selection of hospitals to provide level 3 newborn care will take into account regional disparity in the availability of specialised newborn care, availability of supporting critical care infrastructure and sub-specialists (e.g availability of functional ICU within the health facility) and commitment of the county government to support these services. Level 3 newborn care equipment, including mechanical ventilator machines, surfactant therapy and laryngoscopes for its delivery will be procured. Oxygen delivery systems will be enhanced through procurement of oxygen concentrators for facilities and portable cylinders for ambulances.

Cross-cutting interventions for Maternal and Newborn Health

Service Delivery At the national level Beginnings Fund will complement efforts by WHO, UNICEF, UNFPA, NEST360, and relevant professional associations working in close collaboration with MOH to review and update national MNH guidelines and clinical protocols to incorporate novel interventions and products such as the PPH bundle, caffeine citrate, and heat-stable carbetocin for PPH prevention, and  build capacity to establish a pool of county- and facility-based mentors to support ongoing monitoring and quality improvement in the implementation of the MNH bundles and IPC practices. Beginnings Fund will also support integration of novel interventions and products into EmONC, including safe cesarean section techniques, care of, and use of technologies for POCUS and other new innovations, into the national medical education curriculum, ensuring ongoing capacity building for intern doctors and early-career general practitioners.

The training approach will be harmonized with technical partners to include evidence-based practices including clinical facilitation (generic instructor course), simulation-based training facilitation, low-dose-high-frequency trainings, quality improvement, and equipment use. A pool of National Trainers, who are specialist paediatricians, OBS/GYN, anaesthesiologists, midwives, neonatal nurses, biomedical engineers, and members of professional associations will be trained. Master Trainers will train county mentors to provide on-site mentorship using a hub-and-spoke approach. County mentors will identify and train facility champions to provide on-site team simulation training, low-dose high-frequency drills, and quality improvement cycles informed by data, to institutionalise these practices. All target facilities will be equipped with simulation equipment to establish skills learning corners.  The mentorship system will be strengthened through the analysis and use of data to inform areas for mentorship and quality improvement. The mentorship system of the onsite hub and spokes model, where lower-level facilities receive support from higher-level health facilities, will be used to introduce guideline updates and priority interventions. This approach will also aim to align and strengthen primary care networks as part of the PHC act.

Scale-up of MNH product introduction, forecasting and quantification. Catalytic procurement for MNH products through the CHAI regional grant will support and sustainably introduce new and underutilized MNH products, including updating standard treatment guidelines and the Essential Medicine List, supporting regulatory approval, and harmonisation with KEMSA. Field Technologies, currently funded by Gates Foundation, is working with KEMSA, MEDS, DHA (EMR roll out) in some of the Beginnings Fund focus counties to optimise logistics, supplies and management systems to further enhance data informed forecasting quantification and procurement .  Beginnings Fund will leverage this collaboration to further optimise the eLIMS platform, train health workers on interpretation and data use generated by the platform and enable end to end visibility of products in the supply chain from the medical stores to the health facility. Beginnings Fund will also support the operationalisation of the Drugs quality trace and track module to support monitoring quality of MNH products currently under development by DHA and KEMSA. National quantification and forecasting for MNH commodities will be supported in collaboration with other stakeholders.

Sustained financing for MNH commodities.  To ring-fence MNH commodities financing, prevent displacement of existing allocations, and embed sustainability from inception, the Beginnings Fund will operationalise a milestone-based co-financing mechanism through which external support tapers progressively as counties assume increasing responsibility for financing MNH commodities. An initial seed allocation of up to USD 120,000 per county will be provided within the first six months to address immediate MNH commodity gaps identified through the baseline assessment. From Year 2 onward, access to Beginnings Fund commodity financing will be triggered only upon achievement of agreed performance milestones, independently verified by the CoG. These milestones include: (i) allocation of at least 25% of the total annual county budget to health (excluding conditional grants), with progressive increases up to a 30% cap; (ii) execution of at least 85% of exchequer funds allocated to medical commodities in the preceding financial year (70% for counties with baseline execution below 60%); and (iii) proportional year-on-year increases in county budget allocations for medical commodities corresponding to reductions in Beginnings Fund support.  The CoG will serve as the independent verification body, reviewing supporting documents and conducting targeted field verification of commodity delivery and stock management. Verified milestone achievement will trigger disbursements managed by ICRHK as fiduciary agent, subject to Beginnings Fund no-objection. All Beginnings Fund–supported procurement will be consolidated and undertaken through KEMSA or MEDS, with ICRHK making payments directly to suppliers in arrears against verified proof of delivery to designated facilities. No commodity funds will flow through county accounts. Allocation of the USD 7 million commodities envelope across the 21 counties will be guided by the Commission on Revenue Allocation (CRA) formula to ensure transparency, equity, and predictability. Annex D provides a detailed description of the contractual and operational arrangements.

Beginnings Fund will make investments in infrastructure development to support upgrades of newborn units, maternity units and operating theatres as per MoH policies and standards (12 major and 50 minor renovations and 16 health centre upgrades). Renovation and upgrading of MNH units will ensure integration of iKMC in the design and equipping of these units. Leveraging on the experience of NEST360 renovating newborn units, a matching fund model will be adopted with counties and health facilities committing to in-kind contributions/commitments for instance provision of space, allocation of budgets to specific MNH budget lines e.g on equipment.

Workforce:

- Employment of additional health workers, particularly medical officers, nurse-midwives, clinical officers, and biomedical engineers will be done through a structured, milestone-based co-financing mechanism. The objective is to crowd-in additional domestic financing and strengthen county ownership by improving staff-to-patient ratios in maternity and neonatal units within designated health facilities, where workforce gaps continue to undermine quality and timely care. County governments will commit to achieving clearly defined recruitment and deployment milestones within agreed timelines, while progressively increasing domestic budget allocations for the MNH workforce as Beginnings Fund support tapers.  With support from Beginnings Fund implementing partners, counties will establish a baseline staffing profile (by cadre and number) for maternity and newborn units in participating facilities. Based on this, a phased two-tranche staffing plan will be jointly developed and formally endorsed by the County Department of Health, County Public Service Board, and County Treasury. This ensures that recruitment decisions are not ad hoc, but fully embedded within county planning cycles, annual budgets, and medium-term expenditure frameworks, with a clear pathway for eventual fiscal absorption.  The co-financing mechanism will be governed through a Tripartite Partnership Agreement between the County Government, the CoG, and ICRHK. Counties will lead implementation of agreed recruitment and retention milestones. The CoG will provide independent verification of milestone achievement and spearhead advocacy engagements with county leadership, to secure political buy-in. ICRHK will serve as fiduciary agent, responsible for managing and processing disbursements.  Disbursements will be performance-based and made in arrears, following receipt of a CoG verification report and a formal no-objection from the Beginnings Fund. Payments will be triggered by verified recruitment, deployment, and sustained retention of MNH staff in designated units, alongside documented improvements in staffing ratios relative to baseline. Once approved, funds will be transferred by ICRHK to the County Revenue Fund or another lawful county account designated by the County Treasury. From Year 3 onwards, counties will be expected to demonstrate progressively increased domestic financing for the MNH workforce, matching or exceeding predefined reductions in Beginnings Fund contributions. This phased transition approach is designed to ensure predictability, safeguard sustainability, and embed workforce costs within county budgets, while maintaining the improved staffing levels needed to strengthen maternity and neonatal care over the long term.

- Post-basic and postgraduate training.  Scholarships will be supported leveraging the ELMA supported Kenya Paediatric Fellowship Programme (KPFP) and the East, Central and Southern Africa (ECSA) Collegiate clinician training model (where available and applicable) for existing programs for key maternal and newborn health cadres:  MMED anaesthesia, MMED neonatology, MSc neonatology, Master’s in midwifery, BSc Biomedical Engineering (upgrading) will be supported. The strategic selection of trainees for scholarship support from high-burden and under-resourced counties will improve distribution, deployment and retention. Focusing on departments that produce cadres critical to MNH services, competency-based training will be strengthened by enhancing tutor capacity through short-course training in the latest guidelines and evidence. To increase the annual production of neonatal nurses, Beginnings Fund will support one training institution to start higher diploma/MSc in neonatal nursing.

- Workforce Planning will be strengthened through the further development and operationalisation of the national Integrated Human Resource for Information System (iHRIS) to enhance workforce planning, deployment, monitoring, and decision-making, ensuring data-driven management of the health workforce.

- Continuous in-services training using innovative approaches such as simulation-based training that provides realistic, hands-on practice for emergencies in a safe environment, while also supporting realistic planning and awareness of commodity stock status, nurse-to-patient ratios, and the functionality of equipment and infrastructure.

To improve availability of quality blood and blood products proposed support will include catalytic procurement of reagents for a period of 12 months and strengthening the referral and logistics for blood and blood products within the hospital care networks through integration with the emergency dispatch centre (see referrals section). This catalytic support will allow time to establish necessary frameworks for institutionalisation of more sustainable financing mechanisms currently in discussion which include: i) a percentage contribution from the emergency, Chronic and Critical Illness Fund  to blood transfusion services, ii) net-off a specific amount to cover blood and blood products from caesarean section fees that is directly remitted to KBTTS, and iii) upgrade KBTTS to semi-autonomous government agency with ring fenced direct funding from treasury. The Kenya Red Cross Society will provide targeted technical assistance to KBTTS to strengthen institutional, operational, and financing systems necessary to operationalise and sustain these reforms.

Data: Baseline health facility assessments will be conducted to inform the scope of planned interventions.  The maternal and newborn inpatient dataset and key indicators to better measure quality of care will be integrated in Taifa care (national EMR).  As part of a 10-year public-private-partnership aimed at developing an Integrated Healthcare Information Technology System, DHA has sufficient funding for ICT infrastructure to digitize all public health facilities (levels 2, 3, 4, and 5) including local area networking, internet costs, and roll-out TaifaCare (the national Electronic Medical record) for the next 10 years. Beginnings Fund will provide complementary investments to support with ICT infrastructure and internet connectivity to the Faith Based Organisations and satellite connectivity for public health facilities in remote areas without cellular connectivity. Beginnings Fund will leverage this DHA investment in focus facilities to enable MNH modules integrated Taifa Care to be utilised.  Data integration protocols will be developed between the EMRs and other related digital solutions used in patient referral workflows, including the Social Health Authority (SHA) - social health insurance fund, ensuring secure data exchange that maintains patient privacy and data integrity.  Taifa Care will be configured to automatically generate and transmit standardised indicator data into the national HMIS for aggregate reporting. This integration will significantly reduce the reporting burden and improve data consistency between systems. The national health dashboard will be strengthened to include MNH indicators tracking coverage of key interventions, workforce, commodities, and emergency transport and referral investments. The electronic logistics management system (eLMIS) for tracking commodities will be optimised for MNH commodities and integrated into a centralised dashboard platform leveraging on ongoing work by Field Technologies. Real-time digitisation of MPDSR will be strengthened to enable a more rapid response, including the better capture of perinatal deaths and stillbirths.

Leadership and Management:  To enhance leadership and management for national technical leaders, and key members of CoG and County Health Management Teams (CHMTs), and health facility leaders, short course and customized training will be supported through the Strathmore Business School. This will aim at strengthening MNH health financing and procurement capacity strengthening to enable budgeting and tracking of MNH expenditure, to enable analysis of financing gaps and improved resource mobilization through unlocking of domestic budget sources. The key national technical working groups will also receive complimentary secretariat support where gaps exist, specifically for RMNCAH, Health Products and Technologies, Newborn and Child Health, and M&E to enhance strategic coordination for a more synergistic MNH program implementation. Catalytic budget to support mapping of MNH stakeholders and investments, strategic policy and fiscal advocacy to influence mobilisation of domestic funding for MNH and increase budget allocation for MNH and health workforce by the exchequer will be provided.

Program Consortium:

- The Government of Kenya via Ministry of Health Department of Health Workforce for MNH workforce planning and Department of Family Health and CoG overall joint coordination

- Target counties via the Council of Governors (COG). The CoG will provide overall joint coordination across counties, facilitating a joint framework agreement for implementing Beginnings Fund activities. They will facilitate implementation of the milestone-based grants on workforce recruitment (and subsequent absorption) and routine procurement of medical commodities and supplies (BF funds used to gap fill). CoG will monitor the implementation of inter-county agreements on Beginnings Fund and the scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality through review of annual workplans to inform their integration into county systems.

- Kenya Medical Supplies Agency and Mission for Essential Drugs and Supplies for the procurement of essential MNH commodities, last mile delivery, and strengthening the supply chain of the same commodities.

- Kenya National Blood Transfusion Services – availability of quality blood and blood products through catalytic procurement of reagents and consumables for screening blood

- Digital Health Agency is the dedicated government agency charged to deliver essential digital health services that support the entire healthcare ecosystem in Kenya through comprehensive integrated health information systems. They will lead alongside the programme M &E partner (ICHRK) in the development and integration of the maternal-newborn dataset into Taifa care (national EMR), develop county and national level dashboards, support data for QI, integration of eLIMS

- Aga Khan University which implements the NEST program in Kenya will lead with installation of newborn equipment and scale-up of evidence based SSNC interventions through training and mentorship for health workers and biomedical technicians, use of data for QI in newborn care in 15 intensive counties and provide technical assistance on newborn care to the maternal partners implementing in the 6 equity counties

- Jacaranda Health- lead with installation of equipment and scale-up of evidence based for maternal (ANC, intrapartum, labour, delivery and immediate post-partum) interventions through training and mentorship for health workers and biomeds, use of data for QI in nine intensive counties while prioritizing counties they already are implementing programmes in.

- Lwala Community Health Alliance- lead with installation of equipment and scale-up of evidence based for maternal (ANC, intrapartum, labour, delivery and immediate post-partum) interventions through training and mentorship for health workers and biomeds, use of data for QI in five intensive counties while prioritizing counties they already are implementing programmes in.

- Kenya Red Cross Society (KRCS) - lead with installation of equipment and scale-up of evidence based of maternal (ANC, intrapartum, labour, delivery and immediate post-partum) and newborn interventions through training and mentorship for health workers and biomeds, use of data for QI in the seven counties (six equity counties and 1 intensive county) in Arid and Semi-Arid areas where they have strong presence and expertise working in these counties. At the national level, they will support strategic leadership engagement, advocacy and policy alignment, and the procurement of blood reagents and blood logistics in seven counties. KRCSoperates under a formal, long-standing auxiliary framework with the MoH and the Government of Kenya, established by an Act of Parliament (Cap 256) in 1965. This partnership positions KRCS as a key partner in implementing national health strategies, particularly in emergency response, community health, and Universal Health Coverage (UHC) recently updated 2025.

- InSupply – will strengthen MNH commodity security by supporting data-driven forecasting and quantification, establishing multidisciplinary county planning teams (procurement, finance, pharmacy, and RMNCH leads), and building frontline capacity in supply chain and procurement management. This will improve budget execution beyond 85% and support progressive domestic financing as Beginnings Fund support tapers over five years.

- CHAI Kenya - coordinating partner for the Kenya Paediatric Fellowship Programme consortium members comprised of Moi university, Nairobi University, Aga Khan University, Kenyatta National Hospital Nurse training school, medical training colleges, Professional associations, and Strathmore Business School to support health workforce training scholarships, professional associations coordination for advocacy. CHAI Kenya will also collaborate with the CoG to institutionalise inter-county MPDSR coordination, facilitating structured peer learning, cross-county exchange, and collective action to strengthen implementation of the response component of MPDSR.

- International Centre for Reproductive Health Kenya - overall programme coordination including monitoring and evaluation, and implementation learning across partners, strengthen leadership and governance through advocacy support with the strong use of data analytics and health financing performance management data for strategic advocacy to influence domestic resource mobilization, increased efficiency and improved coordination of partners. They will also serve as the fiscal agent for the milestone-based grants on HRH and medical commodities.

- Referral systems – (Partner TBD) The Ministry of Health, through the Digital Health Authority, is developing a digitally enabled emergency referral system (expected in Q2 2026). The Ministry will establish a centralized dispatch centre to host and operate this system. The platform is designed to maintain real time data on available responders, including ambulances and aircraft. Dispatchers will triage incoming calls by assessing the urgency and care needs of each incident, identifying the closest and best equipped response team, estimating arrival times using real time mapping and traffic data, and coordinating the responder’s route to the scene. Ambulance service providers will be empaneled by the Social Health Authority (SHA) and reimbursed in accordance with SHA rates. Beginnings Fund will leverage this national referral systems and support counties optimize their MNH referral model.

- Hatch – will support procurement installation and maintenance of maternal and newborn medical equipment

- Infrastructure partner (TBD) working together with MASS design will support the renovation of maternal, newborn and operating theatres.

Operational Plan

The following objectives and activities will be supported directly through Beginnings Fund investments in the Government of Kenya and key implementing agencies (see investment memos for detailed plans). Outlined below against each objective, are a) government policy alignment, b) the amount of Beginnings Fund investment, c) government co-investment and commitments, and e) complementary investments that will advance planned support.

Objective 1: Scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality

Policy Alignment: National Reproductive Health Policy 2022-2032, Kenya Health Sector Strategic and Investment Plan 2023-2027, Kenya RMNCAH Investment Framework 2025-2030, National Guidelines on Quality Obstetrics and Perinatal Care 2024 Beginnings Fund Investment: USD 15.9million Government Commitment: USD 23.1 million (GOK and bilateral funds channelled through Treasury) Government Lead: MOH- Director of Family Health, Council of Governors Technical Support Partners: Jacaranda Health, Lwala Community Alliance, Kenya Red Cross Society and NEST 360 Technical Support Partner Co-Investment: USD 2million (UNFA)/ USD5million (UNICEF) Complementary Investments:

Beginnings Fund will provide support for the following activities in 200 high-volume facilities in 21 counties:

Antenatal Care:

  - Procure complementary point-of-care antenatal care diagnostics, including reagents and facilitate uptake for early identification and management of infections, anaemia, hypertension, diabetes.

  - Scale up of point-of-care ultrasound (POCUS) to improve gestational age dating, identify high-risk pregnancies and improve risk-differentiated care through regulatory approval and mentorship

  - Strengthen the uptake of antenatal corticosteroids for premature labour

Labour and Delivery:

  - Introduce digital intrapartum and foetal monitoring technologies at all target facilities (CTG at high-volume sub-county and county referral hospitals)

- Roll out the PPH bundle to prevent and treat post-partum haemorrhage through training of trainers and on-site mentorship

- Improve safe obstetric surgical and anaesthesia skills through training on Safe Surgery and quality improvement approaches utilising the safe surgical checklist and team-based methods, in all CeMONC with a focus on creating centres of excellence at county referral hospitals and hospitals serving as internship centres that are hubs for learning, upskilling and dissemination.

Newborn Care:

- Establish newborn corners in all labour and delivery rooms and operating theatres to improve essential newborn care, iKMC, neonatal resuscitation and stabilization

- Expand Level 2 newborn care in county referral and sub-county hospitals and high-volume CEmONC health centers, train clinical and biomedical staff, improve data management and use through QI cycles.

Cross cutting implementation approach to scale-up priority MNH interventions:

  - Through a training of trainers model, provide orientation on the delivery of ANC, intrapartum, and SSNC bundles to hospitals which will cascade training and provide supportive supervision to sub-county and health centres in their referral network.

  - Provide simulation-based mentorship and equip sites to increase performance of signal functions and reduce prolonged labour and poor outcomes

  - Provide practical skills training on optimized/integrated EmONC (including delivery of the PPH bundle, safe cesarean section techniques, and care and use of technologies for small and sick newborns) and establish peer-to-peer hospital-based mentorship of new nurses, midwives and general practitioners by experienced staff and facility champions.

  - Deploy county-based mentors to monitor progress on implementation of interventions to improve healthy pregnancy, intrapartum care, and SSNC.

- Train 40 national trainers in the harmonized package for continuum of care in MNH, EmONC, Essential Newborn Care and Comprehensive Newborn Care and develop a national database for data-informed mentorship

- Train 20 county mentors in each priority intensive county to provide onsite hub and spokes clinical mentoring, quality improvement and data use, and simulation-based low dose high frequency training, identifying and supporting maternity and neonatal ward champions

- Train 10 facility champions per hospital, 6 per health center and 2 per dispensary

- Support mentors and champions with data driven insights on clinical and training gaps, through usage of MNH data from dashboard and simulation training data

- Mentor staff at focus facilities within six weeks of facility champion training, quarterly in Years 1 to 3, and biannually in Year 4-5 based on performance

- Provide technical implementation support and data analysis and reviews at facility, sub-county, county and national level, to monitor facility progress until coverage indicators improve and simulation-based training and drills and QI cycles are institutionalized

At national level, Beginnings Fund will provide support for the following activities:

- Working closely with CHAI through the Beginnings Fund regional market shaping grant, support scale up of PPH bundle, caffeine citrate, lung surfactant, IV Iron (Ferric carboxymaltose (FCM)) and Multiple Micro-nutrient Supplements at the national level through catalytic procurement of products, training of trainers, development of service delivery guidelines, and ongoing quality improvement.

- Complement efforts by WHO, UNICEF, UNFPA, CHAI, and relevant professional associations to develop an optimized/integrated EmONC curriculum that integrates safe cesarean section techniques, PPH bundle, and use and care of technologies for SSNC, to be incorporated into national pre-service and in-service curricula.

- Support roll-out of the intercounty MPDSR through facilitating joint meetings and peer to peer learning across counties

- Update national guidelines to include new evidence (antenatal care, MPDSR, EmONC Job Aids, POCUS, in collaboration with experts from professional associations and universities.

Objective 2: Increase the availability and use of quality priority MNH commodities

Policy Alignment: National Reproductive Health Policy 2022-2032, Kenya Health Sector Strategic and Investment Plan 2023-2027, Kenya RMNCAH Investment Framework 2025-2030, National Guidelines on Quality Obstetrics and Perinatal Care 2024 Beginnings Fund Investment: USD25.1million Government Commitment: USD 20.6million (GOK and bilateral funds channelled through Treasury) Government Lead: County Department of Health, COG and KEMSA Technical Support Partner: HATCH Technologies, Insupply, International Centre for Reproductive Health Kenya Technical Support Partner Co-Investment: USD600,000 (UNFPA) Complementary Investments: Gates Foundation POCUS, CIFF MMS procurement, MBZ Foundation USD12.0 million for procurement of drugs, equipment and consumables

Beginnings Fund will provide support for the following activities in 200 high-burden facilities in 21 focus counties:

- Equip 200 facilities with POCUS, digital intrapartum monitoring, EMONC, and SSNC equipment and consumables and simulation training equipment (See Annex C)

- Increase uptime of MNH equipment >80% by equipping biomedical engineers with tools and functional workshops to support planned preventive maintenance and repair of MNH equipment

- Strengthen capacity of 21 county teams (finance, procurement, county pharmacist, and RH coordinator) by training on budget cycle, forecasting and quantification and stock management

- Strengthen forecasting and quantification through data informed analytics in eLMIS

At national level:

- Leveraging the CHAI regional grant conduct catalytic procurement of new and priority MNH products (caffeine citrate, POCUS, heat-stable carbetocin, detection drapes, CTG, IMPALA patient monitors) and packaged treatment bundles

- Develop and institutionalize a standardized list of priority MNH medical devices/diagnostics/consumables to reduce fragmentation and improve procurement efficiency

- Work closely with KEMSA/MEDS, DHA, and Field Technologies to improve digital tracking systems to monitor MNH product shipment, distribution, and inventory management.

- Strengthen quantification and forecasting systems by improving data accuracy

- Improve national forecasting and quantification for MNH commodities by ensuring 100% inclusion in national quantification and demand forecasting efforts as well as supply and distribution plans.

- Recommend MNH priority products for inclusion in SHA minimum benefits package across all levels of health facilities

- Ensure 100% priority MNH product financing is tracked through CoG

- Mobilize higher levels of external financing for MNH commodities, including accessing matching opportunities (e.g. Through national treasury, STBF and WB/GFF)

- Increase domestic budgetary resources for MNH commodities for sustainable financing

Objective 3: Strengthen and expand the quality, number, and distribution of the MNH workforce

Policy Alignment: Kenya Health Sector Human Resources Strategy 2019 - 2023, Human resources for health Norms and Standards guidelines for the health sector 2014 Beginnings Fund Investment: USD 12.7million Government Commitment: approx. USD 7million for recruitment and deployment of priority MNH staff through the milestones-based co-financing agreement with participating counties. In addition, the Government of Kenya in collaboration with counties commits to: - Select trainees for scholarship support on agreed criteria, continue salaries, and bond for period of training - Appropriately deploy MNH graduates to maternity and neonatal units in public and faith-based facilities in focus counties - Employ additional health workers supported by Beginnings Fund on agreed timelines - Maintain increased staff: patient ratios in targeted maternity/neonatal units in the target health facilities. Government Lead: KHHRAC and COG (for workforce planning), University of Nairobi, Moi University, KMTC and KNH (for scholarship/fellowship programme). Technical Support Partner: Clinton Health Access Initiative (CHAI) Technical Support Partner Co-Investment: Complementary Investments: KPFP through ELMA, Gates Foundation (POCUS training)

Beginnings Fund will provide support for the following activities in target counties:

- Improve staff: patient ratios in targeted maternity and newborn units through a 50:50 matched funding (milestone-based grant) to counties through COG to recruit ~400 additional health workers (nurse-midwives, clinical officers, doctors, biomedical engineers) and absorb on agreed timelines, particularly focusing on expanded Level 2 neonatal care units and labour wards as a priority.

- Provide scholarship and development support to train 270 MNH workers strategically selecting recipients from focus and other-under-resourced counties

  - Provide scholarship support to upgrade 270 health workers through

    - 20 MMED anaesthesia, (through CANESCA)

    - 20 MMED paediatrics – neonatology (through ECSAPACH)

    - 50 MSc neonatology nursing

    - 50 MSc in midwifery,

    - 30 BSc Biomedical Engineering (upgrading)

    - 60 diploma neonatal nurses

    - 40 Clinical Officer or nurse Anaesthetists

- Support mentors and champions with data driven insights on clinical and training gaps, through usage of MNH data from dashboard and simulation training data

- In target counties and facilities >80% of staff are trained (~3000 health workers) on the newborn package of interventions (the comprehensive newborn protocol for Level 2 neonatal care units) and maternal package of interventions (enhance EmONC training and safe surgery), and engage county and hospital leadership to recognize their competencies and reduce rotation

At national level, Beginnings Fund will provide support for the following activities:

- Support the establishment of one additional training program for neonatal nurses in Moi University to increase production capacity from 50 to 100 neonatal nurses per year through support for faculty training, and equip for teaching and learning

- Support MOH in partnership with training institutions and teaching hospitals to upskill teaching faculty (in nursing, clinical officer, bio-medical engineering and medical schools) on new guidelines and technologies and sub-sequent introduction into respective curriculums

- Through the Kenya Health Human Resource Advisory Council, conduct workforce planning with the MOH, and COG to improve distribution and skill-mix of key MNH cadres nationally, through further development of the Human Resource for Health Information System (HRHIS) to enhance deployment, monitoring, and decision-making, ensuring data-driven management of the health workforce, including integration with training pipeline, to improve supply and demand.

  - Collaborate with national treasury, county public service commission boards, and county finance departments on HRH budgeting and budget allocations

Objective 4: Strengthen other critical health system enablers, including MNH infrastructure, data systems, blood and blood products, emergency transport and referral systems, and advocacy for greater impact.

Policy Alignment: Kenya National E-Health Policy 2016-2030, Kenya Emergency Medical Care Policy 2020-2030, Kenya National Standards for Blood Transfusion Services 2022, Beginnings Fund Investment: USD21.1million Government Commitment: USD 275 million (Infrastructure, Taifacare, Referral system and blood) (GOK and bilateral funds channelled through Treasury) Government Lead: Ministry of Health, Digital Health Agency, Technical Support Partner: Kenya Red Cross Society, International Centre for Reproductive Health Kenya, Infrastructure Partner (TBD), Referral partner (TBD) Technical Support Partner Co-Investment: Complementary Investments: Gates Foundation: DPI Project USD 4 million; USD4.5 for MNH strategic advocacy; MBZ Foundation USD156,000 for renovation of NICU and regional blood centre

- Improve maternal and neonatal infrastructure:

- Renovate and construct level 2 neonatal care units, maternity units and theatres in target counties in line with MOH guidelines for zero separation while addressing address key gaps in service delivery –Renovations - 12 major; 50 minor and 16 health centre upgrades.

- Renovate/construct level 3 neonatal care units (NICU) in three county referral hospitals to expand from the current three to six while ensuring regional and burden needs are addressed

- Support the integration of maternal and neonatal inpatient data (M-NID) into national health information systems, enhance MNH data availability and use through integration with EMRs

  - Provide technical support to the MOH and Health Information Systems departments and the Digital Health Agency to support integration of MNID into Taifa care (national EMR), data analytics, and dashboard development

  - Convene key workshops to support design and user testing of the MNID data system and MNH dashboards

  - Support the roll-out of MNH Modules in Taifa care in 200 target facilities by procuring complementary ICT devices and local area networking equipment (for faith-based organisations) to ensure sufficient coverage of all MNH service delivery areas with Taifa care

  - Develop and manage integrated dashboards for quality improvement to enable program monitoring across all program interventions for use at facility, sub-county, county, and national level

    - Leverage the Taifa care system integration with eLMIS to support improved quantification and forecasting of MNH commodities, with iHRIS to support improved workforce deployment for MNH

- Recruit for DHA two software developers and one data scientist to support with M-NID programming, development of dashboards, and data analytics

- Enhance emergency transport and referral system

  - Support enhanced neonatal referral and stabilization protocols nationally including training for EMTs (paramedics)

  - Equip facilities for enhanced stabilization of neonates during transfer to reduce morbidity and mortality (e.g. portable CPAP, oxygen)

  - Leverage national referral systems established and supported by the Emergency and Chronic illness Fund and SHA for MNH referral

- Strengthen MOH and County leadership and management capacity at all levels to sustain improvement

- Provide technical support in 21 counties to ensure Comprehensive County Health Plans include MNH priorities and budgeting for commodities, including consumables, workforce (including absorption of additional health workers), and infrastructure development.

- Support the MOH department of RMNCAH and COG with MNH health financing capacity strengthening to enable budgeting and tracking of MNH expenditure, to enable analysis of financing gaps and improved resource mobilization

- At national level, support program implementation capacity in MOH, COG, Counties (CHMT), including additional support for the program management team including resources for supportive supervision, and an overall program coordinator, M&E analyst and accountant to support program coordination, enable efficient use of resources, and analyze progress.

- Strengthen the availability of blood and blood products though

- Catalytic procurement for blood reagents and blood bags and other consumables for the first 12 months of the investment

- Support blood collection activities in seven of the 15 intensive counties

- Support logistics for blood and blood products distribution to network of health facilities linked to regional transfusion centres particularly in the arid and semi-arid areas with long travel distances between regional centres and health facilities by leveraging the referral system network

Country Budget and Sources

*Approximately 20% of the budget will be through government as milestone-based grants

Monitoring, Evaluation and Learning (MEL)- under development

The Beginnings Fund will play a catalytic role in strengthening Kenya’s health data systems through targeted technical and operational support to the Digital Health Agency (DHA) whose mandate is to develop, operationalize and maintain the Comprehensive Integrated Health Information System to manage the core digital systems and the infrastructure required for its seamless health information exchange. The Government of Kenya is developing and implementing a national Electronic Medical Record, TaifaCare, with deployment already undertaken in 33 out of the 47 counties. The Beginnings Fund M&E team and ICRHK will work closely with the DHA and Division of Reproductive Maternal Newborn and Adolescent Health to integrate the Maternal-Newborn Inpatient Data Set (M-NIDS) within the TaifaCare to enhance the real-time collection, integration, and analysis of MNH data within government systems.

To strengthen data accuracy and utilization for quality improvement and planning, the Beginnings Fund Multi-country evaluation partner (KEMRI/HROK) will support ICRHK in collaboration with DHA and other stakeholders to co-design a national MNH dashboard, which will be interoperable with routine and programmatic data, including HRMIS and eLIMS (supported by Field Technologies). At the county level and health facilities, ICRHK will build staff capacities to access dashboards aggregating and visualizing this data for timely informed decision-making in improving the quality of care. These dashboards will visualize key MNH indicators, including process metrics such as timely use of uterotonics, management of maternal complications, and neonatal resuscitation practices, enabling health workers and managers to act on emerging trends. The dashboards will also be used during monthly performance review meetings at county level and during national joint monitoring and evaluation reviews. Program teams will use these insights to track coverage and quality of care, identify underperforming health facilities, and inform targeted support.  For health workforce monitoring, ICRHK and DHA will work to strengthen the operationalization and utilization of the Integrated Human Resources Information System (iHRIS) through the Kenya Health Human Resource Advisory Council (KHHRAC).  Across focus counties, ICRHK will ensure that iHRIS data is regularly captured and updated, while strengthening the capacity of the national MOH and county governments to visualize and utilize data from the iHRIS and MNH dashboards for evidence-based decision making and policy development. DHA in collaboration with KEMSA and Field Technologies will also explore the integration of the electronic Logistics Management Information Systems (eLIMS) and iHRIS into the DHIS2 MNH to enhance decision making but also for programmatic tracking of BF workforce, medical products and supplies investments.

Beginnings Fund will provide support for specialized technical staff and equipment to support MNH service delivery system optimization and data use. Two data scientists and a statistician (with expertise in MEL) will be embedded within DHA to improve data quality, oversee real-time analytics, and develop dashboards that allow stakeholders to identify gaps and monitor progress across targeted health facilities as part of the quality improvement and supportive supervision and mentorship activities. These roles will also facilitate the integration of data quality feedback loops between health facilities and the national level, enabling early detection and resolution of data discrepancies. Importantly, both positions will be gradually absorbed into the government structure, ensuring long-term sustainability of capacity gains

To track further programmatic indicators, all implementing partners will be responsible for submitting annual program reports, which will be compiled by ICHRK, integrated within these dashboards, and tracked against the program’s Pathway to Impact. Progress against key program milestones will be monitored and reviewed by the MOH and implementing partners through regular meetings with the Program Implementation Committees – as well as established committees on infrastructure, human resources for health, and other thematic areas – supporting the identification of early signs of success and ensuring that strategies are adapted to evolving needs. Outcome indicators will be collected and reviewed on a quarterly basis using DHIS2, iHRIS, and other existing data platforms, with mentorship and capacity building provided to strengthen the data quality for both new and current MNH indicators.

The Beginnings Fund consortium will leverage MOH and COG structures to share results, exchange insights, and channel findings to scale MNH improvements nationally through HSSP V and Technical Working Groups. Annual learning exchanges between focus counties will be conducted to promote the hands-on sharing of program innovations and the fostering of communities of practice. To ensure that improved MNH data translates into joint accountability across the health sector, the MOH Technical team will ensure that key indicators for MNH are incorporated into the MOH unified M&E framework. This will ensure that MNH indicators are tracked, and lessons are shared during health sector reviews at the facility, district, zonal and national levels, creating a strong foundation for continuous improvement and scale up.

Risk and Reward

| Risks (Significance/Likelihood) | Mitigating Strategies |
| --- | --- |
| National and County Government incongruence (High/Moderate) The national government is responsible for policy & strategy development, quality and regulation and M&E. The county governments are responsible for service delivery, management of human resources for health, supply chain and primary health care. The two levels have had challenges in coordinating policy and implementation and accountability for health outcomes | The steering and technical program committees include all the key national and county health management teams and stakeholders. Beginnings Fund will Support a collaboration and coordination platform that includes the national and county health teams which meets regularly for project updates and for the larger MNH convenings. This ensures the two levels of Government are fully involved in the respective roles ine implementation of MNH as well as transparency and open channels of communication |
| Instability during policy transition the national health insurance scheme resulting in reversal of gains in some of the MNH indicators Kenya passed the Social Health Insurance Act (SHIA) 2023, which repealed the NHIF law and established the Social Health Authority (SHA) — a new agency to manage health insurance (Social Health Insuarance Fund (SHIF)) and universal coverage. SHIF transition officially took effect on 1 October 2024. However, challenges have been flagged on drastic transition, issues around system readiness and digital infrastructure, exclusions or verification problems for certain groups, level 2 and 3 health facilities were not being re-imbursed for certain services such skilled birth delivery undermining access to services In the first year of SHA MNH access indicators have fallen significantly. Antenatal care visits and skilled birth attendance have reduced significantly which risks the reach of the intervention and may undermine the impact of the Beginnings Fund interventions | High level advocacy using data to make the case for removal of financial barriers for pregnant women accessing antenatal, postnatal and child birth services at health facilities across all levels of care |
| Disrupted supply chains (High/High) Essential maternal and newborn health commodities (e.g., oxytocin, heat stable carbetocin, caffeine citrate, CPAP machines) may face delays or shortages due to national supply chain disruptions inconsistent financing for MNH commodities at the county hospitals and high costs compounded by fragmented quantification and procurement | Leverage the CHAI market shaping grant to ensure availability of essential MNH commodities. CHAI will continue collaborating with the MoH, COG, and KEMSA to proactively identify potential supply chain bottlenecks using real-time data and jointly strengthen forecasting, inventory tracking, and procurement coordination in the project counties and at national level |
| Health workforce shortages and turnover (High/High) Health workforce has been a persistent challenge in Kenya. The numbers, skills and high turnover have undermined the delivery of quality MNH services. Further, the counties may not absorb 50% of the health workers that will be recruited by the Beginnings Fund as part of the milestone-based grant. | Bonding of Healthcare workers for two years after their specialty training. Work with county health management team to select and retain healthcare workers in the maternity, MCH and NBUs after the skills-based trainings on Continuum of Care, EmONC and CNC. Regular reviews on the nurse: patient ratios and doctor:patient ratios in MCH, maternity and newborn units and development of action plans to optimize the health worker:patient ratios for improved health outcomes. Support health worker forecasting to ensure timely replacement for health workers departing the system through natural attrition |
| Election campaigns in the run up to the 2027 elections and possible transitions in county leadership This might disrupt operations at the county level indirectly impacting MNH service delivery. There is a risk that commitments made to Beginnings Fund may not be honored by subsequent governments. | Coordination and engagement of counties will be through the Council of Governors which is non-partisan and serves as the coordinating agency across the 47 counties. Onboarding of counties will be through an intergovernmental Agreement co-signed by the Governor and technical officers from County treasury, Public Service Board, and legal the latter three do not change with elections and hence provide continuity. Further, the CoG secretariat does not change with elections and serves to support transition across elected and appointed leaders in counties including through induction of the new teams. |
| County and national contributions as agreed may not come to fruition (High/High This might lead to sub-optimal achievements in investment areas where Beginnings Fund is greatly leveraging these investments for instance 1:1 matching for workforce and data systems through DHA | Beginnings Fund will include an additional investment to track public finance investments aligned with our strategic investments and execute strategic engagements for course correction on a routine basis particularly through review of county and national level budgets and tracking government commitments to ensure that Beginnings Fund commitments are not crowded out |

Transition and Sustainability Plan

This investment is deliberately designed as a catalytic, time-bound intervention that will accelerate progress in maternal and newborn health while laying out the foundations for sustained government ownership beyond the life of the Beginnings Fund support. The approach to sustainability is through a planned transition over the five-year implementation period, rather than a handover at the end of the grant. From inception, implementation will be embedded within routine national and county systems for service delivery, planning, budgeting, and accountability. Over time, operational leadership, financing responsibility, and stewardship will progressively shift to government institutions, with Beginnings Fund support tapering from direct implementation to targeted technical assistance. This phased approach will ensure that gains achieved under the investment are institutionalised, financed, and scaled through Kenya’s devolved health system.

Our specific approaches to sustaining various components of this investment are as follows:

Quality of care: This investment will support the embedding of quality improvement, mentorship, and skills development within routine county and facility systems, aligned with national guidelines and standards. Mentorship and Continuous Quality Improvement (CQI) will be institutionalised through facility-based mentors drawn from the county health workforce and deployed within their own facilities. County and sub-county quality focal persons will be supported to integrate data review, mentorship follow-up, CQI cycles, and action planning into routine supportive supervision and management meetings. Facility Quality Improvement Teams (QITs/WITs), simulation-based drills, and multidisciplinary team learning will be embedded into everyday clinical practice rather than treated as project activities. A phased mentorship model will be implemented, with more intensive external facilitation during the first two years, followed by a progressive transition to county-led mentorship and CQI. Beginnings Fund will support the strengthening of MPDSR processes to ensure that maternal and perinatal death reviews generate costed, time-bound action plans that are formally adopted by counties and tracked through routine performance review systems. Skills sustainability will be reinforced through Training-of-Trainers approaches, peer learning, and the integration of competencies into continuous professional development and performance management frameworks.

MNH workforce:  Beginnings Fund will support a workforce sustainability approach that is fully aligned with county public service structures, national human resources for health policies, and Kenya’s devolved governance arrangements. Recruitment of MNH health workers under this investment will be undertaken in close partnership with county governments and will proceed only where counties formally commit to absorbing and retaining staff within their payrolls. All recruitment and remuneration will be aligned with county terms of engagement, ensuring consistency with county public service regulations and reducing the risk of attrition once external support tapers. A matching and milestone-based grant model will be applied to crowd in county investment in human resources for health. Counties will be required to recruit and deploy at least 50 percent of priority MNH cadres identified through joint workforce gap analyses, using exchequer funds within the first year of implementation. Beginnings Fund support will be used to catalyse, not substitute, county investment, with funded positions progressively absorbed into county payrolls over the life of the investment. Workforce planning, equitable deployment, and skills mix optimisation will be strengthened through collaboration with KHHRAC and improved use of workforce data systems. Deployment will prioritise maternity, newborn, and high-volume referral facilities, where staffing gaps most directly affect quality of care and outcomes. Skills sustainability will be reinforced through Training-of-Trainers models, facility-based mentorship, and integration of MNH competencies into continuous professional development and national accreditation frameworks.

Essential MNH commodities and equipment: The investment will support the embedding of forecasting, quantification, procurement, and distribution within existing supply chain mechanisms, including KEMSA and county procurement systems, thereby avoiding parallel arrangements. Commodity procurement will prioritise KEMSA, to continue its growth and capitalization. A grant mechanism will be used to crowd in county co-investment, prevent displacement of existing county budgets for medical commodities, and progressively reduce reliance on Beginnings Fund financing. Counties will be required to demonstrate increasing proportional allocations to MNH commodities as external support declines, reinforcing domestic financing responsibility. Facility Improvement Financing (FIF) will be leveraged to support routine replenishment and last-mile availability at facility level. Medical equipment investments will follow standardised Ministry of Health specifications and will be coordinated through the national Ministry of Health and County Departments of Health to ensure coherence with other government and partner-supported initiatives. Beginnings Fund will support training and equipping of county biomedical engineers to conduct planned preventive maintenance and repairs, ensuring high equipment uptime. All equipment will be handed over as government-owned assets, maintained through county systems, with supplier contracts embedding installation, training, maintenance support and requisite warranties.

Digital and data systems: All digital and data investments will be fully embedded within government-owned platforms, including KHIS/DHIS-2, TaifaCare (the national EMR), iHRIS, and eLMIS. No parallel reporting systems or standalone databases will be introduced. The digital health systems infrastructure within DHA, is part of wider public-private consortium with funding secured for the next 10 years including system maintenance. The Digital Health Authority (DHA) will retain long-term stewardship, with Beginnings Fund support focused on strengthening system functionality, analytics, dashboards, and user capacity. DHA and county teams will be supported and capacitated not only as system users but as system champions, reducing long-term reliance on external technical assistance. MNH dashboards and routine data review processes will be institutionalised within supervision, CQI, MPDSR, and performance review cycles at facility, county, and national levels. Recurrent digital system costs will be progressively absorbed through user fees financing mechanisms levied by DHA, ensuring sustainability beyond the grant.

Infrastructure improvements: Infrastructure investments in maternity and newborn care units will be aligned with national norms, standards, and design guidelines. Drawing learning from NEST360, sustainability will be reinforced through co-financing arrangements with county governments, promoting ownership from inception. Beginnings Fund will support counties to integrate infrastructure improvements into planning and budgeting processes and to leverage Facility Improvement Funds for ongoing operation, maintenance, and refurbishment.

Sustainable financing: Financial sustainability will be driven through deliberate integration of MNH priorities into Kenya’s evolving public health financing architecture, including the Social Health Insurance Fund (SHIF), the Primary Health Care Fund, and Facility Improvement Financing. Maternal and newborn services are already included in the SHA benefits package; this investment will support evidence-based advocacy to strengthen the package (especially the scope, tariffs, and access rules) to better protect mothers and newborns from out-of-pocket costs. Improved submission and utilisation of SHA reimbursements will be strengthened to enhance facility-level financing for essential services. Beginnings Fund will support counties to translate MNH priorities and MPDSR recommendations into costed plans incorporated into County Integrated Development Plans (CIDPs), Annual Work Plans and budgets, and medium-term expenditure frameworks. Over the life of the investment, counties will progressively assume responsibility for recurrent costs that are supported by this investment. Evidence generated through implementation will be systematically synthesised to inform budget advocacy, policy dialogue, and domestic resource mobilisation at national and county levels. Inter-county peer learning forums facilitated through the CoG will support benchmarking, accountability, and replication of effective practices.

Leadership and coordinated stewardship: Sustainability will be anchored in strong government leadership and ownership at both national and county levels from the outset. All coordination, governance, and accountability mechanisms supported under this investment will be embedded within existing MoH and county structures rather than established as parallel systems. National Technical Working Groups, MPDSR forums, and inter-county learning platforms will operate under MoH leadership, with counties engaged through CHMTs. Implementing partners will initially co-convene and co-facilitate with government counterparts, with convening authority, agenda-setting, and follow-up responsibilities fully transitioning to the MoH and counties by Year 4. The CoG will play a central role in inter-county coordination, leveraging its Health Committee, CECM and Chief Officer Caucuses, and County Health Directors Forum to support harmonisation, peer learning, and scale. Formal partnership agreements and MOUs with government entities will clarify roles, responsibilities, and co-investment commitments, reinforcing accountability and continuity beyond the investment period.

Annex A: Pathway to Impact

By 2030:

- reducing maternal mortality by 18% from 530 to 432 per 100,000 live births

- reducing stillbirths by 14% from 19 to 16 per 1,000 live births

- reducing neonatal mortality by 36% from 18 to 12 per 1,000 live births

| Obj. 1: Priority interventions scaled to address drivers of maternal and neonatal mortality and stillbirths |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 200 facilities in 21 counties: Bungoma, Kakamega, Kiambu, Kilifi, Kisumu, Mombasa, Nairobi, Nakuru, Garissa, Kisii, Migori, Machakos, Kwale, Kericho, Kajiado, Samburu, Tana River, West Pokot, Turkana, Mandera, and Wajir with 727,267 deliveries (62%) annually: |  |
| - Updated national training package for integrated MNH (SBBC+) by end month 3 - A national pool of 70 mentors9 trained on SBBC+ package by end month 6 - National mentorship database established that includes facility training and clinical data, and clinical logbooks for each mentee by end month 9 - A pool of 30 mentors per region (360 total) with competencies in above established by end Year 1 - At least 2,000 facility champions identified, trained and mentored onsite in antenatal, labor and delivery and newborn care and simulation facilitation and quality improvement in focus facilities by end Year 1 - Data-informed mentorship visits reach ~10,000 health workers in target facilities as scheduled (quarterly in Years 1-3, and bi-annually in Years 3-4) | - >80% of 200 facilities (disaggregated by type, EMoNC designation) meet EmONC signal functions by end Year 2 - >80% of health workers in targeted maternity and newborn units (200) achieve EmONC and SSNC competency by end Year 3 (target to be determined post-baseline assessment) - Low-dose high-frequency simulation-based 1) skill drills (90% of individual level maternity and neonatal health workers practice daily) and 2) team training (90% of maternity and neonatal unit levels train and debrief weekly based on data-informed gaps) practiced at 90% of facilities by end Year 3. - Data-informed quality improvement cycles practiced independently at 90% of maternity and neonatal units in focus facilities at a minimum frequency of at least one cycle per month per facility by end Year 3 Coverage of interventions increased to 80% by end Year 3: - % of pregnant women attending ANC screened for 1) anemia, 2) infection, and 3) high-blood pressure - % of women attending ANC who receive POCUS or U/S, with gestational age recorded on the first visit - % of women receiving quality intrapartum care and management of complications (Post-partum Hemorrhage (PPH), Sepsis, Pre-Eclampsia/Eclampsia and Obstructed labour) according to guidelines - % of women who received digital intrapartum monitoring in labor - % of eligible women with pre-term labor who received antenatal corticosteroids - % of women with PPH detected early (300ml-500ml blood loss) and WHO-recommended treatment bundle received - % of eligible babies who received neonatal resuscitation - % of eligible preterm and low birth-weight babies who receive iKMC - % of babies between 1000-1499g who receive prophylactic CPAP - % of eligible babies between 1500-1999g with respiratory distress who receive CPAP - % of babies with clinical jaundice who receive phototherapy - % of babies with suspected sepsis who receive parenteral antibiotics - % of babies not hypothermic on admission to the neonatal unit - % of babies not hypothermic at any time in the neonatal unit At targeted CEmONC facilities (baseline and targets for below indicators to be established by end Year 1 following baseline health facility assessment) - Increased % of women with direct obstetric complications who are definitively treated without outward referral - 90% of members of obstetric surgical teams achieve competency by end Year 3 (as measured by Objective Structured Clinical Exams) - 90% of facilities meet standard safety and infection prevention practices according to the Safe Surgical Checklist by end Year 3 - Less than 10% of post c-section surgical site infections while in-patient in the facility by end Year 3 Additional measures (baseline and target to be determined): - Reduced % of births in health facilities that are intrapartum stillbirths or livebirths followed by very early neonatal death - Reduced % of babies admitted to neonatal unit with a diagnosis of birth asphyxia |

| Obj. 2 Availability of quality MNH commodities improved in focus districts and at national level |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 200 facilities in 21 counties: Bungoma, Kakamega, Kiambu, Kilifi, Kisumu, Mombasa, Nairobi, Nakuru, Garissa, Kisii, Migori, Machakos, Kwale, Kericho, Kajiado, Samburu, Tana River, West Pokot, Turkana, Mandera, and Wajir, and national support |  |
| - 100% of facilities provide package of ANC diagnostics by end Year 1 - 100% of facilities equipped with POCUS, priority MNH products by end Year 1 - >80% of facilities with all tracer commodities to perform EmONC as designated by end Year 1 - Planned preventive maintenance for MNH devices conducted according to guidelines by end Year 2 | By end of Year 3 - 90% inventory accuracy of priority MNH products, as measured by pharmacy ledger vs. physical count data vs eLIMS - <10% stockouts of critical MNH products in targeted facilities by end Year 3 - >80% uptime of antenatal, intrapartum, and small and sick newborn care devices by end Year 3 - 80% of the MNH priority drugs tracked through the eLMIS and track and trace platfor to ensure quality by end Year 3 |
| At national level |  |
| By end Year 1: - Timely procurement, clearance, and distribution of Beginnings Fund-funded priority MNH products (see Annex D) completed by end Year 1 - Identification of critical gaps impeding new product intro and scale-up in all regulations and policies relevant for MNH product provision by end Year 1 | - Variance between the forecasted and actual demand for MNH products reduced to <15% by end Year 5 - Decreased gap between quantified need for MNH commodities and budget (government + donors) to <10% by end Year 5 - 90% of targeted facilities budgeting for essential MNH products costs based on actual need by end Year 5 - 100% inclusion of new products in relevant regulations and policies - 100% standardization of existing products in regulations and policies - 100% inclusion in standardized list of priority medical devices - 100% costing and recommendation for inclusion in Social Health Insurance Fund (SHIF) standard benefits package |

| Obj. 3 Improved quality, number, distribution of MNH workforce in focus districts and at national level |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 172 facilities in 15 counties (Bungoma, Kakamega, Kiambu, Kilifi, Kisumu, Mombasa, Nairobi, Nakuru, Garissa, Kisii, Migori, Machakos, Kwale, Kericho, and Kajiado): |  |
| - Up to 200 additional health workers (doctors, clinical officers, nursing officers, biomedical technologists) recruited and deployed county employes with at least 1 year contracts by end Year 1 using county resources - Up to 200 additional health workers in (doctors, clinical officers, nursing officers, biomedical technologists) recruited and deployed as county employes with at least 1 year contracts by end Year 1 using matching funds from Beginnings fund | - 90% of targeted maternity and neonatal units achieve sustained staff: patient ratios of 1:15 by end Year 2 (target to be determined post-baseline assessment) - 80% (of the 200 additional health workers recruited using Beginnings Fund matching funds) are transitioned to county payroll and budget by end Year 4 - 10% of those not absorbed continue as contractual employees at the same designated facilities Across all target counties: - % of targeted CEmONC facilities (165) that have requisite skills-mix of MNH specialists (midwives, anesthetists, theatre nurses, pediatricians, OBS/GYN) by end Year 5 (target to be determined post-baseline assessment) - >80% of staff in target facilities (165) are trained (~2500 health workers) on the newborn package of interventions (the comprehensive newborn protocol for Level 2 neonatal care units) and maternal package of interventions (enhance EmONC training and safe surgery), and engage county and hospital leadership to recognize their competencies and reduce rotation |
| At national level: |  |
| - Support the establishment of one additional training program for neonatal nurses in Moi University to increase production capacity from 50 to 100 neonatal nurses per year through support for faculty training, and equip for teaching and learning by end Year 1 - Support MOH in partnership with training institutions and teaching hospitals to upskill teaching faculty (in nursing, clinical officer, bio-medical engineering and medical schools) on new guidelines and technologies and sub-sequent introduction into respective curriculums end Year 3 | 270 MNH specialists enrolled in post-basic/post-graduate training: 20 MMED anaesthesia, (through CANESCA); 20 MMED paediatrics – neonatology (through ECSAPACH); 50 MSc neonatology nursing; 50 MSc in midwifery, 30 BSc Biomedical Engineering (upgrading), 60 diploma neonatal nurses, 40 Clinical Officer or nurse Anaesthetists - 95% are strategically selected according to Beginnings Fund-MOH criteria - 90% complete training and graduate within 12 months of program timeline - Increase in number of MNH specialists in the public sector (baseline to be determined) - 90% appropriately deployed to high-burden maternity and newborn units 90% retained in the public sector at 12 months post deployment |

| Obj. 4: Critical health system enablers, including MNH infrastructure, data and quality, emergency transport and referral systems, leadership and management, and advocacy strengthened for greater impact and sustainability |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| Infrastructure: - Infrastructure assessments completed by end month 6 in 15 intensive target counties - Renovation of up to 20 neonatal care units completed by end Year 3 - Renovation of up to 20 maternity units and theatres completed by end Year 3 - Renovate level 2 neonatal care units (NICU) to accommodate five beds for level 3 neonatal intensive care in four county referral hospitals by end Year 3 - Renovation of up to 20 Biomedical Engineering workshops completed by end Year 3 MNH Data Systems: - Taifa care rolled out to all MNH service points in 200 health facilities by end month 6 - M-NID data fully operational in Taifa Care by end Year 1 - M-NID data baseline established by month 18 - M-NID dashboard developed at facility, county and national level level by month 18 - Program monitoring dashboards for quality of care, workforce, and referrals developed and regularly used by MOH and counties in focus facilities, counties and at national level by month 18 - Conduct baseline (by end month 3) and endline Health Facility Assessment in 200 health facilities across 21 counties including tool adaptation, training, data collection and analysis - Develop a program indicator matrix covering all implementing agencies and partners developed and completed quarterly - Annual data management and use through county refresher data analysis/literacy training and mentorship | Infrastructure: - Renovate level 2 neonatal care units, maternity units and theatres in target counties in line with MOH guidelines for zero separation while addressing address key gaps in service delivery –Renovations - 12 major; 60 minor and 16 health centre upgrades. - Biomedical workshops built and equipped in up to 21 facilities (target post baseline assessment) by end Year 3 - % increase in functional Level 2 neonatal units in 15 intensive counties (target at baseline) - % increase in biomedical workshops at county level in 15 intensive counties (target at baseline) - % increase in mother-baby neonatal units (target TBD at baseline) MNH Data Systems: - 90% of patient-level M-NID data meet program defined data quality and completeness criteria by end Year 3 - >95% of facilities utilize MNH dashboard for quality improvement and decision making by end Year 3 - 200 health facilities have maternal newborn dataset integrated and in use in either Taifa Care by end Year 1 - >90% of the target health facilities in the 21 counties can exchange patient level data and allow for longitudinal follow-up by end Year 2 - >90% of the target health facilities in the 21 counties are integrated and submit data to the national MNH dashboard and central data warehouse by end Year 2 Emergency Transport and Referral: - Cost-effective, scalable model for post-natal care follow up of vulnerable neonates established by end Year 2 |

Annex B: Target Facilities

Annex C: MNH Commodities Funding Sources and Beginnings Fund Budget

Annex D: Eligibility and operationalization of Milestone-based grants

This guidance note sets out the operational framework for milestone-based co-financing to gap-fill priority MNH workforce needs and essential medical commodities across the 21 target counties. Designed with sustainability in mind, the approach ring-fences funding to avoid displacement of existing MNH financing, while incentivising increased domestic allocations through a phased and predictable transition of Beginnings Fund support. The model establishes a clear separation of roles: counties lead implementation of agreed actions and milestones; the Council of Governors (CoG) provides independent verification and intergovernmental coordination; and ICRHK acts at the fiscal agent that manages the disbursements alongside its broader portfolio-level coordination and monitoring, evaluation, and learning (MEL) mandate.

Contractual and Governance Architecture

The milestone-based co-financing mechanism will be operationalised and governed through three complementary contractual arrangements, designed to ensure clear role separation, enforceability, fiduciary assurance and smooth coordination across the parties.

- Beginnings Fund–ICRHK grant agreement: This agreement will define ICRHK’s mandate as the fiduciary agent and pass-through entity for the milestone-based co-financing, including responsibility for receiving funds and executing disbursements upon receipt of verification reports, supporting documents from COG, and a no-objection from BF. This role is anchored within ICRHK’s broader mandate for portfolio coordination, monitoring, evaluation, and learning (MEL) across the Kenya investment.

- Beginnings Fund–CoG grant agreement: This agreement will set out the CoG’s role in intergovernmental coordination, county onboarding, and independent verification of milestone achievement. It will formally establish CoG’s function as the milestone verification body, including responsibilities for documentation review, field-level verification where required, and facilitating peer learning and accountability across participating counties.

- Tripartite Partnership Agreement (County Government–CoG–ICRHK):  this will be executed with each participating County Government as a condition of eligibility to access the milestone-based co-financing. This agreement will formalise county opt-in and set out commitments related to agreed performance milestones, documentation and reporting requirements, access for independent verification, and compliance with applicable contractual requirements. It will define the operational interface between counties, CoG, and ICRHK for implementation, verification, and disbursement processes. Annexed to the Agreement will be the specific milestone schedule and performance targets to which the County Government has formally committed.

County Eligibility to Participate

Eligibility to participate in the milestone-based co-financing mechanism will be based on county opt-in, formalised through execution of a Tripartite Partnership Agreement between the participating County Government, the CoG and ICRHK. The agreement will be executed within 6 months of investment start date, with execution formally confirmed and communicated by CoG through provision of executed copies to the Beginnings Fund.

The Partnership Agreement will set out the County Government’s commitments in relation to the agreed performance milestones linked to the co-financing arrangements, including obligations to provide timely and complete technical and financial documentation and to facilitate access by CoG for purposes of independent verification. The Agreement will also require counties to implement all supported activities in full compliance with applicable Kenyan legal, regulatory, and public financial management requirements, consistent with the standards governing the use of county public resources.

Performance Milestones

MNH Workforce

The workforce milestones focus on strengthening staffing levels and sustaining improved staff-to-patient ratios in priority maternity and newborn service delivery units, while progressively transitioning workforce costs supported by the programme to county financing.

MNH Workforce Milestones

| Timeline | Milestones | Means of verification | Linked Disbursement Amount |
| --- | --- | --- | --- |
| Within 6 months of grant start (1 Nov 2026) | - Tri-partite Partnership Agreement signed - In collaboration with Beginnings Fund, establish a baseline staffing profile (by cadre and numbers) for designated maternity and newborn units at participating facilities, defining the benchmark staff-to-patient ratios and agreed HRH gaps to be jointly addressed - Agreement on a phased staffing plan, structured into two cohorts, jointly endorsed by the County Department of Health and the County Public Service Board (CPSB), and formally acknowledged by the CoG. | - A report documenting the baseline staffing profile and an agreed phased staffing plan endorsed by the County Department of Health, CPSB and County Treasury. - CoG verification report confirming recruitment process on course (recruitment request memo, advertisement, shortlisting & interviews, appointment offer letters, posting letters). | Up to USD875,000 |
| 1st March 2027 | - County Government has completed recruitment and deployment of the first cohort of MNH staff in line with the agreed phased staffing plan. | - CoG verification report confirming recruitment and deployment, supported by county-issued deployment lists and facility-level confirmation of staffing in post. | Up to USD875,000 |
| 1st August 2027 | - MNH staff recruited and deployed in the preceding year have been retained in designated maternity and newborn units, and any attrition has been promptly addressed through replacement. - County Government has completed recruitment and deployment of the second cohort of MNH staff in accordance with the agreed phased staffing plan, resulting in an improvement in staff-to-patient ratios from the established baseline in designated maternity and newborn units. | - CoG verification report confirming recruitment and deployment, supported by county-issued deployment lists and facility-level confirmation of staffing in post. | Up to USD875,000 |
| 1st February 2028 | - CoG verification report confirming MNH staff recruited and deployed in the preceding two years have been retained in designated maternity and newborn units, and any attrition has been promptly addressed through replacement. | - CoG verification report confirming recruitment and deployment, supported by county-issued deployment lists and facility-level confirmation of staffing in post. | Up to USD875,000 |
| 1st August 2028 | - MNH staff recruited and deployed in the preceding two years have been retained in designated maternity and newborn units, and any attrition has been promptly addressed through replacement. - Verifiable evidence of increased county budget allocations to MNH workforce financing, matching or exceeding an approximately 15% reduction in the Beginnings Fund contribution (relative to the base year) | - CoG verification report confirming recruitment and deployment, supported by county-issued deployment lists and facility-level confirmation of staffing in post. - County quarterly and annual budget implementation reports showing increased allocation to health workforce. | Up to USD1,500,000 |
| 1st August 2029 | - MNH staff recruited and deployed in the preceding three years have been retained in designated maternity and newborn units, and any attrition has been promptly addressed through replacement. - Verifiable evidence of increased county budget allocations to MNH workforce financing, matching or exceeding an approximately 25% reduction in the Beginnings Fund contribution (relative to the base year) | - CoG verification report confirming recruitment and deployment, supported by county-issued deployment lists and facility-level confirmation of staffing in post. - County quarterly and annual budget implementation reports showing increased allocation to health workforce. | Up to USD1,300,000 |
| 1st August 2030 | - MNH staff recruited and deployed in the preceding three years have been retained in designated maternity and newborn units, and any attrition has been promptly addressed through replacement. - Verifiable evidence of increased county budget allocations to MNH workforce financing, matching or exceeding an approximately 60% reduction in the Beginnings Fund contribution (relative to the base year) | - CoG verification report confirming recruitment and deployment, supported by county-issued deployment lists and facility-level confirmation of staffing in post. - County quarterly and annual budget implementation reports showing increased allocation to health workforce. | Up to USD700,000 |

MNH Commodities

The MNH commodities performance milestones focus on strengthening county allocation and execution of health budgets, alongside proportional increases in county financing for medical commodities as external Beginnings Fund support tapers. Counties will be supported to achieve these milestones through targeted technical assistance delivered via a separate investment (provisionally via inSupply). Commodity procurement will be undertaken through KEMSA or MEDS, the two primary suppliers routinely used by counties. Both suppliers maintain adequate stock levels, have demonstrated fill rates of over 90 percent in recent months, and operate digital platforms that enable real-time order tracking, electronic proof of delivery, and efficient last-mile distribution directly to health facilities. KEMSA has existing MoUs with counties with a provision for 90-days credit period, which allows the counties to make payment once an order has been processed and supplied. A list of priority MNH commodities will be jointly agreed by the Beginnings Fund, the MoH, and the CoG following the baseline health facility assessment, to enable cost predictability, consolidated procurement planning, and to prevent requests for items not directly related to MNH priorities. Beginnings Fund supported procurement list will be consolidated in single Local Purchase Order (LPO) on bi-annual basis for ease of tracking and verification.

MNH Commodities Milestones

| Timeline | Milestones | Means of verification | Linked Disbursement Amount |
| --- | --- | --- | --- |
| 1st November 2026 | - Tri-partite Partnership Agreement signed - In collaboration with Beginnings Fund, establish a baseline of the MNH commodities funding gap and an agreed year-by-year financing plan outlining progressive increases in county budget allocations for MNH commodities over the co-financing period. - Documented baseline of the county health budget allocation (excluding conditional grants) as a proportion of the total annual county budget for the preceding financial year. - Procurement of MNH commodities based on identified gap from baseline assessment in accordance with the BF-approved commodity list through KEMSA or MEDS, with verified proof of delivery to designated health facilities and corresponding supplier invoices submitted for payment. | - A report documenting the baseline MNH commodities funding gap and an agreed phased financing plan to progressively address the gap, formally endorsed by the County Department of Health and the County Treasury. - CoG verification report confirming baseline county health budget allocation and medical commodities budget execution status, supported by statutory Office of the Controller of Budget (OCoB) reports. - CoG verified proof of delivery to designated health facilities and corresponding supplier invoices. | Up to USD2,520,000 (Up to USD120,000 per county as seed fund to fill immediate commodity gaps) |
| 1st August 2027 | - Demonstrated allocation of at least 25 percent of the total annual county budget to health (excluding conditional grants) in the preceding financial year. - Demonstrated execution of at least 85 percent (70% for counties with a baseline of <60%) of exchequer funds allocated to medical commodities in the preceding financial year, as reflected in county budget implementation reports. - Demonstrated proportional increase in county budget allocations for MNH commodities corresponding to reductions in Beginnings Fund support. - Procurement of MNH commodities in accordance with the BF-approved commodity list through KEMSA or MEDS, with verified proof of delivery to designated health facilities and corresponding supplier invoices submitted for payment. | - CoG verification report confirming county health budget allocation and medical commodities budget execution thresholds, supported by statutory Office of the Controller of Budget (OCoB) reports. - CoG verified proof of delivery to designated health facilities and corresponding supplier invoices. | Up to USD2,250,000 |
| 1st August 2028 | - Demonstrated county health budget allocation of at least 25 percent (excluding conditional grants), with progressive year-on-year increases up to a cap of 30 percent. - Demonstrated execution of at least 85 percent of exchequer funds allocated to medical commodities in the preceding financial year, as reflected in county budget implementation reports. - Demonstrated proportional increase in county budget allocations for MNH commodities corresponding to reductions in Beginnings Fund support. - Procurement of MNH commodities in accordance with the Beginnings Fund–approved commodity list through KEMSA or MEDS, with verified proof of delivery to designated health facilities and corresponding supplier invoices submitted for payment. | - CoG verification report confirming county health budget allocation and medical commodities budget execution thresholds, supported by statutory Office of the Controller of Budget (OCoB) reports. - CoG verified proof of delivery to designated health facilities and corresponding supplier invoices. | USD2,000,000 |
| 1st August 2029 | - Demonstrated county health budget allocation of at least 25 percent (excluding conditional grants), with progressive year-on-year increases up to a cap of 30 percent. - Demonstrated execution of at least 85 percent of exchequer funds allocated to medical commodities in the preceding financial year, as reflected in county budget implementation reports. - Demonstrated proportional increase in county budget allocations for MNH commodities corresponding to reductions in Beginnings Fund support. - Procurement of MNH commodities in accordance with the Beginnings Fund–approved commodity list through KEMSA or MEDS, with verified proof of delivery to designated health facilities and corresponding supplier invoices submitted for payment. | - CoG verification report confirming county health budget allocation and medical commodities budget execution thresholds, supported by statutory Office of the Controller of Budget (OCoB) reports. - CoG verified proof of delivery to designated health facilities and corresponding supplier invoices. | USD1,500,000 |
| 1st August 2030 | - Demonstrated county health budget allocation of at least 25 percent (excluding conditional grants), with progressive year-on-year increases up to a cap of 30 percent. - Demonstrated execution of at least 85 percent of exchequer funds allocated to medical commodities in the preceding financial year, as reflected in county budget implementation reports. - Demonstrated proportional increase in county budget allocations for MNH commodities corresponding to reductions in Beginnings Fund support. - Procurement of MNH commodities in accordance with the Beginnings Fund–approved commodity list through KEMSA or MEDS, with verified proof of delivery to designated health facilities and corresponding supplier invoices submitted for payment. | - CoG verification report confirming county health budget allocation and medical commodities budget execution thresholds, supported by statutory Office of the Controller of Budget (OCoB) reports. - CoG verified proof of delivery to designated health facilities and corresponding supplier invoices. | USD1,000,000 |

Allocation of Disbursement Amounts

The total envelope for milestone-based co-financing amounts to USD16.27million, comprising USD7million for the health workforce and USD9.27million for essential medical commodities. Allocation of these resources across the 21 target counties will be guided by the Commission on Revenue Allocation (CRA) formula, which is the nationally established basis for equitable sharing of resources among county governments. Applying the CRA formula ensures transparency, equity, and consistency, while avoiding ad hoc negotiations or contestation over allocations. Under this framework, each county’s allocation will be pre-determined using the CRA formula, arriving at a schedule as follows:

Disbursement Allocation Schedule

| County | % allocation (derived from CRA formula) | MNH Workforce Allocation (USD) |  |  |  |  | MNH Workforce Allocation (USD) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| Total |  |  |  |  |  |  |  |  |  |  |  |

Milestone Verification Process (CoG-Led)

The CoG will serve as the intergovernmental coordination and independent verification body responsible for confirming county achievement of the agreed performance milestones linked to the co-financing arrangements. Verification will be conducted in a structured, transparent, and time-bound manner, drawing on statutory public finance documents, administrative records, and targeted field verification, and will form the formal basis for authorising milestone-based disbursements.

The verification process will encompass the following steps:

- County onboarding: The CoG will lead the county onboarding process, including facilitating county opt-in, executing Partnership Agreements between participating County Governments and CoG within agreed timelines, and formally confirming and communicating executed agreements to the Beginnings Fund and ICRHK. Through this process, CoG will ensure that participating counties have formally committed to the agreed performance milestones, documentation and reporting requirements, access for independent verification, and compliance with applicable Kenyan legal, regulatory, and public financial management frameworks.

- Annual verification planning: At the start of each verification year, the CoG will communicate the agreed performance milestones, documentation and reporting requirements, verification timelines, and cut-off dates to participating counties, aligned with the predefined annual disbursement calendar.

- Submission of county documentation: County Governments will submit the required technical, administrative, and financial documentation as specified in the Partnership Agreement and milestone schedule, including planning and budget documents, budget implementation reports, deployment confirmations, and procurement records, as applicable.

- Desk-based verification: CoG will conduct desk reviews of submitted documentation, triangulating county submissions with statutory sources such as OCoB reports, approved County Annual Work Plans and Budgets (AWPBs), County Fiscal Strategy Papers (CFSPs), and other relevant public financial management records.

- Field-level verification (as required): Where necessary, CoG will undertake targeted field verification to confirm deployment of MNH staff in designated maternity and newborn units and delivery of MNH commodities to health facilities, working through appropriate county structures and in coordination with relevant Beginnings Fund implementing partners in the respective counties.

- Independent verification reporting: For each verification cycle, CoG will prepare a formal verification report summarising milestone achievement status for each county, identifying any gaps or partial achievement, and clearly indicating whether milestones have been met, delayed, or not achieved. The report will annex the county-submitted supporting documentation including facility-level staffing summaries demonstrating maintained/improved staffing levels and staff-to-patient ratios relative to baseline, county budget implementation/execution reports (or extracts) demonstrating increased county financing consistent with the agreed transition schedule, and proof of commodity procurement, invoices, and delivery.

- Triggering disbursements: CoG verification reports will be formally submitted to the Beginnings Fund and ICRHK and will serve as the primary basis for confirming milestone achievement and triggering milestone-based disbursements, subject to concurrence by the Beginnings Fund and in accordance with the agreed allocation schedule.

- Feedback and corrective actions: Where milestones are not fully achieved, CoG will communicate required corrective actions to counties and provide advisory support, including peer learning and technical guidance, to enable achievement within ahead of the next verification cycle.

Milestone-based Disbursement Modalities (ICRHK-Managed)

ICRHK will serve as the fiduciary agent and pass-through entity for funds under the milestone-based co-financing mechanism. Upon receipt of a CoG verification report confirming milestone achievement and following issuance of a formal no-objection communication by the Beginnings Fund, ICRHK will release disbursements in accordance with the Partnership Agreements and the agreed milestone schedule. Disbursements related to MNH workforce and commodities milestones will follow distinct funding flows, as described below.

Disbursement Flow for MNH Workforce

- MNH workforce disbursements will be executed as milestone-based co-financing in arrears, intended to support counties to absorb and retain expanded MNH staffing capacity in designated maternity and newborn units. Disbursements will not be linked to named staff, individual contracts, or payroll invoices, but to verified increases in staff numbers deployed and retained in the units. Disbursements will be made semi-annually to synchronise with COG verification for the commodities milestones. As illustrated in the Workforce milestones table above, an initial tranche will be advanced to enable counties to recruit the first cohort of staff, while phased recruitment is incorporated into subsequent financial year budgets

- Disbursements will be released by ICRHK upon receipt of a CoG verification report (supported by county-issued deployment lists and facility-level confirmation of staffing in post) and a Beginnings Fund no-objection and processed within 30 days of the no-objection.

- Disbursements will be transferred to the participating County Government through the official County Revenue Fund or other lawful county bank account designated for receipt of intergovernmental or programme-related funds, as specified in the Partnership Agreement and confirmed by the County Treasury.

- Following receipt of funds, the County Government will submit to ICRHK (with copy to CoG and Beginnings Fund) a formal acknowledgement of receipt.

Disbursement Flow for MNH Commodities

- Disbursements linked to MNH commodities milestones will be made directly to suppliers (KEMSA or MEDS) as payment in arrears, following verified proof of delivery to designated health facilities. This approach is intended to minimise fiduciary risk and is aligned with the standard procurement and payment models used by counties when sourcing commodities through KEMSA or MEDS.

- ICRHK will initiate commodities-related disbursements upon receipt of a CoG verification report confirming achievement of the applicable MNH commodities milestones, and a formal no-objection communication from the Beginnings Fund confirming concurrence to proceed.

- Subject to receipt of a valid invoice and supporting documentation, ICRHK will process and settle supplier invoices within 45 working days, in line with the agreed disbursement schedule. All commodity-related disbursements will be made directly to KEMSA or MEDS, as applicable, through the supplier’s officially designated bank account. No commodity funds will be transferred to county accounts.

- Following receipt of payment, KEMSA or MEDS will issue a formal acknowledgement of receipt to ICRHK, copied to the CoG, the Beginnings Fund, and the relevant County Government.

Additional Requirements and Considerations

- Predictability and administrative efficiency: To minimise administrative burden and ensure predictability, milestone-based disbursements will follow a predefined annual disbursement calendar with clearly specified cut-off dates for milestone achievement, verification, and disbursement. The CoG will conduct milestone verification in a coordinated and harmonised manner across participating counties, enabling ICRHK to process disbursements efficiently and within agreed timelines. Synchronised disbursement cycles will also facilitate consolidation of MNH commodity orders through KEMSA or MEDS, improving procurement efficiency and price leverage.

- Transparency, accountability, and public financial management compliance: Transparency and accountability will remain central to the operation of the performance-linked co-financing mechanism. All parties will be required to maintain clear documentation, timely reporting, and full auditability of milestone verification, disbursement decisions, and use of funds, in line with applicable Kenyan public financial management regulations and the Beginnings Fund’s fiduciary standards. The Beginnings Fund expects that all disbursements and related expenditures will be captured and reflected in statutory county financial reporting, including relevant budget implementation reports submitted to, or reflected by the OCoB, in accordance with applicable PFM requirements. Counties will also reflect receipt and use of MNH commodities through routine stock management and reporting systems, consistent with standard public sector procedures. ICRHK will undertake onsite verification audits on a sample of selected facilities against the COG verification reports.

Kenya Demographic and Health Survey (KDHS), 2022. https://dhsprogram.com/pubs/pdf/PR143/PR143.pdf

Murphy, Georgina A. V.; Gathara, David; Abuya, Nancy; Mwachiro, Jacintah; Ochola, Sam; Ayisi, Robert; English M. Effective coverage of essential inpatient care for small and sick newborns in a high mortality urban setting: A cross-sectional study in Nairobi City County, Kenya. BMC Med [Internet]. 2018;

Ministry of Health 2025: Kenya Quality of Care Health Facility Assessment: Service Availability and Readiness Report

Zhao Y, Osano B, Were F, et al Characterising Kenyan hospitals’ suitability for medical officer internship training: a secondary data analysis of a cross-sectional study. BMJ Open 2022;12:e056426. doi: 10.1136/bmjopen-2021-056426

Griffiths P, Recio-Saucedo A, Dall’Ora C, et al. The association between nurse staffing and omissions in nursing care: A systematic review. J Adv Nurs. 2018 Jul;74(7):1474–87.

Ministry of Health 2025: Kenya Quality of Care Health Facility Assessment: Service Availability and Readiness Report

MOH (2017) Saving Mothers Lives; the First Confidential Enquiry into Maternal Deaths

MMR: 355 to 88 per 100,000 live births, SBR:18 to 12 per 1,000 live births, and NMR: 21 to 11 per 1,000 live births.

Gates Foundation has rolled out POCUS in 500 health facilities across 8 counties and is undertaking AI enabled POCUS implementation in 5 additional counties in western Kenya. POCUS guidelines have also been developed and launched

Murphy GAV, Waters D, Ouma PO, Gathara D, Shepperd S, Snow RW, English M. Estimating the need for inpatient neonatal services: an iterative approach employing evidence and expert consensus to guide local policy in Kenya. BMJ Glob Health. 2017 Nov 14;2(4):e000472. doi: 10.1136/bmjgh-2017-000472.

Leverage on Field Technologies investments in eLIMS funded by Gates Foundation

Best practices will be adopted from the DANIDA and the World Bank Transforming Health Systems projects that have utilized similar approaches

Leverage Gates Foundation grant to AMPATH and CPHD on POCUS introduction

Field Technologies has a grant from Gates Foundation to strengthen eLIMS systems targeting 11 counties with overlaps in 5 Beginnings Fund target counties

Selection criteria: 1) upgrading trainees employed in public sector or faith-based facilities from target counties, 2) trainees agree to bonding for period of training upon completion of training

The Ministry of Health has confirmed availability of computers to enable roll-out of Taifa care in County and sub-county hospitals