TANZANIA MAINLAND INVESTMENT PLAN

Country Investment Plan Overview

| Grantees: | Investments Presented: - Government of Tanzania – Ministry of Health (MOH) - Government of Tanzania – Prime Minister’s Office of Regional Administration and Local Government (PMO-RALG) - Ifakara Health Institute (Ifakara) - Haydom Lutheran Hospital (Haydom) Investments Planned: - Government of Tanzania - Medical Stores Department (MSD) - InSupply Health - Results for Development (R4D) - Benjamin Mkapa Foundation (BMF) - Doris Mollel Foundation (DMF) - Muhimbili National Hospital - Association of Obstetrician-Gynaecologists of Tanzania (AGOTA) |
| --- | --- |
| Implementer(s) (if different to Grantee): | - Paediatric Association of Tanzania |
| Geographic Focus: | Mwanza, Tabora, Dar es Salaam, Kagera, Simiyu, Mara, Dodoma, Morogoro, Shinyanga, Mbeya, Ruvuma and Mtwara, and national support |
| Amount: | USD75.4million budget, of which US43.2million (57%) in investments are presented to the Investment Committee at the March 2026 meeting, and the remainder will be presented by Q3 2026. This plan covers both presented and planned investments. |
| Co-Investment: | Total: USD175.2million: - Government of Tanzania: USD167million – see Annex E - Technical Support Partners: USD8.2million |
| Term: | 60 months (1 March 2026 – 28 February 2031) |
| Investment Description and Impact Goals: | Beginnings Fund will invest in the scale-up of priority antenatal, intrapartum and newborn interventions that address the primary drivers of maternal and neonatal mortality and stillbirths. This will include management and access to quality maternal and newborn health (MNH) products, increasing the number, competency, skill-mix and distribution of the MNH workforce, improving MNH data systems, supporting neonatal care unit infrastructure development, improving referrals and emergency transport for newborn emergencies, strengthening MNH leadership and management, and advocating for additional MNH resources and scale-up of best practices. Through these investments, the Beginnings Fund will catalyze Tanzania’s 2030 maternal and newborn health goals, saving ~53,628 lives, by: - reducing maternal mortality by 33% from 104 to 70 per 100,000 live births - reducing stillbirths by 33% from 18 to 12 per 1,000 live births - reducing neonatal mortality by 50% from 24 to 12 per 1,000 live births |
| Pathway to Impact: | See Annex A |
| Governance and Management: | A governing steering committee, co-chaired by the Permanent Secretary, Ministry of Health (MOH), and the Deputy Permanent Secretary, Prime Minister’s Office of Regional and Local Government (PMO-RALG), with the Beginnings Fund CEO, will meet bi-annually to provide strategic direction, address major bottlenecks, and approve annual budgets and workplans. A management team comprising MOH and PMO-RALG technical leads, partner representatives, and the Beginnings Fund investment team, will meet regularly to cooridinate implementation. See Annex B. Beginnings Fund will finalize a Memorandum of Understanding with the Government of Tanzania outlining key commitments and measures of success once the Tanzania Mainland Investment Plan is approved. |

| Acronyms and Definitions |  |
| --- | --- |
| Afya eHMS | Afya Electronic Health Management System - electronic medical record system used in regional referral hospitals in Tanzania. |
| AGOTA | Association of Gynaecologists and Obstetricians of Tanzania |
| B/CEmONC | Basic/Comprehensive Emergency Obstetric and Newborn Care |
| CPAP | Continuous Positive Airway Pressure |
| CTG | Cardiotocography |
| DHIS2 | District Health Information Software 2 – the national health management information system |
| ECSA | East, Central, Southern Africa College of Health Sciences – provides standardized curricula, assessments, faculty training and accreditation for hospital-based fellowship training |
| EMRs | Electronic Medical Records |
| GFF | Global Financing Facility |
| GOTHOMIS | Government of Tanzania Hospital Management Information System - electronic medical record system used in primary health care facilities from dispensaries to district hospitals |
| HRHIS | Human Resource for Health Information System |
| ICT | Information, Communication, and Technology |
| iKMC | Immediate Kangaroo Mother Care |
| LDHF | Low-dose high frequency training |
| Level 2 Newborn Care | Level 2 is special newborn care: thermal care, assisted feeding and IV fluids, safe administration of oxygen, detection and management of sepsis (injectable antibiotics), management of neonatal encephalopathy/asphyxia and pathological jaundice, management and referral of congenital abnormalities, use of CPAP for respiratory distress, screening of other conditions. |
| MOH MOH DPPD MOH DRHRD MOH DRMCH MOH PSU MOH ICT MOH MEL | Ministry of Health MOH Department of Planning and Policy Development MOH Department of Human Resource Development MOH Division of Reproductive, Maternal, and Child Health MOH Pharmaceutical Services Unit MOH Department of Information, Communication and Technology MOH Department of Monitoring, Evaluation and Learning. |
| MEMIS | Medical Equipment Management Information System |
| MNH | Maternal and Newborn Health |
| M-NID | Maternal – Newborn Inpatient Dataset |
| MPDSR | Maternal and Perinatal Death Surveillance and Response -a continuous data-driven cycle of identification, review, and analysis of deaths, followed by action to prevent future occurrences. Process identifies the factors contributing to each death to pinpoint specific weaknesses to inform targeted actions and quality improvement initiatives. |
| MSD | Medical Stores Department -government parastatal with the mandate to procure, store and distribute medicines and supplies to all public health facilities in the country. |
| NEST | Neonatal Essential Solutions and Technologies, implemented by Ifakara Health Institute in Tanzania |
| OBS/GYN | Obstetrics and Gynecology |
| PMO-RALG PMO-RALG DHSWNS | Prime Minister’s Office of Regional Administration and Local Government –oversees and coordinates the activities of regional secretariats and local government authorities. It responsibly for health service delivery at primary health care level from dispensary to district hospital level through regional and council health management teams. PMO-RALG Division of Health, Social Welfare and Nutrition Services |
| PAT | Paediatric Association of Tanzania |
| POCUS | Point of Care Ultrasound |
| PPH | Postpartum Hemorrhage |
| QI | Quality improvement |
| R4D | Results for Development |
| R/CHMT | Regional/Council Health Management Team |
| RMNCAH | Reproductive, Maternal Newborn, Child and Adolescent Health |
| SATA | Society of Anesthesiologists of Tanzania |
| SBBC | The Safer Birth Bundle of Care (SBBC) implemented by Haydom Lutheran Hospital in Tanzania is proven to reduce maternal mortality and early neonatal mortality, comprising: 1) user-friendly technologies including an upright bag and mask for newborn resuscitation. 2) Low-dose, high-frequency (LDHF) simulation-based training regular, hands-on skill drills and team-based clinical scenarios using manikins to help health workers build and retain critical skills for managing common obstetric and neonatal emergencies, such as birth asphyxia and postpartum hemorrhage. 3) Quality improvement - data-driven feedback loop local data are collected and analyzed weekly to guide ongoing training and improve care. |
| SBCC+ | The Safer Birth Bundle of Care Plus is the MOH integrated maternal and newborn package, which includes the SBBC approaches, and expands them to include priority interventions during antenatal, post-natal and small and sick newborn care. The SBBC+ package is implemented through a hub and spokes mentorship approach. |
| SSNC | Small and Sick Newborn Care |
| TMCHIP | Tanzania Maternal and Child Health Program supported by the World Bank and GFF |
| TWG | Technical Working Group |

Situation Analysis

Tanzania has made great strides improving maternal survival rates over the past decade, achieving an 80% reduction in the maternal mortality.  These transformative gains are a testament to Tanzania’s strategic investments and innovations such as:

- Bringing healthcare closer to communities through building and equipping ~2,000 new health facilities that allow more women to receive care from skilled providers during pregnancy and childbirth. As of 2022, institutional deliveries increased to 81% from 65% in 2015/16, and caesarean sections increased to 11% of all deliveries.3

- Improving emergency referral and transport through national scaleup of the m-mama initiative which ensures that more mothers receive emergency obstetric care, handling 180,728 cases to date.

- Early adoption of Maternal, Perinatal Death Surveillance and Response (MPDSR), a key quality improvement process which can prevent ~35% of maternal deaths and ~30% of perinatal deaths.

With committed government leadership, there is significant opportunity to build on this progress to achieve 2030 maternal and newborn health goals.

Maternal and Newborn Health (MNH) Snapshot:

To further accelerate progress, improvements in the quality of antenatal care of women and their babies during  labour and delivery are needed to address the leading causes of maternal morbidity and mortality. These are postpartum haemorrhage (33.4%), hypertensive disorders (14%) and puerperal sepsis (6.8%). Insights from the MPDSR review 2018-2023 indicate that ~80% of maternal deaths are linked to inadequate knowledge and skills among health workers. Lack of appropriate care for women experiencing antenatal or intrapartum complications drives the high stillbirth rate of 18 per 1,000 pregnancies in 2022, remaining nearly the same since 2015/16.3

Reducing the high and stagnated rate of neonatal mortality (24 deaths per 1,000 live births) driven by prematurity (35%), birth asphyxia (24%), and infections (23%),  will requires significant attention and resources to ensure adequate health workforce, commodities and infrastructure for Level 2 newborn care.

The Ministry of Health (MOH)’s One Plan III outlines priorities to achieve and sustain significant reductions in maternal and neonatal mortality and stillbirths:

- maintain and expand cost-effective interventions to reduce maternal morbidity and mortality

- expand essential newborn care at all BEmONC facilities

- establish Level 2 newborn care in all CEmONC facilities.

Beginnings Fund investment will help accelerate One Plan III implementation by addressing critical gaps in the health workforce, products and key system enablers across the continuum of antenatal, intrapartum and newborn care, and cross-cutting issues including infrastructure and data systems, as outlined below.

Key MNH Gaps:

Key elements of Emergency Obstetric and Newborn Care (EmONC) provision have not kept pace with healh facility expansion. Key challenges include insufficient implementation of national guidelines,  lack of commodities, and inadequate staffing. A readiness assessment of CEmONC health facilities showed an average readiness score of 69%, with poorer scores at lower-level facilities, where  BEmONC services were only functional in 20% of dispensaries and 39% of health centres.

The lack of commodity availability is critical with only  4% of facilities in a recent survey having all 15 essential medicines (mainly MNH-related) in stock in 2023, and only 1% of hospitals and health centres having all items for CEmONC. Key challenges include fragmented supply chains and inadequate forecasting due to under-capacitated pharmaceutical staff and the need for better data tools. Unstable supply of antenatal care commodities leads to most pregnant women not receiving urine and blood tests and blood pressure checks due to frequent stockouts of devices, test kits, and treatments.  There is also slow uptake of product innovations, such as the full WHO-recommended PPH bundle, despite the EMOTIVE trial being conducted in Tanzania.  The MOH has identified priority MNH products to be integrated in national guidelines and needs initial procurement and product introduction support to enable uptake.

Tanzania has a workforce staffing shortage of 55%, with health infrastructure expansion requiring an increase in the number of health workers. Over 2017- 2023, an estimated 32,500 additional health workers were required to staff new faciliities. While Tanzania has a more than adequate supply of health workers to fill this gap (with thousands of under-employed health professionals including medical doctors), the government could only issue employment permits for 28,061 health workers during that period due to financial constraints.  The gap contines to grow as new facilities are built to accommodate Tanzania’s rapid population growth.  To address this challenge, the government is using external funding to finance health worker employment to allow a graduated timeline for government absorption.  To date the Global Fund has supported 786 health workers who were absorbed as planned, and the World Bank is financing an additional 1,000 health workers. The expansion of this approach is a top government priority.

Another key challenge is the shortage and unequal distribution of qualified MNH specialists which limits the provision of quality care. Regional referral hospitals are experiencing alarming shortages of anaesthesiologists (86%),  paediatricians (51%),  Obstetricians and gynecologists (41%) and  only 17 midwifery specialists, seven neonatal nurses and 12 neonatologists nationally.

Tanzania’s rapid increase in health infrastructure did not include purpose-built neonatal care units. While an improvised approach to utilize existing space increased the number of neonatal care units from 14 in 2018 to 318 in 2024, 75% have only one to four beds. To reduce mortality, these units need to be expanded to facilitate zero separation of mothers and their babies, promoting warmth, breastfeeding, infection prevention, and well-being.

The MOH has standard plans for every level of care, reflecting WHO norms, and is mobilizing infratructure resources, however the gapremains high. With World Bank financing, additional construction of neonatal care units at 43 hospitals is planned, against the 189 district hospitals and 367 health centers (CEmONC) where neonatal care units are needed.

With respect to data systems, Tanzania has invested in government-owned electronic medical record (EMR) platforms, including GOTHOMIS at 80% of primary care facilities and Afya HMS at all regional referral hospitals. However, key MNH data variables are captured as free text, which undermines their ability to be aggregated into DHIS2 or tracked for coverage of quality-of-care indicators. Additionally, these systems are not yet fully interoperable; therefore, support is required to integrate them.

Health Financing Snapshot:

The government’s share in health financing has grown to USD19.7billion in 2024/25, a 49% increase from USD13.2billion in 2019/20, but only 7% of the total budget against the Abuja declaration goal of 15%. Donor funding as a percental of the national health budget declined from 33% in 2020 to 23% in 2022. However, Tanzania was still exposed to the recent reduction in bilateral funding, losing 50,000 health sector jobs, with immediate challenges in infectious disease programs and knock-on effects across the health sector, with a 2025 health product financing gap of ~USD60million.  The government is demonstrating resilience in the face of these challenges, allocating an additional USD74.8million for HIV, TB and malaria commodities, but additional increases in domestic health financing and external resource mobilization are needed. The MOH has challenges tracking resources for MNH and is requesting technical support to track MNH health financing so as to better inform domestic financing and external resource mobilization.

Current external donors for maternal, newborn and child health include the World Bank and Global Financing Facility (GFF), UNICEF, UNFPA, Korea Foundation for International Healthcare, Korea International Cooperation Agency (KOICA), GIZ, the Susan T. Buffet Foundation, and Bloomberg Philanthropies. The World Bank and GFF-supported Tanzania Maternal and Child Health Improvement Program (TMCHIP) is the major maternal and newborn health initiative in the country comprising USD318.5million over 2023-2027.  This includes equipping 175 primary care facilities to perform EmONC signal functions, providing onsite mentorship for 8,000 health workers in 14  regions (of 26) in the MOH integrated MNH package (known as the Safer Birth Bundle of Care Plus (SBBC+), pre-service and postgraduate training of 1,000 health workers including MNH specialists, and employing an additional 1,000 health workers.

This signficant investment has laid a strong foundation for further progress, and additional Beginnings Fund investment will both improve the quality and scale of these interventions to advance the latest MOH priorities as outlined in the Minister of Health’s Budget speech 2025/26. These include enhancing health infrastructure, addressing workforce production, quality and distribution, integrating health information systems, ensuring specialist care for MNH services, improving quantification and procurement of commodities, sustaining the gains of MNH care through improved ANC, labour and delivery, and newborn care, and increasing advocacy for domestic resource mobilization and allocation for the health sector.

Strategic Approach for Beginnings Fund Investments

In partnership with the Government of Tanzania, Beginnings Fund investments aim to accelerate the reduction in maternal and neonatal mortality and prevent stillbirths to reach Tanzania’s 2030 goals and save ~ 51,334 lives (newborn lives 30,930, stillbirths 19,587, maternal lives 3,111).  Beginnings Fund investments will support the rollout of priority interventions targeted at the drivers of maternal and neonatal mortality; improve the availability and use of quality MNH commodities; increase the number, competency and distribution of the MNH health workforce, and improve MNH systems; including infrastructure, data systems, emergency referral and transport, advocacy, and leadership and management.

Given considerable progress to date in reducing maternal mortality, the strategic focus of Beginnings Fund investments will be to enhance the quality of intrapartum care and expand access to quality Level 2 newborn care at district level. The high number of stillbirths (~40,945) and neonatal deaths (~51,334), annually, averaging 253 deaths per day, requires considerable additional resources and attention.  Beginnings Fund will focus investments where the majority of neonatal deaths and stillbirths occur.

Analysing where the majority of stillbirth and neonatal deaths occur, and mapping against available resources, Beginnings Fund will target 12 regions with high-volume facility deliveries, and a high burden of stillbirths and neonatal deaths: Mwanza, Tabora, Dar es Salaam, Kagera, Simiyu, Mara, Dodoma, Morogoro, Shinyanga, Mbeya, Ruvuma and Mtwara. These regions account for 58% of facility deliveries, 60% of stillbirths, and 68% of neonatal deaths.

Beginnings Fund will target focus regions  with a differentiated approach to maximize impact, reaching a total of 210 high-volume facilities.  In the five highest-burden regions – Mwanza, Tabora, Dar es Salaam, Kagera, and Simiyu – intensive support will use a hub and spoke approach to reach all facilities (130) with more than 1,000 annual deliveries to reach 48% of total facility deliveries. In an additional seven high-burden regions – Mara, Dodoma, Morogoro, Shinyanga, Mbeya, Ruvuma and Mtwara - targeted support for 80 hubs (district hospitals and high-volume health centers) with more than 2,000 deliveries will reach 36% of total facility deliveries.

To improve antenatal care, focus facilities will be supported with the catalytic procurement of point-of-care diagnostics, including reagents, to facilitate early identification and management of infections, anemia, hypertension, and diabetes. Point-of-care ultrasound (POCUS) will be introduced at dispensaries and health centres to improve risk-differentiated care through training and mentoring of nurse-midwives, engaging with the MOH and the Tanzania Nursing and Midwifery Council around scope of practice.

To improve intrapartum care and better identify foetal distress for early intervention, digital intrapartum technologies, including foetal monitors and CTG devices, will be introduced, accompanied by uptake of the labour care guide. Improving capacity for assisted vaginal deliveries will be enhanced by equipping facilities and strengthening capacity through simulation based training. The rollout and uptake of the WHO-recommended PPH bundle will be supported nationally through catalytic procurement and onsite mentorship. To address the 80% of maternal deaths linked to unsafe surgery and anaesthesia, an innovative quality improvement approach will be employed for obstetric surgery safety improvement, targeting regional referral hospitals as key training hubs. New higher diploma courses for nurse anaesthetists, theatre managers and midwives, will be established, with graduates formally recognized in the scheme of service.

To improve newborn care, immediate Kangaroo Mother Care (iKMC) practice, and enhance neonatal resuscitation and stabilisation, newborn corners in delivery rooms and operating theatres will be equipped. To increase access to quality Level 2 newborn care in district hospitals and CEmONC health centres, neonatal care units will be equipped, and clinical and biomedical staff will receive onsite mentorship to improve coverage of key interventions. In the five intensive focus regions, 25 additional neonatal care units will be constructed in line with MOH guidelines for zero separation. To rapidly improve newborn care, 1,000 neonatal nurses will be trained through a three-month course at national and zonal hospitals.

Scale-up of the above interventions will be implemented through the rollout of the national MNH mentorship package (the Safer Birth Bundle of Care Plus (SBBC+). The SBBC+ package adapts the Safer Birth Bundle of Care approach implemented by Haydom Lutheran Hospital which improved intrapartum and early newborn care through low-dose high-frequency (LDHF) simulation-based training, to include antenatal care and small and sick newborn care (SSNC). The MOH seeks to update the package with point-of-care ultrasound (POCUS), CTG, the post-partum haemorrhage bundle, and iKMC.  SBBC+ will be implemented through a hub and spokes mentorship model, cascading from national to regional mentors and facility champions. The MOH has requested support to update the package, harmonize best practices in simulation, quality improvement (QI), and equipment use, expand mentor pools at national and regional level and equip facilities, building on support from GFF in two regions.

Cross-cutting investments will also be deployed to strength the availability of priority MNH products nationally, increase the number quality and distribution of the health workforce, and advance health system enablers, including infrastructure, data systems, emergency referral and transport and advocacy.

All 210 focus facilities will be equipped with clinical and simulation equipment and a buffer stock of consumables, procured and distributed via the Medical Stores Department (MSD), with warranties, spare parts, installation training, and maintenance support.

New or under-utilized MNH products will be introduced, including updating standard treatment guidelines and the Essential Medicine List, supporting regulatory approval, and harmonisation with MSD. To improve bottom-up quantification, pharmacists will receive training and AI-enabled tools integrated into the electronic Logistic Management Information System (eLMIS). National quantification and forecasting for MNH commodities will be supported.

To increase staff-to-patient ratios in targeted maternity and neonatal units, additional health workers will be supported in the five intensive regions. Support for post-graduate training of specialist MNH cadres will improve quality of care, and distribution and retention through strategic selection of trainees from high-burden and under-resourced regions, and support for optimal deployment, as well as establishing hospital-based fellowships.  To enhance training institution capacity, departments that produce cadres critical to MNH services willj be strengthened through faculty training in the latest guidelines and evidence. Workforce planning through further development of the national Human Resource for Health Information System (HRHIS) will enhance planning, deployment, monitoring, and decision-making.

Maternal-newborn indicators to better measure quality of care will be integrated in the national electronic medical record systems (EMRs), GOTHOMIS and Afya eHMS, and focus facilities will be equipped with ICT infrastructure and connectivity to enable utilisation. The EMRs will be configured to automatically generate and transmit standardised indicator data into DHIS2 for aggregate reporting to reduce the reporting burden and improve data consistency between systems. The national health dashboard will be strengthened to include MNH, tracking coverage of key interventions, workforce, commodities, and emergency transport and referral investments.. Real-time digitisation of MPDSR in DHIS2 will be strengthened to enable a more rapid response, including the better capture of perinatal deaths.

Advocacy with key decision-makers to prioritise the MNH acceleration agenda is planned, as well as engaging the private sector to mobilize resources for neonatal infrastructure and equipping, advocating with district and regional councils to scale and sustain investments as well as engaging health workers and patients on the key practices to facilitate zero-separation, iKMC and birth companionship. Leadership and management training for national MNH technical leads, and Regional and Council Health Management Teams (R/CHMTs) will be supported. The key national technical working groups will receive support.

Implementation Approach

The implementation approach was co-designed with the MOH, PMO-RALG and MSD, and will be managed through a consortium of government and technical partners selected based on their track record of MNH delivery. To ensure supported interventions are embedded in government systems from inception, the MOH and PMO-RALG will lead implementation across the investment plan objectives. Technical support partners will provide support to the lead government agency or parastatal as outlined in the table below.

Governance and Program Management: Partnership roles and responsibilities were negotiated between the government and technical partners with clear scopes of work and mutual accountability, which requires close coordination. A governance structure and program management process (see Annex B) will facilitate collaboration. Overall accountability is with the MOH’s Department of Planning and Policy Development (DPPD), with technical leadership and program delivery responsibility with the MOH Division of Reproductive Maternal and Child Health (DRMCH), and the PMO-RALG Division of Health, Social Welfare, and Nutrition (DHSWN).

Ifakara Health Institute (Ifakara) will support the MOH DPPD to manage program coordination, M&E and reporting, with joint workplans to foster transparency, accountability, and provide data-driven analysis to monitor progress.

Figure 1: Government Lead by Objective, and Technical Support Partner roles

Objectives and Operational Plan

The overall aim is to reach 2030 goals and save ~53,628 lives by:

- reducing maternal mortality by 33% from 104 to 70 per 100,000 live births

- reducing stillbirths by 33% from 18 to 12 per 1,000 live births

- reducing neonatal mortality by 50% from 24 to 12 per 1,000 live births

The following activities will be supported through Beginnings Fund investments (see grantee investment memos for detailed plans).  In each region, the targeted facilities will be validated at inception with the R/CHMTs, and a baseline health facility assessment conducted to inform the scope of activities. Outlined below against each objective, are a) government policy alignment, b) the amount of Beginnings Fund investment, c) government co-investment and commitments, d) key implementing partners and their co-investment, and e) complementary investments that will advance planned support.

Objective 1: Scale-up of evidence-based interventions to address the primary drivers of maternal mortality, stillbirths, and neonatal mortality

Policy Alignment: One Plan III 2.1, 3.3, 3.3.1, MoH 2025/2026 Budget Priorities: strengthening preventive and curative services Beginnings Fund Investment: USD18million Government Commitment: USD59.6million. Incorporate priority MNH interventions outlined in this investment plan in HSPP VI and One Plan IV 2026/27- 2030/31 and align domestic and external financing for greater scale. Government Lead: MOH DRMCH, RHMT and CHMTs in focus regions Technical Support Partners: Ifakara and Haydom Technical Support Partner Co-Investment: USD5.1million Complementary Investments: Thamini Uhai will support a similar package of interventions in Geita, Kigoma and Katavi regions

Beginnings Fund will provide support for the following activities in 210 high-volume facilities in 12 regions:

  - Procure point-of-care antenatal care diagnostics, including reagents and facilitate uptake for early identification and management of infections, anaemia, hypertension, diabetes.

  - Introduce point-of-care ultrasound (POCUS) to improve risk-differentiated care

  - Improve the uptake of antenatal corticosteroids enabled by POCUS gestational age dating

  - Introduce digital intrapartum and foetal monitoring technologies

  - Provide simulation-based mentorship on assisted vaginal delivery

  - Roll out the PPH bundle to prevent and treat post-partum hemorrhage through on-site mentorship

  - Improve obstetric surgery and anaesthesia skills through a QI approach utilising the safe surgical checklist and team-based methods, in regional referral hospitals serving as hubs for dissemination.

  - Establish newborn corners in all delivery rooms and operating theatres to improve essential newborn care, iKMC, neonatal resuscitation and stabilization

  - Expand Level 2 newborn care in district hospitals and high-volume CEmONC health centers by training clinical and biomedical staff, and improving practice through data-driven QI cycles

  - Implement interventions through the SBBC+ approach by harmonizing the package to include evidence-based practices and train 70 National Trainers, 360 regional mentors and 2,980 facility champions to provide onsite clinical and QI mentoring, and simulation-based LDHF training for ~10,000 staff .

At national level:

- Update national guidelines to include new evidence (antenatal care, MPDSR, EmONC Job Aid, POCUS, Neonatal Guidelines, Paediatric Standard Treatment Guidelines).

- Provide secretariat support to key national TWGs to enable data review and mobilization of other actors for further scale (RMNCAH, Newborn and Child Health and M&E)

Objective 2: Increase the availability and use of quality priority MNH commodities

Policy Alignment: One plan III 2.3 MoH 2025/2026 Budget Priorities Beginnings Fund Investment: USD15million Government Commitment: USD14.1million. Increase the annual budget for MNH commodities to reduce the gap between quantified need and projected expenditure to <10% by 2029/30. Integrate new MNH products in standard treatment guidelines, procurement catalogues, essential medicines list, and annual budgets. Government Lead: MOH PSU and Medical Stores Department Technical Support Partner: R4D at national level, InSupply in focus regions, Ifakara for equipment procurement Technical Support Partner Co-Investment: USD2.3million Complementary Investments: JICA, Global Affairs Canada

Beginnings Fund will support the following activities in 210 high-burden facilities in 12 focus regions:

- Equip 210 facilities with POCUS, digital intrapartum monitoring, EMONC, and SSNC equipment and consumables and simulation training equipment (See Annex D)

- Increase uptime of MNH equipment >80% by equipping biomedical engineers with tools and workshops to support planned preventive maintenance and repair of MNH equipment

- Strengthen capacity of 2,374 pharmacy staff by training on stock management and improve 200 pharmacy stores through minor renovations and furnishing

- Strengthen bottom-up quantification by rolling out AI-enabled tools in the electronic Logistics Management Information system (eLMIS) to improve forecasting and quantification

At national level:

- Introduce new and priority MNH products (caffeine citrate, POCUS, CTG, heat-stable carbetocin, detection drapes, surfactant), support catalytic procurement, update standard treatment guidelines, support regulatory approval, harmonization with MSD, and inclusion in forecasting and quantification

- Develop and institutionalize a standardized list of priority MNH medical devices, diagnostics, and consumables to reduce fragmentation and improve procurement efficiency

- Include MNH priority products the new universal health insurance minimum benefits package

- Mobilize higher levels of external financing for MNH commodities, including match opportunities

- Increase domestic budgetary resources for MNH commodities for sustainable financing

Objective 3: Strengthen and expand the quality, number, and distribution of the MNH workforce

Policy Alignment: One Plan III 2.2 MoH 2025/2026 Budget Priorities Beginnings Fund Investment: USD13.4million Government Commitment: USD9.3million. In addition, the Government of Tanzania commits to: - Select trainees for scholarship support on agreed criteria, continue salaries, and bond for period of training - Deploy MNH graduates to maternity and neonatal units in public and faith-based facilities in focus/under-resourced regions - Recruit and deploy additional health workers to focus maternity and neonatal units in Mwanza, Dar es Salaam, Tabora, Kagera and Simuyu, and absorb on agreed timelines - Maintain increased staff: patient ratios in targeted maternity/neonatal units in focus districts - Reduce rotation of trained staff from maternity and neonatal units in focus facilities to <5% annually Government Lead: PMO-RALG -employment of health workers; MOH DRHD– scholarships and workforce planning Technical Support Partner: Benjamin Mkapa Foundation Technical Support Partner Co-Investment: to be determined Complementary Investments: UNFPA for midwifery training institutions. Thamini Uhai will support upgrading of health workers in anesthesia, theatre management by upgrading teaching hospital/health center facilities in Mwanza region.

Beginnings Fund will provide support for the following activities in five intensive focus regions:

- Improve staff: patient ratios in targeted maternity and newborn units by funding PMO-RALG to recruit ~500 additional health workers and absorb on agreed timelines, prioritizing neonatal care units.

At national level, Beginnings Fund will provide support for the following activities:

- Provide scholarships to train 550 MNH specialists: OBS/GYN, Anaesthesia, Paediatrics, Neonatology, Advanced Midwifery, Biomedical Engineering, and midwifery, anesthesia, and theatre management

- Develop and scale-up short-course (9 weeks) neonatal nurse training for 1,000 neonatal nurses

- Establish ECSA hospital training and train 92 pediatricians, OBS/GYN, anaesthesiologists, midwives

- Conduct workforce planning with the MOH to improve distribution and skill-mix of MNH cadres nationally, further develop the HRHIS to enhance deployment, monitoring, and decision-making.

Objective 4: Strengthen other critical health system enablers, including MNH infrastructure, data systems, emergency transport and referral systems, and advocacy for greater impact.

Policy Alignment: One plan III 2.4, 3.3.1 MoH 2025/2026 Budget Priorities Beginnings Fund Investment: USD20.3million Government Commitment: USD78.4million. Absorb additional ICT staff in the MOH, and data officers in focus regions by Year 4. Lead integration of the maternal-newborn dataset into Afya eHMS and GOTHOMIS. Update neonatal protocols in m-mama. Government Lead: PMO-RALG – ICT for GOTHOMIS; MOH – ICT and M&E for Afya HMS Technical Support Partner: Ifakara, Doris Mollel Foundation, Vodafone Foundation Technical Support Partner Co-Investment: USD800,000 Complementary Investments: UNICEF is supporting GOTHOMIS improvements

- Improve maternal and neonatal infrastructure in focus facilities in five intensive focus regions:

- Construct neonatal care units in up to 26 district hospitals and CEmONC health centres, and make minor renovations to up to 22 maternity units. Construct/renovate 16 biomedical workshops

- Support the integration of maternal and neonatal inpatient data (M-NID) into national EMRs

  - Provide technical support to the MOH and PMO-RALG ICT and M&E departments to support integration in Afya eHMS, GOTHOMIS and procure ICT devices for focus facilities

  - Develop and manage integrated dashboards for quality improvement and program monitoring

- Advocate for MNH resources and best practices

  - Engage patients and providers on zero separation, iKMC and birth companionship through social media and district and facility outreach

  - Mobilize the private sector to provide match funding for neonatal infrastructure and equipment

  - Work with district councils to budget for resources to sustain and further scale interventions

- Strengthen MOH and PMO-RALG leadership and management capacity to sustain improvement

  - Provide technical support in focus districts to ensure Comprehensive Council Health Plans include MNH priorities and budgeting for commodities, workforce and infrastructure development.

  - Support the MOH DPPD with MNH health financing capacity strengthening to enable budgeting and tracking of MNH expenditure, analysis of financing gaps and improved resource mobilization

  - Support leadership and management training for national, regional and district MNH leaders

Country Budget and Sources

Of the total budget of USD75.4million, USD43.2million (57%) is presented, USD31.2million (35%) is in the pipeline. Key cost drivers are scaling up priority MNH interventions (Objective 1) at 23% of the budget and improving the availability of MNH Products (Objective 2) at 24%, including USD15million (20%) to equip sites. Beginnings Fund will work with the MOH and Ifakara (NEST) at program outset to conduct a rapid equipment procurement directly, utilizing Hatch Technologies. Subsequent procurements following health facility assessments, and to equip and furnish newly constructed neonatal units, will be channelled through the Medical Stores Department. System enablers (Objective 4) at USD15.5million is 22% of the budget, led by infrastructure at USD10.5million (14%), and M&E and data systems (6%).  Increasing MNH Workforce (Objective 3) is 20% of the total budget,.  Program Management costs total 7%, indirect costs for technical support partners are 3%, and there is a 1% contingency.

Of the total budget, USD29.9million (40%) will go to the Government of Tanzania and USD44.4million (59%) to partners. A total of USD175.2million of co-investment will be leveraged, of which USD167million is government co-financing outlined in Annex E.

Monitoring, Evaluation and Learning (MEL)

The Beginnings Fund will provide support to the MOH and PMO-RALG to integrate a maternal-newborn inpatient dataset co-developed with maternal and newborn stakeholders from Beginnings Fund focus countries, in GOTHOMIS and Afya eHMS, and support the integration of aggregated data into DHIS2. GOTHOMIS is centrally hosted, and therefore, the deployment of any improvements will be beneficial beyond the health facilities of focus. The GOTHOMIS and Afya eHMS teams are developing a unique identifier generation system that will allow tracking of patients across the levels of the health system. The MOH and PMO-RALG will co-design and develop the maternal and newborn sections of the national dashboards to track 1) quality of care 2) commodities and equipment, 3) workforce recruitment, training, and deployment, and 4) emergency transport and referral. This will create a unified evidence base upon which progress towards the Pathway to Impact in the Tanzania Investment Plan can be tracked (see Annex A).  Annual program reports will be integrated in this dashboard and tracked against the Pathway to Impact. Progress against program milestones will be monitored by the MOH, PMO-RALG, and technical support partners to identify early signs of success and ensure that strategies are adapted to evolving needs.

MOH structures, including national TWGs, will be supported to share results, exchange insights, and channel findings to scale MNH improvements nationally.  To ensure that improved MNH data translates into joint accountability across the health sector, the MOH will ensure that key indicators are incorporated into the MOH unified M&E framework and lessons are shared during health sector reviews at the facility, district, regional, and national levels, creating a strong foundation for continuous improvement and scale-up.

Risk and Reward

| Risks (Significance/Likelihood) | Mitigating Strategies |
| --- | --- |
| Changes in MOH leadership (Medium/High) Transitions for key MOH officials closely engaged during investment preparation may occur. | The Minister of Health changed following the October 2025 election. The technical leadership team that Beginnings Fund has engaged with remains in post. |
| Lack of coordination can result in fragmented implementation (High/Low) Various government entities and multiple partners own specific areas of implementation. | A Management Team (see Annex B) comprising government and partner leads will support coordination coordination. A program operational manual is being developed in Q1 2026 to support coordination and clearly outline roles and responsibilites between the government and partners. |
| Procurement, equipment or commodity delays (High/Medium) Delays in procurement and/or delivery of equipment and/or essential MNH commodities can hinder program activities. | A rapid equipment inventory assessment in focus facilities at program outset will support timely equipment procurement via Beginnings Fund directly to Hatch Technologies. MSD will work with MOH to improve forecasting for timely distribution of MNH medicines and supplies. |
| Human resource workforce limitations may hinder quality care (High/Medium) Tanzania’s staffing ratios do not currently meet WHO standards. It is also common for health workers to be rotated. This poses a risk that MNH specialized staff may be relocated. Leadership at the R/CHMT level is frequently transitioned. | Recruitment and deployment of additional staff will help optimize and monitor skilled staff allocations. A deep bench of facility champions will be trained, and there is government commitment to ensure that rotations will be kept to <5% of trained staff. Co-location in RHMT offices will support transitions. |

Risk/reward:  Medium-high risk/High reward: Tanzania is stable and has a rapidly growing economy.   At a minimum, Beginnings Fund investments reach ~7.3 million mother-baby pairs during the investment period, develop 430 national and regional mentors and 2,980 facility champions with comprehensive MNH, QI and simulation skills, supporting 10,000 health workers to deepen MNH competencies, increase the number of MNH specialists by 642 and in regional referral hospitals by 61%, train and deploy 1,000 neonatal nurses, sustain improved staff: patient ratios in maternity and neonatal units, integrate new effective MNH  products into routine systems, reduce stockouts of MNH commodities, equip 210 health facilities, upgrade 200 medical stores and train 2,000 pharmacists, while upgrading neonatal care unit infrastructure and biomedical workshops in 25 district hospitals and health centers.

Transition and Sustainability Plan

Beginnings Fund’s sustainability approach ensures government-led commitment at the outset.

To sustain and further scale-up of priority MNH interventions, mentor pools with robust skills will be available to support additional facilities and regions. Updated national guidelines and the SBBC+ package will create sustainable resources for capacity building and improved service delivery. A government-owned mentorship database will improve data-driven programming. Co-location of Ifakara and Haydom teams in focus regions will empower facility leaders to institutionalize monitoring, supportive supervision, and data review mechanisms to track progress and guide continuous improvement. Institutionalization of simulation training and QI will improve practice for successive cohorts of patients and health worker trainees. R/CHMTs will be supported to scale interventions to reach 80% of all deliveries in focus regions by 2030.

The majority of commodity procurement will be channelled through the MSD, to continue its growth in managing quantification, procurement and distribution of equipment, and ensure equipment is installed with appropriate training, spare parts, maintenance servicing, and warranties for sustained uptime and longevity, alongside training and equipping biomedical engineers for preventive maintenance.  New product introduction and addressing system gaps across policies, forecasting, quantification, and procurement processes will optimize national MNH commodity systems. Iincreasing the capacity of pharmacists in bottom-up quantification will enable rigorous quantification and forecasting. Government commitments, including increased budget allocations for MNH products will sustain new interventions such as POCUS, PPH bundle and SSNC.

Investment in the health workforce will increase the number, skill-mix, and distribution of MNH cadres to increase quality service provision for mothers and newborns immediately and over the long-term. Additional health workers will increase staff: patient ratios, and if absorbed by the government as planned, mother-baby pairs in maternity and neonatal units will continue to benefit from better service delivery.  Establishing hospital-based fellowships will improve distribution of specialists to underserved populations and improve care as the teaching hospital platform expands.  All health workers supported by Beginnings Fund supported scholarship to upgrade as MNH specialists will be eligible for increased salaries as all supported posts are within the scheme of service.   Key MOH and PMO-RALG national and district leaders will have their capacity strengthened in HRH planning, recruitment and equitable distribution for quality MNH services.

Significant data systems  improvements will outlive the period of investment. Strengthening Afya eHMS and GOTHOMIS centrally, to enable further deployment of MNH modules nationally, and facilitating interoperability and data integration with national systems and integration with the national health dashboard will enable ongoing evidence-based decision making.

Engaging leadership from RHMTs, CHMTs and District Engineers in directly supervising construction of neonatal care units, and engagement of end users, will enhance understanding of zero separation, birth companionship and iKMC, increasing district capacity in managing such projects. The use of standardized designs, participatory planning, and government-led oversight mechanisms will ensure the long-term functionality, usability, and scalability of infrastructure investments.

Responsible departments at both PMO-RALG and MOH will be strengthened to build sustainable capacity in program management and coordination, stakeholders’ engagement, resource mobilization, and data use for decision making and quality improvement. Commodity and workforce requirements to sustain new interventions such as POCUS, the PPH bundle and Level 2 newborn care will be included in Comprehensive Council Health Management Plans (CCHP) for sustainable financing.

Enhancing functioning of technical working groups and leadership and management capacity for technical officers at the MOH and PMO-RALG will improve national capacity in planning, resource allocation and performance monitoring. During the investment period, the MOH will develop the Health Sector Strategic Plan VI (1 July 2026-30 June 2031), and its related One Plan IV,  the strategic plan for reproductive maternal newborn child and adolescent health, which will serve as the blueprint to mobilize additional resources and reinforce alignment of development partner contributions for further scale-up of the evidence-based interventions in which Beginnings Fund is investing to additional regions.

Annex A: Pathway to Impact

By 2030:

- reducing maternal mortality by 33% from 104 to 70 per 100,000 live births

- reducing stillbirths by 33% from 18 to 12 per 1,000 live births

- reducing neonatal mortality by 50% from 24 to 12 per 1,000 live births

| Obj. 1: Priority interventions scaled to address drivers of maternal and neonatal mortality and stillbirths |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 210 facilities in 12 regions: Mwanza, Tabora, Dar es Salaam, Kagera, Simiyu, Mara, Dodoma, Morogoro, Shinyanga, Mbeya, Ruvuma and Mtwara with 520,369 deliveries annually: |  |
| - Updated national training package for integrated MNH (SBBC+) by end month 3 - A national pool of 70 mentors9 trained on SBBC+ package by end month 6 - National mentorship database established that includes facility training and clinical data, and clinical logbooks for each mentee by end month 9 - A pool of 30 mentors per region (360 total) with competencies in above established by end Year 1 - At least 2,000 facility champions identified, trained and mentored onsite in antenatal, labor and delivery and newborn care and simulation facilitation and quality improvement in focus facilities by end Year 1 - Data-informed mentorship visits reach ~10,000 health workers in target facilities as scheduled (quarterly in Years 1-3, and bi-annually in Years 3-4) | - >80% of 210 facilities (disaggregated by type, EMoNC designation) meet EmONC signal functions by end Year 2 - >80% of health workers (~10,000) in targeted maternity and newborn units (210) achieve EmONC and SSNC competency by end Year 3 (target to be determined post-baseline assessment) - Low-dose high-frequency simulation-based 1) skill drills (90% of individual level maternity and neonatal health workers practice daily) and 2) team training (90% of maternity and neonatal unit levels train and debrief weekly based on data-informed gaps) practiced at 90% of facilities by end Year 3. - Data-informed quality improvement cycles practiced independently at 90% of maternity and neonatal units in focus facilities at a minimum frequency of at least one cycle per month per facility by end Year 3 Coverage of interventions increased to 80% by end Year 3: - % of pregnant women attending ANC screened for 1) anemia, 2) infection, and 3) high-blood pressure - % of women attending ANC who receive POCUS or U/S, with gestational age recorded on the first visit - % of women receiving quality intrapartum care and management of complications (Post-partum Hemorrhage (PPH), Sepsis, Pre-Eclampsia/Eclampsia and Obstructed labour) according to guidelines - % of women who received digital intrapartum monitoring in labor - % of eligible women with pre-term labor who received antenatal corticosteroids - % of women with PPH detected early (300ml-500ml blood loss) and WHO-recommended treatment bundle received - % of eligible babies who received neonatal resuscitation - % of eligible preterm and low birth-weight babies who receive iKMC - % of babies between 1000-1499g who receive prophylactic CPAP - % of eligible babies between 1500-1999g with respiratory distress who receive CPAP - % of babies with clinical jaundice who receive phototherapy - % of babies with suspected sepsis who receive parenteral antibiotics - % of babies not hypothermic on admission to the neonatal unit - % of babies not hypothermic at any time in the neonatal unit At targeted CEmONC facilities (baseline and targets for below indicators to be established by end Year 1 following baseline health facility assessment) - Increased % of women with direct obstetric complications who are definitively treated without outward referral - 90% of members of obstetric surgical teams achieve competency by end Year 3 (as measured by Objective Structured Clinical Exams) - 90% of facilities meet standard safety and infection prevention practices according to the Safe Surgical Checklist by end Year 3 - Less than 10% of post c-section surgical site infections while in-patient in the facility by end Year 3 Additional measures (baseline and target to be determined): - Reduced % of births in health facilities that are intrapartum stillbirths or livebirths followed by very early neonatal death - Reduced % of babies admitted to neonatal unit with a diagnosis of birth asphyxia |

| Obj. 2 Availability of quality MNH commodities improved in focus districts and at national level |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 210 facilities in 12 regions: Mwanza, Tabora, Dar es Salaam, Kagera, Mara, Dodoma, Morogoro, Shinyanga, Mbeya, Ruvuma and Mtwara and national support |  |
| - 100% of facilities provide package of ANC diagnostics by end Year 1 - 100% of facilities equipped with POCUS and priority MNH products by end Year 1 - >80% of facilities with all tracer commodities to perform EmONC as designated by end Year 1 - Planned preventive maintenance for MNH devices conducted according to guidelines by end Year 2 | By end of Year 3 - 90% inventory accuracy of priority MNH products, as measured by store ledger vs. physical count data. - <10% stockouts of critical MNH products in targeted facilities by end Year 3 - >80% uptime of antenatal, intrapartum, and small and sick newborn care devices by end Year 3 |
| At national level |  |
| By end Year 1: - Timely procurement, clearance, and distribution of Beginnings Fund-funded priority MNH products (see Annex D) completed by end Year 1 - Identification of critical gaps impeding new product intro and scale-up in all regulations and policies relevant for MNH product provision by end Year 1 | - Variance between the forecasted and actual demand for MNH products reduced to <15% by end Year 5 - Decreased gap between quantified need for MNH commodities and budget (government + donors) to <10% by end Year 5 - 90% of targeted facilities budgeting for essential MNH products costs based on actual need by end Year 5 - 100% inclusion of new products in relevant regulations and policies - 100% standardization of existing products in regulations and policies - 100% inclusion in standardized list of priority medical devices - 100% costing and recommendation for inclusion in universal health insurance standard benefits package |

| Obj. 3 Improved quality, number, distribution of MNH workforce in focus districts and at national level |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| In 123 facilities in Mwanza, Tabora, Dar es Salaam, Kagera, Simiyu: |  |
| - Up to 300 additional health workers in Group 1 (doctors, clinical officers, nursing officers, assistant nursing officers, biomedical technologists) recruited and deployed as government contractual workers by end Year 1 - Up to 200 additional health workers in Group 2 (doctors, clinical officers, nursing officers, assistant nursing officers, biomedical technologists) recruited and deployed as government contractual workers by end Year 3 | - 90% of targeted maternity and neonatal units achieve sustained staff: patient ratios of 1:12 by end Year 2 (Group 1) and end Year 4 (Group 2) (target to be determined post-baseline assessment) - 80% are absorbed in government employment system within one month of completion of two-year contract period (240 in Group 1; and 160 in Group 2) - 10% of those not absorbed continue as contractual employees at the same designated facilities Across all target regions: - % of targeted CEmONC facilities (188) that have requisite skills-mix of MNH specialists (midwives, anesthetists, theatre nurses, pediatricians, OBS/GYN) by end Year 5 (target to be determined post-baseline assessment) |
| At national level: |  |
| - New higher diploma nurse training programs established for Midwifery, Operating Theatre management, and Anesthetist Nursing at three training institutions with capacity to train 25 per cohort by end Year 1 - ECSACOG training established at 8 regional or zonal hospitals by end Year 1 - ECSAPACH training established at 5 regional or zonal hospitals by end Year 2 - CANESCA training established at 3 regional or zonal hospitals by end Year 2 - ECSACONM Midwifery and Neonatal Nurse training established at 3 regional or zonal hospitals by end Year 2 | - 550 MNH specialists enrolled in post-basic/post-graduate training: 15 MMED OBS-GYN, 25 MMED Pediatrics 30 MMED Anesthesiology, 20 MSc Neonatology, 30 Master’s Midwifery, 30 Master’s Neonatal Nursing, 20 BSc Biomedical Engineering (upgrading for biomedical technicians), 150 higher diploma Midwifery, 80 higher diploma Operating Theatre management, 150 higher diploma in Anesthetist Nursing. - 95% are strategically selected according to Beginnings Fund-MOH criteria - 90% complete training and graduate within 12 months of program timeline - Increase in number of MNH specialists in the public sector (baseline to be determined) - 90% appropriately deployed to high-burden maternity and newborn units 90% retained in the public sector at 12 months post deployment - At least 92 MNH specialists enrol in ECSA-hospital based fellowship by end Year 2 at zonal and regional referral hospitals (OBS/GYN (48), pediatrics (20), anesthesiology (12), and advanced midwifery (12) - 90% complete training and graduate within 12 months of program timeline - Increase in number of MNH specialists in Regional Referral Hospitals and district hospitals in region of training (baseline to be determined) - 90% appropriately deployed to high-burden maternity and newborn units - 90% retained in the public sector at 12 months post deployment |

| Obj. 4: Critical health system enablers, including MNH infrastructure, data and quality, emergency transport and referral systems, leadership and management, and advocacy strengthened for greater impact and sustainability |  |
| --- | --- |
| Key Milestones | Outcome Indicators |
| Infrastructure: - Infrastructure assessments completed by end month 6 in five focus regions - Renovation and construction of up to 26 neonatal care units completed by end Year 3 - Construction of up to 11 Biomedical Engineering workshops completed by end Year 3 MNH Data Systems: - Conduct baseline (by end month 3) and endline Health Facility Assessment in 210 health facilities across 12 regions including tool adaptation, training, data collection and analysis - GOTHOMIS rolled out to all MNH service points (equipping with computers, tablets, internet) in 191 health facilities by end month 6 - M-NID data fully operational in GOTHOMIS by end Year 1 - Afya eHMS centrally hosted and functional in 19 regional referral hospitals by end month 6 - M-NID data fully operational in Afya eHMS by end Year 1 - M-NID data baseline established by month 18 - M-NID dashboard developed and at facility level by month 18 - Program monitoring dashboards for quality of care, workforce, and referrals developed and regularly used by MOH in focus facilities, districts and at national level by month 18 - Develop a program indicator matrix covering all implementing agencies and partners developed and completed quarterly - Annual data management and use through regional/council refresher data analysis/literacy training and mentorship at regional levels | Infrastructure: - Construction of 26 neonatal care units completed by end Year 3 in five intensive regions, equipped and furnished - Minor renovations completed to improve birth companionship and iKMC in up to 22 district hospitals and health centre (CEmONCs) - Biomedical workshops built and equipped in up to 11 facilities (target post baseline assessment) by end Year 3 - % increase in functional Level 2 neonatal units in five intensive regions (target at baseline) - % increase in biomedical workshops at district level in give intensive regions (target at baseline) - % increase in mother-baby neonatal units (target TBD at baseline) MNH Data Systems: - 90% of patient-level M-NID data meet program defined data quality and completeness criteria by end Year 3 - >95% of facilities utilize MNH dashboard for quality improvement and decision making by end Year 3 - 210 health facilities have maternal newborn dataset integrated and in use in either GOTHOMIS or Afya eHMIS by end Year 1 - >90% of the target health facilities in the 12 regions can exchange patient level data and allow for longitudinal follow-up by end Year 2 - >90% of the target health facilities in the 12 regions are integrated and submit data to the DHIS2, national MNH dashboard and central data warehouse by end Year 2 Advocacy - Increased knowledge and awareness among maternity unit and newborn care unit providers and patients on the benefits and key practices of iKMC and zero separation |

Annex B:  Governance and Program Management

Governance: A Steering Committee of government leaders and Beginnings Fund will meet biannually to review progress,  and address challenges. The Steering Committee will hold an annual meeting  alongside a national health meeting, to enable sharing learning with the World Bank/GFF, UN and bilateral agencies, STBF, Bloomberg Philanthropies, and other stakeholders.

Steering Committee Members:

- Permanent Secretary MoH (Co-Chair)

- Deputy Permanent Secretary (Health) PMO-RALG (Co-Chair)

- Permanent Secretary MOF

- Chief Medical Officer MOH

- Director of Policy and Planning MoH (Secretary)

- Director of Department of Reproductive Maternal and Child Health, MoH

- Director of Health, Social Welfare and Nutrition PMO-RALG

- Director MSD

- Chief Accountant – MOH

- CEO Beginnings Fund (or Program Director/Senior Country Program Officer)

Program Management: The implementation of the the country plan will be managed by a team comprised of the MNH technical leads of the MOH and PMO-RALG, and technical partner representatives. This team will meet monthly in Year 1 and quarterly thereafter to coordinate implementation and manage timelines, review progress and engender mutual accountability. Joint workplans and M&E tools will be developed to facilitate regular reporting and surface key insights and areas for engagement by the SteerCo.

Management Team representatives:

- MOH: Coordinator, DPPD,  Assistant Director, NCAH, Safe Motherhood Coordinator, Planning and Training Coordinator, DRHD, Chief Pharmacist, M&E Director, ICT Coordinator, Beginnings Fund Program Coordinator

- PMO-RALG: Director RMCAH, Coordinator, RMCAH, Chief Architect, ICT Director, Human Resources Director, Beginnings Fund Program Coordinator

- Ifakara Health Institute – Beginnings Fund Program Manager

- Haydom Lutheran Hospital –Program Manager and Program Lead

- R4D –Country Director

- InSupply –Country Director

- Benjamin Mkapa Foundation –Executive Director, Program Lead

- Doris Mollel Foundation –Executive Director

- Muhimbili National Hospital – lead neonatologist

- AGOTA and PAT – Executive Directors or Program Leads

- Muhumbili University of Health and Allied Sciences (MUHAS)-Digital Health Lead

- Beginnings Fund – Program Director and Senior Program Officer

Annex C:  Facilities Targeted for Infrastructure Improvement by Region and Partner

In the five intensive focus regions, three partners (PMO-RALG, Doris Mollel and Ifakara) will work simultaneously to build 25 new neonatal care units and 16 biomedical workshops at district hospitals according to MOH standards by level of facility for the below focus facilities. Facilities selected for infrastructure improvement are all high-volume district hospitals and health center (CEmONC) in the five intensive focus regions.  Facility selection will be validated with R/CHMTs at inception and site assessments completed to develop the final scope of work.

Annex D: MNH Commodities Budget

The total equipment budget presented is USD30.7 million, of which USD15million will be supported through Beginnings Fund and the remainder through in-kind support from the MBZ Foundation procuring from Hatch Technologies.

Annex E: Government of Tanzania Co-Investments by Source

Under the new cabinet formed after the October 2025 elections, the Regional Administration and Local Government ministry moved from the President’s Office to the Prime Minister’s office.

Key changes from the December 2025 Investment Committee presentation are reducing the amount to the Government of Tanzania from 59% to 40%, with some activities moving to techinal and implementing partners following agreement with the MOH and PMO-RALG.  Ifakara assumed some programme management costs for the MOH and PMO-RALG, an 11% budget increase, Haydom assumed the cost of training facility champions, 63% budget increase, and Benjamin Mkapa Foundation (pipeline) investment, assumed the costs of hiring and deploying additional health workers,  budget allocation increase from 700k to USD7.1m.  With learning from Malawi to facilitate early procurement of equipment, the budget allocation for commodity procurement to equip focus facilities was split, with USD5million allocated to Hatch Technologies, which Beginnings Fund will directly manage, and the remaining USD10million to Medical Stores Department. The budget allocations to AGOTA, Doris Mollel Foundation (DMF) (pipeline investments) are updated with latest budget information. DMF will build 4 neonatal units (increase from original 3).  Vodafone Foundation pipleline investment to improve neonatal emergency transport and referral under m-mama was removed from planned investments, due to shifts in their capacity to manage this activity in the updated timeline. There are no other changes to the operational plan presented in December 2025.

The Tanzania Demographic Health Survey (TDHS) 2022

Cochrane Database of Systematic Reviews, 2020

MPDSR Review 2018 -2023

WHO and UNICEF. Every Newborn Action Plan: Ending Preventable newborn deaths and stillbirths by 2030 (2020)

Kamala SR, et al. PLoS One. 2022;17

Juma, D., Stordal, K., Kamala, B. et al.  BMC Health Serv Res 24, 870 (2024).

Medium-Term Review of Health Sector Strategic Plan (HSSP V) 2021–2026

PMO-RALG Staff Recruitment and Deployment Plan

Tanzania’s population is projected to increase from 62 million to 129 million by 2050.

Bundala, et al, BMJ Glob Health. 2025;1–11.

USD285million is credit financing from the World Bank and USD33.5million is grant financing from GFF. Of the credit financing, USD260million is for Tanzania Mainland and USD25million is for Zanzibar.

MMR: 104 to 70 per 100,000 live births, SBR:18 to 12 per 1,000 live births, and NMR: 24 to 12 per 1,000 live births.

Neonatal deaths are under-reported in DHIS2, facility deliveries are included as proxy indicator.

Outcomes of the Safer Birth Bundle of Care program https://www.nejm.org/doi/full/10.1056/NEJMoa2406295

Technical partners will coordinate with the Muhimbili University of Health and Allied Sciences (MUHAS), which is funded by the Gates Foundation to provide technical support to the MOH and PMO-RALG to align the technical packages to ensure evidence-based interventions are incorporated, define success metrics, and advise policy updates.

Selection criteria: 1) trainees employed in public sector or faith-based facilities from focus and under-resourced regions 2) neonatal short-course training candidates from focus facilities, followed by other neonatal care units 3) ECSA-scholarship recipients must be based in region where training will take place 3 4) trainees agree to bonding for period of training.

Additional potential support from the Gates Foundation and Beginnings Fund in Sand Technologies for a health intelligence center, and Field on AI-enabled supply chain forecasting, will be coordinated to ensure alignment and integration.

This approach will evolve over Q1 2026, as the MOH and Gates Foundation invite Beginnings Fund and other MNH funders and partners to participate in the co-design of a planned investment in a health transformation unit embeded in the MOH to better cooridinate and manage health investments. Beginnings Fund welcomes the opportunity to coordinate scale-up of the MOH MNH package, introduce products nationally, and align workforce investments across the continuum of care, and from facility to community.